## Slide 1: Rel-19 Planning
SA1 chair & Rapporteurs
S1-230009

## Slide 2: Introduction
This set of slides aims to present the rapporteurs’ view regarding the planning for the remaining part of Rel-19 Stage 1 work
It takes into account:
  the updates and planning from SA1 Rapporteurs
  the information available at this time from the rest of 3GPP
SA1’s goal: SA1 normative work ready for the content package definition in Stage 2 (Sep-Dec 2023).

## Slide 3
3GPP Release 19 timeline
TSG#93-e
SA1 Stage 1 80%
100%
Note: All starting dates are indicative
TSG#94-e
TSG#95-e
TSG#96
TSG#97-e
TSG#98
TSG#99
TSG#100
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
RAN4
content def.
RAN Content def.
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
RAN Rel-19 workshop
SA Rel-19
Workshop (TBC)
Note: Other Rel-19 milestones/timelines to be specified (latest June 2023 for SA/CT)
SA St.2 Content approval
SA1 expected completion dates:
SA1#103 21-25 Aug 2023 80% normative ready
SA1#104 13-17 Nov 2023 100% normative ready

## Slide 4: Rel-19 Stage1 work - General overview
 | SA1#101 | SA1#102 | SA1#103 | SA1#104
Sensing |  |  |  | 
Ambient IoT |  |  |  | 
Metaverse |  |  |  | 
NetShare |  |  |  | 
FRMCS_Ph5 |  |  |  | 
RVAS |  |  |  | 
AIML_MT_Ph2 |  |  |  | 
5GSAT_Ph3 |  |  |  | 
UAV_Ph3 |  |  |  | 
DualSteer |  |  |  | 
EnergyServ |  |  |  | 
SOBOT |  |  |  | 
SID
WID
TR sent for approval
Normative WID presented
80% normative ready
TSG#99 Mar.
TSG#100 Jun.
TSG#101 Sep.
TSG#102 Dec.
100% normative ready

## Slide 5: FS_Sensing Progress
SID planning
  SA1#101 (Feb 2023): 80%
    Remarks: last meeting for new use cases, update existing ones for using common terminology (e.g. Sensing transmitter, sensing receiver), resolve EN. Initial consolidation. Send TR for information.
  SA1#102 (May 2023): 100%
    Remarks: consolidation, conclusions, resolve EN.
    Send TR for approval
  SA1#103 (Aug 2023)
    Remarks: Corrections if needed
  SA1#104 (Nov 2023)
    Remarks: None
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
950003 | Study on Integrated Sensing and Communication | FS_Sensing | 06/2023 | 65% | SP-220717
WID planning
  Intention of a following WID?
    Yes/No/Maybe
  If Yes,
    WID expected by SA1#102 (05/2023)
    Completion target
      80% normative ready – SA1#103 (08/2023)
      100% normative ready – SA1#104 (11/2023)
Others remarks:
  CC or email discussion would be scheduled for the end of January.

## Slide 6: FS_AmbientIoT Progress
SID planning
  SA1#101 (Feb 2023): 80%
    Remarks: Last meeting for new use case and updating. KPI consolidation and requirement consolidation. TR sent for approval.
  SA1#102 (May 2023): 100%
    Final consolidation. Propose WID.
  SA1#103 (Aug 2023):
    Remarks: maintanance work if needed
  SA1#104 (Nov 2023):
    Remarks: maintanance work if needed
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | Jun-23 | 65% | SP-220085
WID planning
  Intention of a following WID?
    Yes
  If Yes,
    WID expected by SA1#102 (May/2023)
    Completion target
      80% normative ready – SA1#103 (08/2023)
      100% normative ready – SA1#104 (11/2023)
Others remarks:
  Schedule 2 conference calls before SA1#101 meeting (Feb meeting) to discuss consolidation and possible new use cases.
  No new use cases in SA1#102.

## Slide 7: FS_Metaverse Progress
SID planning
  SA1#101 (Feb 2023): 75%
    Remarks: last meeting for use cases, last call for new requirements, initial consolidation. Send for information
  SA1#102 (May 2023): 95%
    Remarks: consolidation, resolve debated requirements / last chance for new requirements, close all ENs, aim for (partial) conclusions. Send for approval
  SA1#103 (Aug 2023): 100%
    Remarks: final clean up & last decisions (only for remaining open questions from SA1 102, captured in the FS_Metaverse Status Report). No new input to the study after this point.
  SA1#104 (Nov 2023)
    Remarks: corrections only
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
950005 | Study on Localized Mobile Metaverse Services | FS_Metaverse | 06/23 | 55% | SP-220353
WID planning
  Intention of a following WID?
    Yes
  If Yes,
    WID expected by SA1#102 (05/2023)
    Completion target
      80% normative ready – SA1#103 (08/2023)
      100% normative ready – SA1#104 (11/2023)
Others remarks:
  CC will be scheduled for late Jan to review input, and email discussion started 30.01
  The effectively concluded study in May will allow some input to the June SA Rel-19 workshop (if one is scheduled)
  Though at 55%, this progress was set due to lack of a cover sheet. Actual progress is ~65%.

## Slide 8: FS_Netshare Progress
SID planning
  SA1#101 (Feb 2023): 100%
    Remarks: Use cases Updates and consolidation work.
    Planning to send for approval on SA#99 (Mar 2023)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
950006 | Study on Network Sharing Aspects | FS_NetShare | Mar-23 | 75% | SP-220087
WID planning
  Intention of a following WID?
    Yes
  If Yes,
    First round of WID and CR expected by SA1#101 (02/2023)
    Completion target
      30% normative ready – SA1#101 (02/2023)
      100% normative ready – SA1#102 (05/2023)
Others remarks:
  None

## Slide 9: FS_RVAS Progress
SID planning
  SID finalized, TR 22.877 approved by SA#98-e
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
960015 | Study on roaming value added services | FS_RVAS | Dec-22 | 100% | SP-220442
WID planning
  Intention of a following WID?
    Yes
  If Yes,
    WID and CR expected by SA1#101 (02/2023)
    Completion target
      80% normative ready – SA1#101 (02/2023)
      100% normative ready – SA1#102 (05/2023)
Others remarks:
  None

## Slide 10: FS_FRMCS_Ph5 Progress
SID planning
  SA1#101 (Feb 2023): 60%
    Objective: 1 new UC
  SA1#102 (May 2023): 75%
    Objective: 2 UC updated + 1 new UC
  SA1#103 (Aug 2023): 90%
    Objective: 4 UC updated
  SA1#104 (Nov 2023): 100%
    Objective: SID objectives fully covered
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
950007 | Study on FRMCS Phase 5 | FS_FRMCS_Ph5 | 01/09/2023 | 50% | SP-220088
WID planning
  Intention of a following WID?
    Maybe
Others remarks:
  New UIC colleague starting in SA1#101 Athens meeting to contribute to FS_FRMCS_Ph5
  SID target completion plenary shifted from SA#101 (09/2023) to SA#102 (12/2023)
  If needed, WID to be performed in parallel

## Slide 11: FS_AIML_MT_Ph2 Progress
SID planning
  SA1#101 (Feb 2023): 80%
    Remarks: Last meeting for new use case and updating. And start consolidation work. Sent for information.
  SA1#102 (May 2023): 100%
    Remarks: Final consolidation of potential requirements. Propose WID. Sent for approval.
  SA1#103 (Aug 2023)
    Remarks: maintanance work if needed
  SA1#104 (Nov 2023)
    Remarks: maintanance work if needed
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
950008 | Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2 | Jun-23 | 50% | SP-220439
WID planning
  Intention of a following WID?
    Yes
  If Yes,
    WID expected by SA1#102 (May 2023)
    Completion target
      80% normative ready – SA1#103 (08/2023)
      100% normative ready – SA1#104 (11/2023)
Others remarks:
  None
  …

## Slide 12: FS_5GSAT_Ph3 Progress
SID planning
  SA1#101 (Feb 2023): 80%
    Updated/Additional Use cases and potential requirements
    Clean up/Consolidation
    Send TR to SA for information
  SA1#102 (May 2023): 100%
    Conclusion, Overview, TR corrections/clean-up
    Send TR to SA for Approval
    Final consolidation
    Propose WID
  SA1#103 (Aug 2023)
    Remarks: corrections if needed
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
960016 | Study on satellite access - Phase 3 | FS_5GSAT_Ph3 | JUN-23 | 55% | SP-220679
WID planning
  Intention of a following WID?
    Yes
  If Yes,
    WID expected by SA1#102 (May/2023)
    Completion target
      80% normative ready – SA1#103 (08/2023)
      100% normative ready – SA1#104 (11/2023)
Others remarks:
  CC or email discussion will be scheduled for late Jan/early Feb

## Slide 13: FS_UAV_Ph3 Progress
SID planning
  SA1#101 (Feb 2023): 70%
    Remarks: Input additional new use cases and update use cases and potential requirements; Last meeting for use case and new requirements; Progress consolidation and initial consolidation if possible;
    Send TR for information
  SA1#102 (May 2023): 90%
    Remarks: Aim to complete consolidation and conclusions if possible.
    Send TR for approval
  SA1#103 (Aug 2023): 100%
    Remarks: Complete consolidation and conclusions;
    Final TR clean to close all remaining ENs;
  SA1#104 (Nov 2023)
    Remarks: maintanance work if needed.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
960017 | Study on UAV Phase 3 | FS_UAV_Ph3 | 22/09/2023 | 45% | SP-220954
WID planning
  Intention of a following WID?
    Yes
  If Yes,
    WID expected by SA1#102 (05/2023)
    Completion target
      80% normative ready – SA1#103 (08/2023)
      100% normative ready – SA1#104 (11/2023))
Others remarks:
  CC or email discussion will be scheduled for late early Feb.

## Slide 14: FS_DualSteer Progress
SID planning
  SA1#101 (Feb 2023): 80%
    Updated/new Use Cases and requirements
    Start Consolidation
    Send TR to SA for information
  SA1#102 (May 2023): 100%
    Finalize requirements and consolidation
    Conclusions
    Send TR for SA approval
  SA1#103 (Aug 2023)
    Potential clean-ups & corrections
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
960018 | Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer | Jun-2023 | 60% | SP-220445
WID planning
  Intention of a following WID?
    Yes
  If Yes,
    WID expected by SA1#102 (May/2023)
    Completion target
      80% normative ready – SA1#103 (08/2023)
      100% normative ready – SA1#104 (11/2023)
Others remarks:
  Email discussion/coordination planned prior to Feb meeting

## Slide 15: FS_EnergyServ Progress
SID planning
  SA1#101 (Feb 2023): 70%
    Additional new use cases
    Update use cases and potential requirements
    Progress consolidation
    Send TR for information
  SA1#102 (May 2023): 100%
    Complete consolidation and conclusions and TR clean-up
    Send final TR for Approval
  SA1#103 (Aug 2023)
    Remarks: maintanance work if needed
  SA1#104 (Nov 2023)
    Remarks: maintanance work if needed
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
950005 | Study on Energy Efficiency as service criteria | FS_EnergyServ | 21/06/23 | 40% | SP-220446
WID planning
  Intention of a following WID?
    Yes
  If Yes,
    WID expected by SA1#102 (05/2023)
    Completion target
      80% normative ready – SA1#103 (08/2023)
      100% normative ready – SA1#104 (11/2023)
Others remarks:
  CC or email discussion will be scheduled for early Feb.

## Slide 16: FS_SOBOT Progress
SID planning
  SA1#101 (Feb 2023): 70%
    Remarks: add necessary terminology, add new use cases relating to (representative) application fields /scenarios with focus on collaborative operations of multiple robots (e.g., unstructured job site env., media communication for robotic applications, aerial/underwater and safety-critival env.)
    TR sent for information
  SA1#102 (May 2023): 90%
    Remarks: last meeting for new use cases, input on relations between existing and ongoing studies/features;
    last meeting for new questions to be opened which needs to be indicated as Editor’s Note
  SA1#103 (Aug 2023): 100%
    Remarks: clean-up, resolution of already identified issues only.
    TR sent for approval
  SA1#104 (Nov 2023)
    Remarks: corrections if necessary
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID
960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | Sep-23 | 40% | SP-220447
WID planning
  Intention of a following WID?
    Maybe (for a small set of key requirements)
  If Yes,
    WID expected by SA1#103 (08/2023)
    Completion target
      80% normative ready – SA1#103 (08/2023)
      100% normative ready – SA1#104 (11/2023)
Others remarks:
  CC or email discussion will be scheduled for late Jan/early Feb