## Slide 1: FS_Metaverse Status Update Localized Mobile Metaverse Services
Erik Guttman
Samsung
3GPP TSG-SA WG1 Meeting #101
Athens, Greece, 20 - 24 February 2023
Notes: 1

## Slide 2: <Acronym> Progress
Progress made at this meeting
  8 new use cases
  Several improvements and clean up
  Alignment of new terminology
New Work/Study Item Completion: 75%
Controversial issues
  None
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
940040 | Feasibility Study on Localized Mobile Metaverse Services | FS_Metaverse | 06/06/2023 | 55% | SP-22xxxx | 75% | 
Notes: 1

## Slide 3: Planning
  Guide: if WID is 100% complete or if SA1 agreed to stop the work, delete this slide
Planning for subsequent meetings
  Guide: information below is for guidance purposes, to give an idea of what work still remains and what percentage completion is expected
  SA1#102 (May 2023): <100%>
    Consolidation of requirements
    Conclusions
    Clean up and correction
Notes: 1

## Slide 4: Work plan between meetings
  Guide: this optional slide is an opportunity for rapporteurs to indicate what activities are proposed between meetings
Email discussion
  Requirement consolidation
  Beginning March
Telephone conference
  Requirement consolidation
  April
Notes: 1

## Slide 5: Completion Date
Current expected completion dates:
  For information: SA#100 (03/2023)
  For approval: SA#101 (06/2023)
Have these dates been changed at this meeting? <y/n>
  If yes, previous target completion dates:
    No
Notes: 1

## Slide 6: History
This WI has been <agreed/approved/revised> at <SA1#nn / SA#nn>
  <Agreed/Approved> WID is in tdoc <S1-xxxxxx / SP-xxxxxx>
History of completion rates
  SA1#100 (date): <55%>
  SA1#99 (date): <40%>
  <Until start of WI>
Notes: 1