## Slide 1: FS_NetShare Status Update Feasibility Study on Network Sharing Aspect
Qun Wei
China Unicom
FS_NetShare Rapporteur
3GPP TSG-SA WG1 Meeting #101
Athens, Greece, 20 - 24 February 2023
Notes: 1

## Slide 2: FS_NetShare Progress
Progress made at this meeting
  Numbers discussed this meeting are listed:
  TR ：
    -TR 22.851v1.0.0 Study on Network Sharing Aspects
  Study Item Completion: 80%
Controversial issues
  None.
S1-230579
S1-230746
S1-230361
S1-230580
S1-230067
S1-230781
S1-230782
S1-230583
Notes: 1

## Slide 3: FS_NetShare Planning
Planning for subsequent meetings
  SA1#102 (May) : <100%>
    Editorial Notes need to be processed.
    Update requirements and use cases according to the agreed definition of this meeting.
    The consolidated documents need to be submitted.
    Conclusion document need to be provided.
    Editorial modification, if necessary.
Notes: 1

## Slide 4: Work plan between meetings
  Email discussion
  Yes, consolidated documents need to be sent.
Telephone conference
  Mainly discuss the consolidated document.
Notes: 1

## Slide 5: FS_NetShare Completion Date
Current expected completion dates:
  For approval: SA#100 (6/2023)
Have these dates been changed at this meeting?
  Yes.
Notes: 1

## Slide 6: FS_NetShare History
This WI has been agreed at SA1#97e
  Agreed WID is in tdoc S1-220196
This WI has been approved at SA#95e
  Approved WID is in tdoc SP-220087
History of completion rates
  SA1#98e (9 – 19 May 2022): 10%
  SA1#99e (22 Aug – 1 Sep 2022): 20%
  SA1#100 (14 Nov – 18 Nov 2022): 75%
  SA1#101 (20 Feb – 24 Feb 2023): 80%
Notes: 1