## Slide 1
Process for
SA1 Rel-20 work planning
Source: SA1 Chair
Agenda item: 2
Document for: Information
© 3GPP 2023
S1-232653 (rev of S1-232009, S1-232550) - 3GPP SA1#103, 21 -25 August 2023, Gothenburg, Sweden

## Slide 2: Rel-20 planning – SA1 capacity
We aim the same capacity as Rel-19:
  corresponding to ≈ 12 SIDs if same size as the Rel-19 SIDs,
  or can be much less if one SID takes much more time (see e.g. SMARTER, which was one big SID for 5G study in Rel-14).

## Slide 3: Rel-20 planning – time sharing
Divide the Rel-20 content definition in two parts:
  Part 1 (≈50% of SA1’s time  around max. 6 SIDs) – Only studies with normative work aiming for Rel-20
    Window to present studies (2 meetings): SA1#104 (Nov) and SA1#105 (Feb)
    Window to agree studies (2 meetings): SA1#105 (Feb) and SA1#106 (May)
  Part 2 (≈50% of SA1’s time  from 1 big SID to max. 6 SIDs) – Priority given to studies with normative work aiming for beyond Rel-20. The work planning for this part 2 will be presented at SA plenary for endorsement.
    Window to present studies (2 meetings): SA1#105 (Feb) and SA1#106 (May)
    Window to agree studies (2 meetings): SA1#106 (May) and SA1 #107 (Aug)

## Slide 4
Release 20 SA1 work planning
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
TSG#106
TSG#107
TSG#108
TSG#109
TSG#110
TSG#111
TSG#112
TSG#99
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
TSG#100
June
2023
Now
SA1#102
SA1#103
SA1#104
SA1#105
SA1#106
SA1#107
SA1#108
SA1#109
SA1#110
SA1#111
SA1#112
Rel-20 part 1 (≈50%)
SIDs presentation
SIDs agreement
Rel -20 SA1 Stage 1
Rel-19 Stage 2
Rel-19 Stage 3
Rel-19 Stage 1
Rel-19 TSG Cont. Def
Rel-20 part 2 (≈50%)
presentations
SID(s) agreement
Grey boxes = SA 1 Content definition process
Release 19
Release 20
100%(TBC)
No decision yet from
TSG on timeline
80%(TBC)