## Slide 1: < FS_SOBOT > Status Report
Progress made at this meeting
  Editorial clean-up
  Admin sections: Overview, conclusions
  update on 5.1 Online cooperative high-resolution 3D map building
  update on 5.8 Communication support for a group of Mining robots
  Communications scenarios, relations to existing or recently completed studies
Controversial or Open issues from this meeting
  none
Planning for next meetings
  none
  Actions before next meeting
  none
Note: Big Thanks to all contributors and participants
Previous status report: S1-232580, @ SA1#103 S1-231743 @ SA1#102
  Rapporteur: <Name, company>
UID | Name | Acronym | Target | Old % | SID/WID | New % | Change or comment
960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | 09/09/2023 | 90% | SP-220447 | 100% | 
3GPP TSG SA WG 1 Meeting #104 – Chicago, IL, USA November 2023 S1-233516

## Slide 2: FS_AmbientIoT Status Report
Planning for next meetings
  SA1#102 (May 2023): 85%
    Remarks: Sending TR for approval
  SA1#103 (Aug 2023): 100%
    Remarks: final clean up
  Actions before next meeting
  email discussion to be started 30.05, and Conf Call will be scheduled for late June to review inputs
  Rapporteur: Jose Almodovar, KPN
Example – DELETE SLIDE
UID | Name | Acronym | Target | Old % | SID/WID | New % | Change or comment
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 06/06/2023 | 50% | SP-220085 | 75% | 
Copy-paste the 6 first fields from slide 3
If new target date, write “New target: dd/mm/yyyy”
If TR is sent to plenary: “TR for info/approval”
Provide a short technical description of what was agreed (on terminology, example of use cases, …). The text also serves as input for the SA1 report to SA plenary. No need to list tdoc numbers.
Progress made at this meeting
  Note: TR 22.840 already sent for information to SA plenary in December.
  7 new use cases introduced (e.g. among them: Electronic Shelf Label, Device permanent deactivation, Device acting as a controller in smart agriculture).
  Initial discussions on requirements and KPI consolidation.
Controversial or Open issues from this meeting
  Finish consolidated potential requirements.
  Agree conclusions.
  Resolve editor's notes.

## Slide 3: List of all SA1 ongoing Work Items (1/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
950003 | Study on Integrated Sensing and Communication | FS_Sensing | 09/09/2023 | 90% | SP-220717 |  | 
1000026 | Integrated Sensing and Communication | Sensing | 12/12/2023 | 0% | SP-230750 |  | 
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 12/12/2023 | 90% | SP-220085 |  | 
950005 | Study on Localized Mobile Metaverse Services | FS_Metaverse | 09/09/2023 | 90% | SP-220353 |  | 
1000028 | Mobile Metaverse Services | Metaverse | 12/12/2023 | 0% | SP-230509 |  | 
950006 | Study on Network Sharing Aspects | FS_NetShare | 09/09/2023 | 95% | SP-220087 |  | 
1000029 | Indirect Network Sharing | NetShare | 12/12/2023 | 0% | SP-230511 |  | 
950007 | Study on FRMCS Phase 5 | FS_FRMCS_Ph5 | 12/12/2023 | 80% | SP-220437 |  | 
1000031 | FRMCS Phase 5 | FRMCS_Ph5 | 12/12/2023 | 0% | SP-230512 |  | 
950008 | Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2 | 09/09/2023 | 95% | SP-220439 |  | 
1000030 | AI/ML Model Transfer Phase 2 | AIML_MT_Ph2 | 12/12/2023 | 0% | SP-230514 |  | 
960016 | Study on satellite access - Phase 3 | FS_5GSAT_Ph3 | 09/09/2023 | 90% | SP-220679 |  | 
1000024 | Satellite access Phase 3 | 5GSAT_Ph3 | 12/12/2023 | 0% | SP-230516 |  | 
960017 | Study on UAV Phase 3 | FS_UAV_Ph3 | 09/09/2023 | 95% | SP-220954 |  | 
1000032 | Uncrewed Aerial System Phase 3 | UAS_Ph3 | 12/12/2023 | 0% | SP-230518 |  | 
960015 | Study on roaming value added services | FS_RVAS | 12/12/2022 | 100% | SP-220442 |  | 
990051 | Roaming Value-Added Services | RVAS | 03/03/2023 | 100% | SP-230231 |  | 
960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | 12/12/2023 | 80% | SP-220447 |  | 
960019 | Study on Energy Efficiency as service criteria | FS_EnergyServ | 09/09/2023 | 90% | SP-230235 |  | 
1000033 | Energy Efficiency as Service Criteria | EnergyServ | 12/12/2023 | 0% | SP-230520 |  | 
960018 | Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer | 09/09/2023 | 90% | SP-220445 |  | 
DELETE SLIDE

## Slide 4: List of all SA1 ongoing Work Items (1/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
850044 | Study on Supporting of Railway Smart Station Services | FS_RAILSS | 08/09/2022 | 100% | SP-190838 |  | 
990053 | Study on Interconnect of SNPN | FS_ISN | 12/12/2023 | 30% | SP-230236 |  | 
990052 | Supporting UE Mobility for XR Services | XRMobility | 06/06/2023 | 50% | SP-230233 |  | 
990050 | Edge Computing for Industrial Scenarios | EDGINDUS | 03/03/2023 | 100% | SP-230229 |  | 
990049 | PS Data Off for IMS Data Channel Service | IMSDCDataOff | 03/03/2023 | 0% | SP-230227 |  | 
970044 | Multi-path relay | MultiRelay | 19/09/2022 | 100% | SP-220943 |  | 
970043 | Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services | DTT4MBS | 19/09/2022 | 100% | SP-220941 |  | 
970042 | MPS for Messaging services | MPS4msg | 19/09/2022 | 100% | SP-220939 |  | 
970041 | Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | 19/09/2022 | 100% | SP-220992 |  | 
980108 | Measurement Data Collection | MeasureData | 20/12/2022 | 100% | SP-221263 |  | 
1000025 | UE-to-UE multi-hop relay | UEMHopRelay | 06/06/2023 | 100% | SP-230521 |  | 
1000027 | NPN security considerations | SecNPN | 06/06/2023 | 100% | SP-230523 |  | 
DELETE SLIDE

## Slide 5: Guidance to write the Work Item Status Report
A Status Report shall be provided by the Rapporteur at the end of the SA1 meeting for all the ongoing (not-completed) WIDs
Only the first slide has to be provided. The other slides are supporting material.
About the table on the top of the template:
  The 6 first fields have to be a copy-paste of the information provided in the slide “List of all SA1 ongoing Work Items”
  The last 2 fields (in red) have to be completed by the Rapporteur
  This table is also used by all the other Working Groups in 3GPP
Other comments:
  In case both a Study and the corresponding Normative work are progressing in parallel, two Status Reports have to be provided: one for the Study, one for the Normative work
  If the target date is changed, use the same number for the day and the month (e.g. “09/09/yyyy” or “12/12/yyyy”) as to avoid confusion in day/month order. Or just write mm/yyyy.
DELETE SLIDE