## Slide 1
Review of the process to introduce 5G in SA1
José Almodóvar
SA1 Chair, KPN
S1-240011 3GPP SA1#105, Athens, Greece, 26 Feb - 1 March 2024
© 3GPP 2024

## Slide 2: Reminder on Initial 5G Timeline
5G was introduced in two releases in SA1:
  Rel-14: Studies only.
  Rel-15: Normative work (first 5G Release)
  Note: Since there was no official 3GPP name for 5G at that time, SA1 started its work by calling it “SMARTER” (for “New Services and Markets Technology Enablers”)
Other groups started about one year later (see next slide)
  Also with studies in Rel-14 and normative work in Rel-15

## Slide 3: 5G Timeline: SA1 / SA2 / RAN
2017
2015
2016
2018
RAN
SA2
SA1
FS_SMARTER (Rel-14)
SMARTER normative (R15)
FS_NextGen
5GS_Ph1 (normative)
FS_NR_newRAT
NR_newRAT (normative)
3GPP
Workshop
FS_SMARTER umbrella
building blocks
RAN level study
Joint TSG chair
5G timeline
contribution
(SP-150149)
Rel-14
Stage 1 freeze
Rel-13
Stage 1 freeze
Rel-15
Stage 1 freeze

## Slide 4: SA1 5G Planning, as per FS_SMARTER SID (simplified)
“Brain-storming” phase: develop use cases covering all possible types of scenarios and identify the related high-level potential requirements
  Step 1 started in February 2015.
  TR 22.891 ended having 74 Use Cases
Group the use cases with common characteristics
Select the main (i.e. 3 to 4) (groups of) use cases that SA1 will focus on
  The target for completion of Step 3 was September 2015.
  This resulted in the creation of the 4 BBs SIDs (next bullet and next slide).
Introduce individual Building Blocks SIDs for each of these main 3-4 (groups of) use cases. Identify the related system requirements and capabilities.
Consolidate the requirements of these 4 BB SIDs as to prepare for normative work.
  The target for completion of Step 5 was March 2016.
  Note that there was no common, single TR that contained all the consolidated 5G potential requirements.
Then start normative work after Step 5.

## Slide 5: FS_SMARTER and its Building Blocks
New Services and Markets Technology Enablers (FS_Smarter)
SID: SP-150142
TR 22.891
massive Internet of Things (FS_SMARTER-mIoT)
SID: S1-153204
TR 22.861
Critical Communications (FS_SMARTER-CriC)
SID: S1-153205
TR 22.862
enhanced Mobile Broadband (FS_SMARTER-eMBB)
SID: S1-153198
TR 22.863
Network Operation (FS_SMARTER-NEO)
SID: S1-153203
TR22.864
Note: FS_SMARTER initially scheduled to be completed by March 2016 but was extended to June 2016 (completed in SA1 at SA1#74, 9-13 May 2016).

## Slide 6: (FS_)SMARTER documents
FS_SMARTER documents:
  Initial work started by the creation of an Excel file
    to capture all different white papers and corresponding use cases on 5G
    By contrast with 6G, SA1 did not have a workshop for 5G
  One TR for FS_SMARTER, with one rapporteur
  Four TRs for the four BBs SIDs, with one rapporteur each
  Note: upon completion of the study phase, all the potential requirements were not combined into a single document and remained spread over the 4 BB TRs.
SMARTER documents:
  One TS for SMARTER (TS 22.261) (“Service requirements for the 5G system”), that covers all 5G main aspects, with one rapporteur
  Other TSs to cover specific aspects/verticals, e.g. TS 22.104 for “Service requirements for cyber-physical control applications in vertical domains

## Slide 7: Lessons learnt
Identify what worked well and not so well in SA1 when introducing 5G/SMARTER
  A drafting session is proposed to be held during at SA1#105
  All delegates involved in the process (2015 to 2017) are invited to join

## Slide 8
Thank you