## Slide 1: FS_EnergyServ_Ph2 Status Report
Rapporteur: Laurent-Walter GOIX (Nokia)
Progress made at this meeting
  TR cleanup agreed (S1-241318)
  4 pCR agreed:
    S1-241405: New use case on energy saving service for UE
    S1-241407: Dynamic service adjustment support based on energy information
    S1-241410: Carbon Certificates as a Service
    S1-241417: New use case on supporting information exposure and service adjustment based on energy supply mix
Controversial or Open issues from this meeting
  None
Planning for next meetings
  SA1#107:
    Scope
    Definitions of relevant terms
    New + updated use cases and potential requirements (recommended: ~60%)
  SA1#108: Start consolidation
  Actions before next meeting
  Potential ad-hoc call to be confirmed
UID | Name | Acronym | Target | Old % | SID/WID | New % | Change or comment
1030044 | Study on Energy Efficiency as Service Criteria Phase 2 | FS_EnergyServ_Ph2 | 03/2025 | 0% | SID | 25% | 
3GPP TSG SA WG 1 Meeting #106 – Jeju, Korea, 27-31 May 2024 S1-241420