## Slide 1: FS_eIBCD Status Update
Toon Norp
KPN
FS_eICBD Rapporteur
3GPP TSG-SA WG1 Meeting #64
San Francisco, CA, USA, 11 – 15 November 2013
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_eIBCD Status
Is this a new WI? No
This WI has been approved at SP#61
  Approved WID is in tdoc SP-130418
Notes: 1

## Slide 3: FS_eIBCD Progress
Progress made at this meeting
  TR skeleton and scope approved
  4 use cases approved
  1 temporary annex with scoping approved
  Decision to use the extended form for use cases
Work/Study Item Completion: 10%
Draft TR 22.807 Completion: 10%
Notes: 1

## Slide 4: FS_eIBCD Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 3
Number of slots requested for next meeting
  sum of plenary and drafting slots: 3
Number of Drafting session participants: x
Notes: 1

## Slide 5: FS_eIBCD Completion Date
Target completion date in WID: 08/2014 SP#65
Current target completion date: 08/2014 SP#65
Will target completion date be met? Yes
Expected date to send TR to SA plenary:
  For information: SA1#66 (05/2014)
  For approval: SA1#67 (08/2014)
Notes: 1

## Slide 6: FS_eIBCD Planning/Progress
Topics to focus on at SA1#65 (Jan 2014):
    Complete use cases
    Impact and interactions
    Potential requirements
Planning for subsequent meetings
  SA1#66 (May 2014)
    Complete potential requirements
  SA1#67 (Aug 2014)
    Conclusions
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  Alignments of use case contributions
  Tentative start date: <01/01/2014>
Notes: 1

## Slide 8: FS_eIBCD Progress Estimate
Estimated percentage completion:
  SA1#65 (Jan 2014): 40%
  SA1#66 (May 2014): 70%
  SA1#67 (Aug 2014): 100%
Notes: 1

## Slide 9: FS_eIBCD Agreed documents
List of agreed documents at this meeting:
S1-135219 | Rapporteur | Draft TR skeleton for FS_eIBCD
S1-135099 | Rapporteur | Draft scope statement for TR on FS_eIBCD
S1-135224 | InterDigital | eICBD Discussion paper
S1-135222 | Intel | eICBD use case: UE requests its MNO to help create IP connection to another UE
S1-135223 | Intel | eICBD use case: Automated IP Connection Establishment for UEs with Private IP Addresses
S1-135314 | Intel | eICBD use case: UE requests a Public IP Address from its MNO
S1-135147 | Interdigital | Proposed use cases for eICBD – General and Limited Backhaul
Notes: 1