## Slide 1: SEES Status Update
Toon Norp
KPN
SEES Rapporteur
3GPP TSG-SA WG1 Meeting #64
San Francisco, CA, USA, 11 – 15 November 2013
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: SEES Status
Is this a new WI? No
This WI has been approved at SP#61
  Approved WID is in tdoc SP-130505
Notes: 1

## Slide 3: SEES Progress
Progress made at this meeting
  Skeleton and scope agreed
  4 application related use cases approved
  Agreed to use the extended use case template
Work/Study Item Completion: 15%
Draft TR 22.853 Completion: 15%
Notes: 1

## Slide 4: SEES Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: ~3
Number of slots requested for next meeting
  sum of plenary and drafting slots: 3
Number of Drafting session participants: 41
Notes: 1

## Slide 5: SEES Completion Date
Target completion date in WID: 06/2014 SP#64
Current target completion date: 06/2014 SP#64
Will target completion date be met? No
Expected date to send TS to SA plenary:
  For information: SA1#66 (05/2014)
  For approval: SA1#67 (08/2014)
  It seems unlikely that the TR can be ready for information in 01/2014
  It is therefore proposed to move the completion date to SP#65
Notes: 1

## Slide 6: SEES Planning/Progress
Topics to focus on at SA1#65 (Jan 2014):
  Use cases
  Impact and interactions
  Potential requirements
Planning for subsequent meetings
  SA1#66 (May 2014)
    Use cases
    Consolidated potential requirements
  SA1#67 (Aug 2014)
    Consolidated potential requirements
    Conclusions
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  Align use cases, impacts and potential requirements
  Tentative start date: 01/01/2014
Notes: 1

## Slide 8: SEES Progress Estimate
Estimated percentage completion:
  SA1#65 (Jan 2014): 40%
  SA1#66 (May 2014): 70%
  SA1#67 (Aug 2014): 100%
Notes: 1

## Slide 9: SEES Agreed documents
List of agreed documents at this meeting:
S1-135167 | Rapporteur (KPN) | Draft TR skeleton for SEES
S1-135250 | Huawei | Relationship of SEES work with MOSAP and OMA
S1-135316 | Huawei | SEES Use Case on background traffic
S1-135328 | China Telecom | Use Case on user RAT type exposure
S1-135144 | Huawei | Use Case on real-time population movement exposure
S1-135334 | Huawei | Use Case on exposure of charging model choice
Notes: 1