## Slide 1: FS_MBSP Status Update
Eddy Hall
Qualcomm Incorporated
FS_MBSP Rapporteur
3GPP TSG-SA WG1 Meeting #65
Taipei, Taiwan, 20–24 January 2014
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_MBSP Status
Is this a new WI? No
This WI has been approved at SP#62
  Approved WID is in TDoc SP-130599
Notes: 1

## Slide 3: FS_MBSP Progress
Progress made at this meeting:
  Scope and Introduction agreed, based on WID
  3 use cases agreed
    Geotargetted Warning: where users are notified of the location of a specific incident
    Streaming Media: where users are provided with streaming media about a specific incident
    Download Media: where users are provided with download media about a specific incident
Work Item Completion: 40%
Controversial issues
  none
Notes: 1

## Slide 4: FS_MBSP Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 1
Number of slots requested for next meeting
  sum of plenary and drafting slots: 1
Notes: 1

## Slide 5: FS_MBSP Completion Date
Target completion date in WID: 06/2014 SP#64
Current target completion date: 09/2014 SP#65
Will target completion date be met? Yes
Notes: 1

## Slide 6: FS_MBSP Planning/Progress
Topics to focus on at SA1#66 (May 2014):
  Finalise use cases
  Derive requirements from use cases
  Investigate considerations
    Security
    Broadcast initialisation
Planning for subsequent meetings
  SA1#67 (Aug 2014)
    Consolidation of potential requirements
    Conclusion
    Finalize TR
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  Socialise any final use cases
  Derive requirements from existing use cases
Notes: 1

## Slide 8: FS_MBSP Progress Estimate
Estimated percentage completion:
  SA1#66 (May 2014): 70%
  SA1#67 (Aug 2014): 100%
Notes: 1

## Slide 9: FS_MBSP Agreed documents
List of agreed documents at this meeting:
S1-140113 | Rapporteur | Skeleton TR for FS_MBSP
S1-140279 | Rapporteur | TR22.815
S1-140280 | Qualcomm Incorporated | Introduction and Scope for FS_MBSP TR
S1-140298 | Qualcomm Incorporated | Use Case on geotargetted warning
S1-140302 | Qualcomm Incorporated | Use Case on Streaming Media
S1-140303 | Qualcomm Incorporated | FS_MBSP Use Case: Multimedia Download
Notes: 1