## Slide 1: IMS_Corp2 Status Update Transfer of ETSI business trunking specifications
Betsy Covell
Alcatel-Lucent
IMS_Corp2 Rapporteur
3GPP TSG-SA WG1 Meeting #66
Sapporo, Japan, 12-16 May 2014
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: IMS_Corp2 Status
Is this a new WI? no
This WI has been approved at SP#63
  Approved WID is in tdoc SP-140170
Notes: 1

## Slide 3: IMS_Corp2 Progress
Progress made at this meeting
  The initial transferred technical specification transfer was agreed
Work/Study Item Completion: 95%
Draft TS 22.519 Completion: 95%
Controversial issues
  none
Notes: 1

## Slide 4: IMS_Corp2 Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 1
Number of slots requested for next meeting
  sum of plenary and drafting slots: 1
Notes: 1

## Slide 5: IMS_Corp2 Completion Date
Target completion date in WID: 06/2014 SP#64
Is current completion date the same as above? n
  If not, current target completion date: 09/2014 SP#65
Will target completion date be met? n
Expected date to send TS to SA plenary:
  For information: SA1#66 (05/2014)
  For approval: SA1#67 (08/2014)
Notes: 1

## Slide 6: IMS_Corp2 Planning/Progress
Topics to focus on at SA1#66 (May 2014):
  Resolve the open issues remaining in S1-141148
Planning for subsequent meetings
  SA1#67 (Aug 2014)
    Resolve references and other cleanups identified in S1-141148
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  Draft CRs to 22.522.519, 22.228 and perhaps 22.101 and 21.509
  Tentative start date: 06/2014
Notes: 1

## Slide 8: IMS_Corp2 Progress Estimate
Estimated percentage completion:
  SA1#67 (Aug 2014): 100%
Notes: 1

## Slide 9: IMS_Corp2 Agreed documents
List of agreed documents at this meeting:
S1-141398 | Alcatel-Lucent | TS 22.519 Business Communication Requirements
Notes: 1