## Slide 1: FS_CATS Status Update Control of Applications when Third party Servers encounter difficulties
Eriko Yoshida
KDDI
FS_CATS Rapporteur
3GPP TSG-SA WG1 Meeting #67
Sophia Antipolis, France, 18-22 August 2014
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FC_CATS Status
Is this a new WI? <no>
Notes: 1

## Slide 3: FS_CATS Progress
Progress made at this meeting
  Agreed TR Skelton, Introduction/Scope
  Agreed use cases to describe “Soft” and “Hard” Third Party Server Failures
Work/Study Item Completion: 30%
Draft TR 22.818 Completion: 30%
Controversial issues
  None
Notes: 1

## Slide 4: FS_CATS Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 1
Number of slots requested for next meeting
  sum of plenary and drafting slots: 2
Number of Drafting session participants: ~25
Notes: 1

## Slide 5: FS_CATS Completion Date
Target completion date in WID: 12/2014 SP#66
Is current completion date the same as above? Yes
Will target completion date be met? No
  If not, change target completion date to:
    03/2015 SP#67
Expected date to send TR22.818 to SA plenary:
  For information: SA1#66 (12/2014)
  For approval: SA1#67 (03/2015)
Notes: 1

## Slide 6: FS_CATS Planning/Progress
Topics to focus on at SA1#68 (Nov 2014):
  Use cases
  Potential requirements
Planning for subsequent meetings
  SA1#69 (Feb 2015)
    Potential requirements
    Clean-up
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  Focus items in previous slide
  Tentative start date: 2014/09/01
Notes: 1

## Slide 8: FS_CATS Progress Estimate
Estimated percentage completion:
  SA1#68 (Nov 2014): 60%
  SA1#69 (Feb 2015): 100%
Notes: 1

## Slide 9: FS_CATS Agreed documents
List of agreed documents at this meeting:
S1-143094 | Rapporteur | TR Skelton for FS_CATS
S1-143094 | KDDI, KPN, Qualcomm, Intel, Mediatek | Scope for TR22.818
S1-143459 | Qualcomm Incorporated | CATS Conceptual Approaches
S1-143282 | KDDI, Qualcomm, Teliasonera, KPN, Mediatek, Intel, China Unicom | Use Cases for “Soft” and “Hard” Third Party Server Failures
Notes: 1