## Slide 1: FS_UC_SPOOF Status Update Service aspects for dealing with User Control over spoofed calls
Greg Schumacher
Sprint
FS_UC_SPOOF Rapporteur
3GPP TSG-SA WG1 Meeting #69
Sanya, China, 2-6 February 2015
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_UC_SPOOF Status
Is this a new WI? n
This WI has been approved at SP#63
  Approved WID is in tdoc SP-140074
Notes: 1

## Slide 3: FS_UC_SPOOF Progress
Progress made at this meeting
  Editorial cleanup
  Consolidation of requirements
  Conclusion
  Consideration of device capabilities
  Consideration of deployment penetration
Work/Study Item Completion: 100%
Draft TR 22.898 Completion: 100%
Controversial issues
  None
S1-150157
Notes: 1

## Slide 4: FS_UC_SPOOF Meeting Time
Number of slots assigned at this meeting
  sum of plenary slots: 1
S1-150157
Notes: 1

## Slide 5: FS_UC_SPOOF Completion Date
Target completion date in WID: 03/2015 SP#67
Is current completion date the same as above? y
Will target completion date be met? y
  If Expected date to send <TR/TS> to SA plenary:
  For approval: SA1#67 (03/2015)
S1-150157
Notes: 1

## Slide 6: FS_UC_SPOOF Agreed documents
List of agreed documents at this meeting:
S1-150097 | Sprint | UC_SPOOF considerations based on device capabilities
S1-150098 | Sprint | UC_SPOOF consideration on spoofed call detection deployments
S1-150210 | Sprint | Editorial cleanup of TR 22.898
S1-150262 | Sprint | UC_SPOOF potential requirements
S1-150262 | Sprint | UC_SPOOF conclusions and recommendations
S1-150264 | Rapporteur | Updates to TR 22.898
S1-150332 | Rapporteur | Cover page for presentation to SA#67 for approval
S1-150157
Notes: 1