## Slide 1: FS_MCDATA Status Update Mission Critical Data Communications
Emmanuelle Villebrun
French MoI
FS_MCDATA Rapporteur
3GPP TSG-SA WG1 Meeting #69
Sanya, China, 2-6 February 2015
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_MCDATA Status
Is this a new WI? yes
This WI has not been approved by SP
  The following slides assume approval at SP#67
Notes: 1

## Slide 3: FS_MCDATA Progress
Progress made at this meeting
  Discussion of SID
Work/Study Item Completion: 0%
Draft <TS/TR> 22.xxx Completion: 0%
Controversial issues
  None
S1-150312
Notes: 1

## Slide 4: FS_MCDATA Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 0
Number of slots requested for next meeting
  sum of plenary and drafting slots: 4
S1-150312
Notes: 1

## Slide 5: FS_MCDATA Completion Date
Target completion date in WID: <11/2015> SP#70
Is current completion date the same as above? Yes
Will target completion date be met? Yes
Expected date to send <TR/TS> to SA plenary:
  For information: SA1#71 (08/2015)
  For approval: SA1#72 (11/2015)
S1-150312
Notes: 1

## Slide 6: FS_MCDATA Planning/Progress
Topics to focus on at SA1#70 (Apr 2015):
  Discussion of initial use cases
  Skeleton
Planning for subsequent meetings
  SA1#71 (Aug 2015)
    Overview, requirements consolidation
  SA1#72 (Nov 2015)
    Final Consolidation
S1-150312
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  None
S1-150312
Notes: 1

## Slide 8: FS_MCDATA Progress Estimate
  Estimated percentage completion:
  SA1#70 (Apr 2015): 50%
  SA1#71 (Aug 2015): 90%
  SA1#72 (Nov 2015): 100%
S1-150312
Notes: 1

## Slide 9: FS_MCDATA Agreed documents
List of agreed documents at this meeting:
S1-150298 | French MoI | FS_MCDATA study item description
S1-150312
Notes: 1