## Slide 1: FS_V2XLTE Status Update Study on LTE support for V2X services
Ki-Dong Lee
LG Electronics Inc.
FS_V2XLTE Rapporteur
3GPP TSG-SA WG1 Meeting #71
Belgrade, Serbia, 17-21 August 2015
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_V2XLTE Status
Is this a new WI? <y/n> N
  Guide: remove one of the following bullets as appropriate:
This WI has been approved at SP#67
  Approved WID is in tdoc SP-150051
  Guide: indicate the SA tdoc number for the most recent version of the approved WID
Notes: 1

## Slide 3: FS_V2XLTE Progress
Progress made at this meeting
  Spectrum usage scenario/coverage
  Clarification/addition for existing use cases
  Discussion of some new use cases
  RSU aspect, Density, numerology, security
Work/Study Item Completion: 75%
Draft <TS/TR> 22.885 Completion: 75%
Controversial issues
  <list of controversial issues, if any>
S1-152759
Notes: 1

## Slide 4: FS_V2XLTE Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 7
Number of slots requested for next meeting
  sum of plenary and drafting slots: 8
  Guide: remove bullet above if WID is 100% complete
Number of Drafting session participants: 20+
  Guide: remove bullet above if no Drafting sessions held
S1-152759
Notes: 1

## Slide 5: FS_V2XLTE Completion Date
Target completion date in WID: <12/2015> SP#70
    Guide: SA plenary meeting number and date (not SA1)
Is current completion date the same as above? <y>
Will target completion date be met? <y>
  If not, change target completion date to:
    <mm/yyyy> SP#xx
  Guide: Remove “change target completion date” bullet above if current target can be met
Expected date to send <TR/TS> to SA plenary:
  For information: SA1#71 (08/2015)
  For approval: SA1#72 (11/2015)
S1-152759
Notes: 1

## Slide 6: FS_V2XLTE Planning/Progress
Topics to focus on at SA1#72 (Nov 2015):
  Completion of Study: security/privacy, leftover
  Consolidation of PRs
  Review existing Use Cases (no major changes)
  TR Clean-up
Planning for subsequent meetings
  SA1#72 (Nov 2015)
    Clean-up and completion
  SA1#73 (Feb 2016)
    <Short list of topics>
  <Until close of WI as defined in WID>
S1-152759
Notes: 1

## Slide 7: Work plan between meetings
  Guide: if WID is 100% complete or if SA1 agreed to stop the work, delete this slide
Email discussion
  Consolidation of Potential Requirements
  Tentative start date: <tbd/09/2015>
S1-152759
Notes: 1

## Slide 8: FS_V2XLTE Progress Estimate
  Guide: if WID is 100% complete or if SA1 agreed to stop the work, delete this slide
Estimated percentage completion:
  SA1#72 (Nov 2015): <100%>
  SA1#73 (Feb 2016): <xx%>
  <Until expected Completion Date>
S1-152759
Notes: 1

## Slide 9: FS_V2XLTE Agreed documents
  Guide: List agreed CRs. For draft TR/TS, list agreed contributions – document details can be copied from meeting Agenda
List of agreed documents at this meeting:
Tdoc number | Sourcing company | Title
Tdoc number | Sourcing company | Title
Tdoc number | Sourcing company | Title
Tdoc number | Sourcing company | Title
S1-152759
Notes: 1