## WP_3GPP
ID | Unique_ID | Name | Acronym | Outline_Level | Release | Resource_Names | Start_Date | Finish_Date | Percent_Complete | Hyperlink | Status_Report | WI_rapporteur_name | WI_rapporteur_e_mail | Notes | Impacted_TSs_and_TRs | TSG_approved | PCG_approved | TSG_stopped | PCG_stopped | Created | last_modif
1 | 0 | Work Plan 3GPP version July 28th 2016 |  | 1 |  |  | 2000-01-03 08:00 | 2000-01-03 17:00 | 0% | [10 empty] | 2015-01-15 10:44 | 2015-03-05 08:00
Blue: new WID
Green: completed WID
Yellow: Rel-13, completion between 80 and 99%
Orange: Rel-13, completion between 50 and 79%
Red: Rel-13, completion between 0 and 49%
2 | 0 | This version includes all the Work Items approved at TSG#72 |  | 1 |  |  | 2000-01-03 08:00 | 2000-01-03 17:00 | 0% | [10 empty] | 2015-03-04 10:24 | 2015-03-05 08:00
3 | 0 | Next target dates: Rel-14 St. 2: Sept 2016; St.3: Mar 2017, ASN.1: Jun 2017 |  | 1 |  |  | 2000-01-03 08:00 | 2000-01-03 17:00 | 0% | [10 empty] | 2015-08-12 08:23 | NA
4 | 0 |  |  | 1 |  |  | 2000-01-03 08:00 | 2000-01-03 17:00 | 0% | [10 empty] | 2015-09-29 11:40 | NA
5 | 0 | Release 15 Features | - | 1 | Rel-15 | SP,RP,CP,GP | 2016-03-15 08:00 | 2017-09-15 17:00 | 0% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 11:19 | 2014-08-29 08:00
6 | 710083 | LTE Measurement Gap Enhancement | LTE_meas_gap_enh | 1 | Rel-15 | R4 | 2016-03-15 08:00 | 2017-06-15 17:00 | 4% | RP-160678 |  | Intel |  |  |  | TSG#71 |  |  |  | 2016-03-22 11:04 | 2016-03-22 08:00
7 | 710183 | Core part: LTE Measurement Gap Enhancement | LTE_meas_gap_enh-Core | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-03-15 17:00 | 10% | RP-160912 | - | Intel |  | ; 1/7/16: Compl:0%->10%; 1/7/16: CD:Thu 15/06/17->Wed 15/03/17; 1/7/16: WID: RP-160678->RP-160912; ... |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
8 | 710283 | Perf. part: LTE Measurement Gap Enhancement | LTE_meas_gap_enh-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-06-15 17:00 | 0% | RP-160912 | - | Intel |  | 1/7/16: WID: RP-160678->RP-1609121/7/16: Release: Rel-15->Rel-14 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
9 | 710074 | Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS) | AASenh_BS_LTE_UTRA | 1 | Rel-15 | R4 | 2016-03-15 08:00 | 2017-09-15 17:00 | 2% | RP-160548 |  | Huawei |  | follow-up WI of REL-13 WI AAS_BS_LTE_UTRA |  | TSG#71 |  |  |  | 2016-03-22 11:04 | 2016-03-22 08:00
10 | 710174 | Core part: Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS) | AASenh_BS_LTE_UTRA-Core | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-03-15 17:00 | 5% | RP-160940 | - | Huawei |  | follow-up WI of REL-13 WI AAS_BS_LTE_UTRA1/7/16: Compl:0%->5%1/7/16: CD:Fri 15/09/17->Wed 15/03/17... |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
11 | 710274 | Perf. part: Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS) | AASenh_BS_LTE_UTRA-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-09-15 17:00 | 0% | RP-160940 | - | Huawei |  | 1/7/16: WID: RP-160548->RP-1609401/7/16: Release: Rel-15->Rel-14 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
12 | 720091 | Shortened TTI and processing time for LTE | LTE_sTTIandPT | 1 | Rel-15 | R1 | 2016-06-15 08:00 | 2018-03-15 17:00 | 0% | RP-161299 |  | Ericsson |  |  |  | TSG#72 |  |  |  | 2016-07-08 16:02 | 2016-06-22 08:00
13 | 720191 | Core part: Shortened TTI and processing time for LTE | LTE_sTTIandPT-Core | 2 | Rel-15 | R1 | 2016-06-15 08:00 | 2017-09-15 17:00 | 0% | RP-161299 |  | Ericsson |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
14 | 720291 | Perf. part: Shortened TTI and processing time for LTE | LTE_sTTIandPT-Perf | 2 | Rel-15 | R4 | 2016-06-15 08:00 | 2018-03-15 17:00 | 0% | RP-161299 |  | Ericsson |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
15 | 0 | Release 15 Features on 5G Mobile Network for Advanced communications | - | 1 | Rel-15 | SP,RP,CP,GP | 2016-06-09 08:00 | 2017-12-12 17:00 | 0% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 11:19 | 2014-08-29 08:00
16 | 720005 | New Services and Markets Technology Enablers | SMARTER | 1 | Rel-15 | S1 | 2016-06-09 08:00 | 2016-09-15 17:00 | 0% | SP-160364 |  | Li, Alice | alice.li@vodafone.com | Resulting from FS_SMARTER |  | TSG#72 |  |  |  | 2016-06-09 10:10 | NA
17 | 0 | Release 15 Studies | - | 1 | Rel-15 | SP,RP,CP,GP | 2016-06-09 08:00 | 2017-12-12 17:00 | 0% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 11:19 | 2014-08-29 08:00
18 | 720003 | Study on Enhancement of 3GPP support for V2X services | FS_eV2X | 1 | Rel-15 | S1 | 2016-06-09 08:00 | 2016-12-15 17:00 | 30% | SP-160370 |  | LG Electronics, SungDuck Chun | sungduck.chun@lge.com |  |  | TSG#72 |  |  |  | 2016-06-09 10:14 | NA
19 | 720004 | Study on Future Railway Mobile Communication System | FS_FRMCS | 1 | Rel-15 | S1 | 2016-06-09 08:00 | 2016-12-15 17:00 | 0% | SP-160371 |  | Merkel, Juergen | Merkel, Juergen - Nokia Networks |  |  | TSG#72 |  |  |  | 2016-06-09 10:15 | NA
20 | 0 | Release 15 Studies on 5G Mobile Network for Advanced communications | - | 1 | Rel-15 | SP,RP,CP,GP | 2016-06-09 08:00 | 2017-12-12 17:00 | 0% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 11:19 | 2014-08-29 08:00
21 | 710062 | Study on New Radio (NR) Access Technology | FS_NR_newRAT | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-03-15 17:00 | 10% | RP-161214 | - | NTT DOCOMO |  | includes RAN TR 38.801; 1/7/16: Compl:0%->10%; 1/7/16: CD:Thu 15/06/17->Wed 15/03/17; 1/7/16: WID: RP-160671->RP-161214; 1/7/16: Release: Rel-15->Rel-14; 28/7/16: 38.802 added | TR 38.801, TR 38.912; 38.802 | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-28 08:00
22 | 720046 | Study on Management Aspects of Next Generation Network architecture and features | FS_MAN_NGNAF | 1 | Rel-15 | S5 | 2016-06-13 08:00 | 2017-03-15 17:00 | 0% | SP-160399 |  | Nokia Networks, Yizhi Yao | Yizhi.yao@nokia.com | 28/7/16: 28.802 added; | TR (new); 28.802 | TSG#72 |  |  |  | 2016-06-13 03:11 | 2016-07-28 08:00
23 | 720047 | Study on Management and Orchestration Architecture of Next Generation Network and Service | FS_NGNS_MOA | 1 | Rel-15 | S5 | 2016-06-13 08:00 | 2017-03-15 17:00 | 0% | SP-160400 |  | Huawei Technologies, Zou Lan | zoulan@huawei.com | 28/7/16: 28.800 added; | TR xy.abc; 28.800 | TSG#72 |  |  |  | 2016-06-13 03:13 | 2016-07-28 08:00
24 | 720048 | Study on management and orchestration of network slicing for next generation network | FS_MONETS | 1 | Rel-15 | S5 | 2016-06-13 08:00 | 2017-03-15 17:00 | 0% | SP-160394 |  | Ericsson , Robert Petersen |  | 28/7/16: 28.801 added; | 32.8xx; 28.801 | TSG#72 |  |  |  | 2016-06-13 03:17 | 2016-07-28 08:00
25 | 0 | Release 14 Features | - | 1 | Rel-14 | SP,RP,CP,GP | 2014-12-12 08:00 | 2017-06-14 17:00 | 0% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 11:19 | 2014-08-29 08:00
26 | 700027 | Mission Critical Improvements | MCImp | 1 | Rel-14 | S1 | 2015-04-14 08:00 | 2016-12-15 17:00 | 51% |  |  |  |  | Umbrella Feature |  | SP-70 |  |  |  | 2015-12-07 11:50 | 2015-12-11 08:00
27 | 700029 | Mission Critical Push to Talk over LTE Realignment | MCImp-MCPTTR | 2 | Rel-14 | S1 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | SP-150821 |  | Andrew Thiessen | andrew (at) its (dot) bldrdoc (dot) gov | 2/3/16: FCD: 03/16->06/16. ES in SP-160102; 0->75%; 9/6/16: 75%->100 | 22.179 | SP-70 |  |  |  | 2015-12-07 11:51 | 2016-06-09 08:00
28 | 720056 | Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT | 2 | Rel-14 | S6 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | SP-160343 |  | Lazara, Dom | dom.lazara@motorolasolutions.com | 28/7/16: 23.379 added; | TS 23.PTT, TS 23.CFA, TS 23.VID, TS 23.DAT; 23.379 | TSG#72 |  |  |  | 2016-06-13 04:36 | 2016-07-28 08:00
29 | 700028 | Mission Critical Services Common Requirements | MCImp-MCCoRe | 2 | Rel-14 | S1 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | SP-150822 |  | Andrew Thiessen | andrew (at) its (dot) bldrdoc (dot) gov | 2/3/16: FCD: 03/16->06/16. ES in SP-160104; 0->75%; 9/6/16: 75%->100 | New TS 22.280 | SP-70 |  |  |  | 2015-12-07 11:51 | 2016-06-09 08:00
30 | 720055 | Common functional architecture to support mission critical services | MCImp-MC_ARCH | 2 | Rel-14 | S6 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | SP-160342 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 28/7/16: 23.280 added; | TS 23.CFA, TS 23.PTT, TS 23.VID, TS 23.DAT; 23.280 | TSG#72 |  |  |  | 2016-06-13 04:31 | 2016-07-28 08:00
31 | 720053 | Mission Critical Video over LTE | MCImp-MCVideo | 2 | Rel-14 | S1 | 2015-04-14 08:00 | 2016-12-15 17:00 | 70% | SP-150849 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160106; 0->80%; 9/6/16: 80%->100 |  | SP-70 |  |  |  | 2015-12-07 11:51 | 2016-06-09 08:00
32 | 670006 | Study on Mission Critical Video over LTE | FS_MCVideo | 3 | Rel-14 | S1 | 2015-04-14 08:00 | 2015-12-15 17:00 | 100% | SP-150048 |  | Villebrun, Emmanuelle (French MoI) | emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 1/4/15:TR number added; June2015: Compl:0%->50; 07/09/15: 50%->70; 7/12/15: 70%->100 | New TR 22.879 | SP-67 | PCG-34 |  |  | 2015-03-04 10:20 | 2015-12-07 08:00
33 | 700030 | Stage 1 of MCVideo | MCImp-MCVideo | 3 | Rel-14 | S1 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | SP-150849 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160106; 0->80%; 9/6/16: 80%->100 | New TR 22.281 | SP-70 |  |  |  | 2015-12-07 11:51 | 2016-06-09 08:00
34 | 720051 | Stage 2 for MCVideo | MCImp-MCVideo | 3 | Rel-14 | S6 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | SP-160344 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 28/7/16: 23.281 added; | TS 23.VID, TS 23.CFA, TS 23.PTT, TS 23.DAT; 23.281 | TSG#72 |  |  |  | 2016-06-13 04:21 | 2016-07-28 08:00
35 | 720054 | Mission Critical Data over LTE | MCImp-MCData | 2 | Rel-14 | S1 | 2015-04-14 08:00 | 2016-12-15 17:00 | 70% | SP-150850 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160109; 0->80%; 9/6/16: 80%->100 |  | SP-70 |  |  |  | 2015-12-07 11:51 | 2016-07-28 08:00
36 | 670007 | Study on Mission Critical Data Communications | FS_MCDATA | 3 | Rel-14 | S1 | 2015-04-14 08:00 | 2015-12-15 17:00 | 100% | SP-150049 |  | Villebrun, Emmanuelle (French MoI) | emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 1/4/15:TR number added; June2015: Compl:0%->20; 07/09/15: 20%->90; 7/12/15: 90%->100 | New TR 22.880 | SP-67 | PCG-34 |  |  | 2015-03-04 10:20 | 2015-12-07 08:00
37 | 700031 | Stage 1 of MCData | MCImp-MCData | 3 | Rel-14 | S1 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | SP-150850 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160109; 0->80%; 9/6/16: 80%->100 | New TR 22.282 | SP-70 |  |  |  | 2015-12-07 11:51 | 2016-06-09 08:00
38 | 720052 | Stage 2 for MCData | MCImp-MCData | 3 | Rel-14 | S6 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | SP-160345 |  | David Freeman (UK Home Office) | david@dnf-consulting.co.uk | 28/7/16: 23.282 added; | 23.282 | TSG#72 |  |  |  | 2016-06-13 04:21 | 2016-07-28 08:00
39 | 720083 | Study on Mission Critical Security Enhancements | FS_MC_Sec | 2 | Rel-14 | S3 | 2016-06-17 08:00 | 2016-12-15 17:00 | 0% | SP-160374 |  | Haigh, Peter, CESG | peter.haigh@cesg.gsi.gov.uk | 28/7/16: 33.280 added;; 28/7/16: 39.880 added; | TR 33.xxx; 33.280; 39.880 | SP-72 |  |  |  | 2016-06-17 07:19 | 2016-07-28 08:00
40 | 720057 | Study on mission critical system migration and interconnect between MCPTT systems | FS_MCSMI | 2 | Rel-14 | S6 | 2016-06-13 08:00 | 2016-09-15 17:00 | 0% | SP-160340 |  | Chater-Lea, David |  | 28/7/16: 23.781 added; | New TR 23.781 | TSG#72 |  |  |  | 2016-06-13 04:47 | 2016-07-28 08:00
41 | 720058 | Study on Mission Critical Communication Interworking between LTE and non-LTE Systems | FS_MCCI | 2 | Rel-14 | S6 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | SP-160341 |  | Monnes, Peter (Harris Corp.) |  | 28/7/16: 23.782 added; | New TR 23.782 | TSG#72 |  |  |  | 2016-06-13 04:47 | 2016-07-28 08:00
42 | 720030 | LTE support for V2X services | V2XLTE | 1 | Rel-14 | S1 | 2015-09-09 08:00 | 2017-09-15 17:00 | 19% | SP-150573 |  |  |  | 7/12/15: 0%->5; 28/1/16: 22.185 added; 2/3/16: 5%->90; 9/6/16: 90%->100 | 22.278; 22.185 | SP-68 |  |  |  | 2015-09-09 10:53 | 2016-06-09 08:00
43 | 690035 | Stage 1 for LTE support for V2X services | V2XLTE | 2 | Rel-14 | S1 | 2015-09-09 08:00 | 2016-03-17 17:00 | 100% | SP-150573 |  |  |  | 7/12/15: 0%->5; 28/1/16: 22.185 added; 2/3/16: 5%->90; 9/6/16: 90%->100 | 22.278; 22.185 | SP-68 |  |  |  | 2015-09-09 10:53 | 2016-06-09 08:00
44 | 720011 | Architecture enhancements for LTE support of V2X services | V2XARC | 2 | Rel-14 | S2 | 2016-06-09 08:00 | 2016-09-15 17:00 | 0% | SP-160317 |  | LG Electronics, LaeYoung Kim | laeyoung.kim@lge.com | 28/7/16: 23.285 added; | 23.285 | TSG#72 |  |  |  | 2016-06-09 10:33 | 2016-07-28 08:00
45 | 720090 | RAN aspects of LTE-based V2X Services | LTE_V2X | 2 | Rel-14 | R1 | 2016-06-15 08:00 | 2017-09-15 17:00 | 0% | RP-161298 |  | LG Electronics |  | follow-up WI of REL-14 SI FS_LTE_V2X |  | TSG#72 |  |  |  | 2016-07-08 16:00 | 2016-06-22 08:00
46 | 720190 | Core part: LTE-based V2X Services | LTE_V2X-Core | 3 | Rel-14 | R1 | 2016-06-15 08:00 | 2017-03-15 17:00 | 0% | RP-161298 |  | LG Electronics |  | follow-up WI of REL-14 SI FS_LTE_V2X |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
47 | 720290 | Perf. part: LTE-based V2X Services | LTE_V2X-Perf | 3 | Rel-14 | R4 | 2016-06-15 08:00 | 2017-09-15 17:00 | 0% | RP-161298 |  | LG Electronics |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
48 | 700061 | Support for V2V services based on LTE sidelink | LTE_SL_V2V | 1 | Rel-14 | R1 | 2015-12-15 08:00 | 2017-03-15 17:00 | 23% | RP-152293 |  | LG Electronics |  |  |  | RP-70 |  |  |  | 2016-01-07 10:48 | 2015-12-22 08:00
49 | 700161 | Core part: Support for V2V services based on LTE sidelink | LTE_SL_V2V-Core | 2 | Rel-14 | R1 | 2015-12-15 08:00 | 2016-09-15 17:00 | 60% | RP-161272 |  | LG Electronics |  | 22/3/16: Compl:0%->15%22/3/16: WID: RP-152293->RP-1606491/7/16: Compl:15%->60%1/7/16: WID: RP-160649->RP-161272; 28/7/16: 36.785 added; | 36.785 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-28 08:00
50 | 700261 | Perf. part: Support for V2V services based on LTE sidelink | LTE_SL_V2V-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 0% | RP-161272 |  | LG Electronics |  | 22/3/16: WID: RP-152293->RP-1606491/7/16: WID: RP-160649->RP-161272 |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
51 | 710023 | Non-IP for Cellular Internet of Things (CIoT) for 2G/3G-GPRS(EC-EGPRS) | NonIP_GPRS | 1 | Rel-14 | S2,C1,C4 | 2016-03-02 08:00 | 2016-09-15 17:00 | 40% | SP-160196 | [5 empty] | TSG#71 |  |  |  | 2016-03-02 10:45 | 2016-03-02 08:00
52 | 710024 | Non-IP for Cellular IoT for EC-EGPRS | NonIP_GPRS | 2 | Rel-14 | S2 | 2016-03-02 08:00 | 2016-06-15 17:00 | 50% | SP-160196 |  | Hans Ronneke, Ericsson | hans . Ronneke (a) ericsson . Com | 9/6/16: 0%->50 | 23.060, 23.682, 23.401? | TSG#71 |  |  |  | 2016-03-02 10:45 | 2016-06-09 08:00
53 | 710025 | CT aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 2 | Rel-14 | C1,C4 | 2016-03-02 08:00 | 2016-09-15 17:00 | 38% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: WID:CP-160161->CP-160293 |  | TSG#71 |  |  |  | 2016-03-02 10:45 | 2016-06-11 08:00
54 | 710026 | CT1 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 3 | Rel-14 | C1 | 2016-03-02 08:00 | 2016-09-15 17:00 | 50% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: 0%->50; 11/6/16: WID:CP-160161->CP-160293 | 24.008 | TSG#71 |  |  |  | 2016-03-02 10:45 | 2016-06-11 08:00
55 | 720069 | CT3 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 3 | Rel-14 | C3 | 2016-03-02 08:00 | 2016-09-15 17:00 | 0% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: WID:CP-160161->CP-160293; 13/6/16: 0%->65 | 29.060, 29.274, 29.002, 29.303, 23.008, 29.128, 29.272, 23.007 | CT-72 |  |  |  | 2016-03-02 10:45 | 2016-06-13 08:00
56 | 710027 | CT4 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 3 | Rel-14 | C4 | 2016-03-02 08:00 | 2016-09-15 17:00 | 65% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: WID:CP-160161->CP-160293; 13/6/16: 0%->65 | 29.060, 29.274, 29.002, 29.303, 23.008, 29.128, 29.272, 23.007 | TSG#71 |  |  |  | 2016-03-02 10:45 | 2016-06-13 08:00
57 | 720092 | Further enhanced MTC for LTE | LTE_feMTC | 1 | Rel-14 | R1 | 2016-06-15 08:00 | 2017-09-15 17:00 | 0% | RP-161321 |  | Ericsson |  |  |  | TSG#72 |  |  |  | 2016-07-08 16:03 | 2016-06-22 08:00
58 | 720192 | Core part: Further enhanced MTC for LTE | LTE_feMTC-Core | 2 | Rel-14 | R1 | 2016-06-15 08:00 | 2017-03-15 17:00 | 0% | RP-161321 |  | Ericsson |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
59 | 720292 | Perf. part: Further enhanced MTC for LTE | LTE_feMTC-Perf | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2017-09-15 17:00 | 0% | RP-161321 |  | Ericsson |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
60 | 720093 | Enhancements of NB-IoT | NB_IOTenh | 1 | Rel-14 | R1 | 2016-06-15 08:00 | 2017-09-15 17:00 | 0% | RP-161324 |  | Huawei |  |  |  | TSG#72 |  |  |  | 2016-07-08 16:06 | 2016-06-22 08:00
61 | 720193 | Core part: Enhancements of NB-IoT | NB_IOTenh-Core | 2 | Rel-14 | R1 | 2016-06-15 08:00 | 2017-03-15 17:00 | 0% | RP-161324 |  | Huawei |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
62 | 720293 | Perf. part: Enhancements of NB-IoT | NB_IOTenh-Perf | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2017-09-15 17:00 | 0% | RP-161324 |  | Huawei |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
63 | 720006 | Enhancements of Dedicated Core Networks selection mechanism | eDecor | 1 | Rel-14 | S2 | 2015-09-17 08:00 | 2016-09-15 17:00 | 86% | SP-160310 |  | Roland Gustafsson | Roland.Gustafsson@ericsson.com | 7/12/15: 0%->70; 7/3/16: 70%->80; 9/6/16: 80%->95 | 23.711 | SP-69 |  |  |  | 2015-09-17 00:23 | 2016-06-09 08:00
64 | 690051 | Study on Enhancements of Dedicated Core Networks selection mechanism | FS_eDecor | 2 | Rel-14 | S2 | 2015-09-17 08:00 | 2016-03-18 17:00 | 95% | SP-150518 |  | Roland Gustafsson | Roland.Gustafsson@ericsson.com | 7/12/15: 0%->70; 7/3/16: 70%->80; 9/6/16: 80%->95 | 23.711 | SP-69 |  |  |  | 2015-09-17 00:23 | 2016-06-09 08:00
65 | 720007 | Enhancements of Dedicated Core Networks selection mechanism | eDecor | 2 | Rel-14 | S2 | 2016-06-09 08:00 | 2016-09-15 17:00 | 70% | SP-160310 |  | Roland Gustafsson | Roland.Gustafsson@ericsson.com |  | 23.401, 23.060, 23.251 | TSG#72 |  |  |  | 2015-09-17 00:23 | 2016-06-09 08:00
66 | 700020 | Evolution to and Interworking with eCall in IMS | EIEI | 1 | Rel-14 | S1,S2,C1,C6 | 2015-05-11 08:00 | 2016-09-15 17:00 | 43% | SP-150275 |  | Kurt Bischinger |  | 12/15: created by MCC to distinguish Stage 1 from Stage 2 | 22.101 | SP-68 |  |  |  | 2015-12-07 11:29 | 2015-06-09 08:00
67 | 680004 | Stage 1 of Evolution to and Interworking with eCall in IMS | EIEI | 2 | Rel-14 | S1 | 2015-05-11 08:00 | 2015-06-19 17:00 | 100% | SP-150275 |  | Kurt Bischinger |  |  | 22.101 | SP-68 |  |  |  | 2015-06-09 11:27 | 2015-06-09 08:00
68 | 700021 | Stage 2 of Evolution to and Interworking with eCall in IMS | EIEI | 2 | Rel-14 | S2 | 2015-12-11 08:00 | 2016-06-10 17:00 | 100% | SP-150623 |  | Haris Zisimopoulos, Qualcomm Incorporated | harisz@qti.qualcomm.com | 7/3/16: 0%->20; 9/6/16: 20%->100. FCD: 03/16->06/16 | 23.167, 23.401 | SP-68 |  |  |  | 2015-12-07 11:29 | 2016-06-09 08:00
69 | 710020 | CT aspects of evolution to and interworking with eCall in IMS | EIEI-CT | 2 | Rel-14 | C1,C6 | 2016-03-02 08:00 | 2016-09-15 17:00 | 22% | CP-160053 |  | Lena Chaponniere | lguellec@qti.qualcomm.com |  |  | TSG#71 |  |  |  | 2016-03-02 10:25 | 2016-03-02 08:00
70 | 710021 | CT1 aspects of evolution to and interworking with eCall in IMS | EIEI-CT | 3 | Rel-14 | C1 | 2016-03-02 08:00 | 2016-09-15 17:00 | 35% | CP-160053 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 11/6/16: 0%->35 | 24.229, 24.301 | TSG#71 |  |  |  | 2016-03-02 10:25 | 2016-06-11 08:00
71 | 720068 | (IETF) Next-Generation Pan-European eCall (draft-ietf-ecrit-ecall) | EIEI-CT | 3 | Rel-14 | C1.IETF | 2016-03-02 08:00 | 2016-09-15 17:00 | 30% | CP-160053 |  |  |  |  | draft-ietf-ecrit-ecall | TSG#72 |  |  |  | 2016-03-02 10:25 | 2016-07-08 08:00
72 | 710022 | CT6 aspects of evolution to and interworking with eCall in IMS | EIEI-CT | 3 | Rel-14 | C6 | 2016-03-02 08:00 | 2016-09-15 17:00 | 0% | CP-160053 |  | Lena Chaponniere | lguellec@qti.qualcomm.com |  | 31.102 | TSG#71 |  |  |  | 2016-03-02 10:25 | 2016-03-02 08:00
73 | 670003 | Multimedia Priority Service Modifications | MPS_Mods | 1 | Rel-14 | S1 | 2015-03-11 08:00 | 2016-06-15 17:00 | 100% | SP-150043 |  | Ray P. Singh (Applied Communications Science) | rsingh@appcomsci.com | 1/4/15: rapporteur added, Impacted TS added. 6/15: 0->25%; 07/09/15: 25%->40; 7/12/15: 40%->70; 2/3/16: 70%->80; 9/6/16: 80%->100 | 22.153 | SP-67 | PCG-34 |  |  | 2015-03-04 10:16 | 2016-06-09 08:00
74 | 721004 | Lawful Interception Rel-14 | LI14 | 1 | Rel-14 | S3LI | 2016-06-15 08:00 | 2017-09-14 17:00 | 0% | SP-160375 |  | Koen JASPERS, PIDS |  |  |  | TSG#72 |  |  |  | 2016-07-27 10:35 | 2016-07-27 08:00
75 | 690034 | Enhancements to User Location Reporting Support | eULRS | 1 | Rel-14 | S1 | 2015-09-09 08:00 | 2015-12-18 17:00 | 100% | SP-150540 |  |  |  | 2/3/16: 0%->100 |  | SP-68 |  |  |  | 2015-09-09 10:53 | 2016-03-02 08:00
76 | 700032 | Enhancement for TV service | EnTV | 1 | Rel-14 | S1 | 2015-11-02 08:00 | 2016-03-17 17:00 | 100% | SP-150756 |  | Zhiming Li | Lizhiming@huawei.com | 2/3/16: 0%->100 | 22.101 | SP-70 |  |  |  | 2015-12-07 11:55 | 2016-03-02 08:00
77 | 700054 | MBMS Transport Protocol and APIs | TRAPI | 1 | Rel-14 | S4 | 2015-12-11 08:00 | 2016-09-09 17:00 | 35% | SP-150851 |  | Samsung, Imed Bouazizi | i.bouazizi@samsung.com | 28/1/16: 26.347 added;; 7/3/16: 0%->20; 11/6/16: 20%->35 | 26.346, 26.852, New TS; 26.347 | SP-70 |  |  |  | 2015-12-11 15:41 | 2016-06-11 08:00
78 | 720031 | EIR check for WLAN access to EPC | EWE | 1 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-09-15 17:00 | 54% | SP-150624 |  | Alcatel-Lucent, Nicolas Drevon | Nicolas.Drevon@alcatel-lucent.com | 7/3/16: 45%->60; 9/6/16: 60%->100 | 23.002, 23.402 | SP-70 |  |  |  | 2015-12-07 14:12 | 2016-06-09 08:00
79 | 700039 | Stage 2 of EWE | EWE | 2 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-06-17 17:00 | 100% | SP-150624 |  | Alcatel-Lucent, Nicolas Drevon | Nicolas.Drevon@alcatel-lucent.com | 7/3/16: 45%->60; 9/6/16: 60%->100 | 23.002, 23.402 | SP-70 |  |  |  | 2015-12-07 14:12 | 2016-06-09 08:00
80 | 720002 | CT aspects of EWE | EWE-CT | 2 | Rel-14 | ct | 2016-06-13 08:00 | 2016-09-15 17:00 | 0% | CP-160244 |  | Nokia, Bruno Landais | bruno.landais@nokia.com |  |  | TSG#72 |  |  |  | 2016-06-13 02:18 | NA
81 | 720032 | CT1 aspects of EWE | EWE-CT | 3 | Rel-14 | C1 | 2016-06-13 08:00 | 2016-09-15 17:00 | 0% | CP-160244 |  | Nokia, Bruno Landais | bruno.landais@nokia.com |  | 24.302 | TSG#72 |  |  |  | 2016-06-13 02:18 | NA
82 | 720033 | CT4 aspects of EWE | EWE-CT | 3 | Rel-14 | C4 | 2016-06-13 08:00 | 2016-09-15 17:00 | 0% | CP-160244 |  | Nokia, Bruno Landais | bruno.landais@nokia.com |  | 29.273 | TSG#72 |  |  |  | 2016-06-13 02:18 | NA
83 | 720060 | Enhancements to Multi-stream Multiparty Conferencing Media Handling | MMCMH_Enh | 1 | Rel-14 | S4 | 2016-03-02 08:00 | 2017-03-15 17:00 | 0% | SP-160272 |  | Nikolai Leung | nleung@qti.qualcomm.com |  | TS 26.114 | TSG#72 |  |  |  | 2016-06-11 05:48 | NA
84 | 720029 | Overall aspects of MMCMH_Enh | MMCMH_Enh | 2 | Rel-14 | S4 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | SP-160272 |  | Nikolai Leung | nleung@qti.qualcomm.com |  | TS 26.114 | TSG#72 |  |  |  | 2016-06-11 05:48 | NA
85 | 720064 | CT aspects of MMCMH_Enh | MMCMH_Enh-CT | 2 | Rel-14 | ct | 2016-03-02 08:00 | 2017-03-15 17:00 | 0% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | To be checked at SA4 if a part can stay in Rel-13 (now Stages 1 and 2 by SA4 in UID660050), while the CT aspects are in Rel-14. 06/16: Name changed from "CT aspects of (or "Enhancements of") MTSI Extension on Multi-stream". Acronym changed from "MMCMH-... |  | TSG#72 |  |  |  | 2016-03-02 11:12 | 2016-06-13 08:00
86 | 720065 | CT1 aspects of MMCMH_Enh | MMCMH_Enh-CT | 3 | Rel-14 | C1 | 2016-03-02 08:00 | 2017-03-15 17:00 | 0% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Name changed from "CT1 aspects of MTSI Extension on Multi-stream". Acronym changed from "MMCMH-CT"; 13/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17; 13/6/16: WID:CP-160250->CP-160369 | 24.229 | TSG#72 |  |  |  | 2016-03-02 11:12 | 2016-06-13 08:00
87 | 720066 | CT3 aspects of MMCMH_Enh | MMCMH_Enh-CT | 3 | Rel-14 | C3 | 2016-03-02 08:00 | 2017-03-15 17:00 | 0% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Acronym changed from "MMCMH-CT"; 13/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17; 13/6/16: WID:CP-160250->CP-160369 | 29.162, 29.213, 29.214, 29.165 | TSG#72 |  |  |  | 2016-03-02 11:12 | 2016-06-13 08:00
88 | 720067 | CT4 aspects of MMCMH_Enh | MMCMH_Enh-CT | 3 | Rel-14 | C4 | 2016-03-02 08:00 | 2017-03-15 17:00 | 0% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | 3/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17; 13/6/16: WID:CP-160250->CP-160369 | 23.333, 29.333, 23.334, 29.334, 29.238 | TSG#72 |  |  |  | 2016-03-02 11:12 | 2016-06-13 08:00
89 | 710002 | Deleted - CT aspects of (or "Enhancements of") MTSI Extension on Multi-stream | MMCMH-CT | 1 | Rel-14 | ct | 2016-03-02 08:00 | 2016-09-15 17:00 | 0% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT |  | TSG#71 |  | CP-72 |  | 2016-03-02 11:12 | 2016-06-13 08:00
90 | 710028 | deleted -CT1 aspects of MTSI Extension on Multi-stream | MMCMH-CT | 2 | Rel-14 | C1 | 2016-03-02 08:00 | 2016-09-15 17:00 | 0% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT | 24.229 | TSG#71 |  | CP-72 |  | 2016-03-02 11:12 | 2016-06-13 08:00
91 | 710029 | deleted -CT3 aspects of MTSI Extension on Multi-stream | MMCMH-CT | 2 | Rel-14 | C3 | 2016-03-02 08:00 | 2016-09-15 17:00 | 0% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT | 29.162, 29.213, 29.214, 29.165 | TSG#71 |  | CP-72 |  | 2016-03-02 11:12 | 2016-06-13 08:00
92 | 710030 | deleted -CT4 aspects of MTSI Extension on Multi-stream | MMCMH-CT | 2 | Rel-14 | C4 | 2016-03-02 08:00 | 2016-09-15 17:00 | 0% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT | 23.333, 29.333, 23.334, 29.334, 29.238 | TSG#71 |  | CP-72 |  | 2016-03-02 11:12 | 2016-06-13 08:00
93 | 630007 | IMS Signalling Activated Trace | ISAT | 1 | Rel-14 | C1,C3,C4,IETF | 2014-03-05 08:00 | 2016-03-11 17:00 | 28% | CP-150091 | - | Vodafone | peter.dawes @vodafone.com | Mar 15: WID: CP-140195->CP-150091. ES in CP-150637. 8/3/16: Moved from Rel-13 at CT#71 | - | CP-63 | PCG-32 |  |  | 2014-01-29 17:11 | 2016-03-08 08:00
94 | 630107 | CT1 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-14 | C1 | 2014-03-10 08:00 | 2016-03-11 17:00 | 0% | CP-150091 | CP-140606 | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150728 | 24.229, 24.323 | CP-63 | PCG-32 |  |  | 2014-01-29 17:11 | 2014-12-09 08:00
95 | 651003 | (IETF) IMS Signalling Activated Trace (draft-dawes-sipping-debug) | ISAT | 2 | Rel-14 | C1-IETF | 2014-09-12 08:00 | 2016-03-11 17:00 | 28% | CP-150091 | - | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637; 13/6/16: 25%->28 | draft-dawes-sipping-debug | CP-65 | PCG-33 |  |  | 2014-09-02 16:38 | 2016-06-13 08:00
96 | 651103 | (IETF) IMS Signalling Activated Trace (draft-dawes-sipping-debug) | ISAT | 2 | Rel-14 | C3-IETF | 2014-09-12 08:00 | 2016-03-11 17:00 | 25% | CP-150091 | - | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637 | draft-dawes-sipping-debug | CP-65 | PCG-33 |  |  | 2014-09-02 16:38 | 2014-12-09 08:00
97 | 651203 | (IETF) IMS Signalling Activated Trace (draft-dawes-sipping-debug) | ISAT | 2 | Rel-14 | C4-IETF | 2014-09-12 08:00 | 2016-03-11 17:00 | 25% | CP-150091 | - | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637 | draft-dawes-sipping-debug | CP-65 | PCG-33 |  |  | 2014-09-02 16:38 | 2014-12-09 08:00
98 | 630207 | CT3 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-14 | C3 | 2014-03-10 08:00 | 2016-03-11 17:00 | 0% | CP-150091 | CP-140564 | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637 | 29.165 | CP-63 | PCG-32 |  |  | 2014-01-29 17:11 | 2014-12-09 08:00
99 | 630307 | CT4 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-14 | C4 | 2014-03-05 08:00 | 2016-03-11 17:00 | 90% | CP-150091 | CP-140480 | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar.15: 90%. ES in CP-150615. 7/3/16: Rel-13->Rel-14 | 23.008, 29.228, 29.229, 29.328, 29.329 | CP-63 | PCG-32 |  |  | 2014-01-29 17:11 | 2016-03-07 08:00
100 | 720008 | Control and User Plane Separation of EPC nodes | CUPS | 1 | Rel-14 | S2 | 2015-09-17 08:00 | 2016-09-15 17:00 | 73% | SP-160316 |  | Huawei, Mirko Schramm | mirko.schramm@huawei.com | 7/12/15: 0%->20; 7/3/16: 20%->40; 9/6/16: 40%->100; 28/7/16: 23.214 added; | 23.714; 23.214 | SP-69 |  |  |  | 2015-09-17 00:24 | 2016-07-28 08:00
101 | 690052 | Study on Control and User Plane Separation of EPC nodes | FS_CUPS | 2 | Rel-14 | S2 | 2015-09-17 08:00 | 2016-06-17 17:00 | 100% | SP-150519 |  | Huawei, Mirko Schramm | mirko.schramm@huawei.com | 7/12/15: 0%->20; 7/3/16: 20%->40; 9/6/16: 40%->100 | 23.714 | SP-69 |  |  |  | 2015-09-17 00:24 | 2016-06-09 08:00
102 | 720009 | Control and User Plane Separation of EPC nodes | CUPS | 2 | Rel-14 | S2 | 2016-06-09 08:00 | 2016-09-15 17:00 | 0% | SP-160316 |  | Huawei, Mirko Schramm | mirko.schramm@huawei.com |  | 23.214, 23.002, 23.203, 23.401, 23.402 | TSG#72 |  |  |  | 2015-09-17 00:24 | 2016-06-09 08:00
103 | 690048 | OAM14 Rel-14 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM14 | 1 | Rel-14 | S5 | 2015-03-12 08:00 | 2017-06-12 17:00 | 41% | [6 empty] | SP-68 |  |  |  | 2015-09-16 19:15 | 2015-09-16 08:00
104 | 680035 | Management of mobile networks that include virtualized network functions | OAM14-MAMO_VNF | 2 | Rel-14 | S5 | 2015-06-15 08:00 | 2016-12-09 17:00 | 41% | SP-150362 |  | Jinglei Liu, China Mobile | liujinglei@chinamobile.com | June2015: WID:SP-150308->SP-150362 |  | SP-68 |  |  |  | 2015-06-15 10:06 | 2015-06-18 08:00
105 | 680036 | Management concept, architecture and requirements for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-MCAR | 3 | Rel-14 | S5 | 2015-06-15 08:00 | 2016-09-15 17:00 | 70% | SP-160023 |  | Jinglei Liu, China Mobile (liujinglei@chinamobile.com) | liujinglei@chinamobile.com | June2015: WID:SP-150309->SP-150363. Aug2015: FCD: Mar 2016; 07/09/15: 0%->20. 15/09/15: FCD: Mar 16->Dec 16, moved to Rel-14; 7/12/15: 20%->40; 7/3/16: 40%->50; 7/3/16: WID:SP-150363->SP-160023 ( FCD: Dec16->Sep16); 13/6/16: 50%->70 | 28.xyz, 32.101 | SP-68 |  |  |  | 2015-06-15 10:06 | 2016-06-13 08:00
106 | 690039 | Configuration Management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-CM | 3 | Rel-14 | S5 | 2015-09-16 08:00 | 2016-12-09 17:00 | 30% | SP-160401 |  | ZTE Corporation (Zhu Weihong, zhu.weihong@zte.com.cn) | zhu.weihong@zte.com.cn | 5/10/15: 28.513; 28.512; 28.511; 28.510 added; 7/12/15: 0%->15; 7/3/16: 15%->20; 13/6/16: 20%->30 | 28.513; 28.512; 28.511; 28.510; 28.621, 28.622, 28.623, 28.704, 28.707 | SP-69 |  |  |  | 2015-06-15 10:06 | 2016-06-13 08:00
107 | 690040 | Fault Management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-FM | 3 | Rel-14 | S5 | 2015-09-16 08:00 | 2016-12-09 17:00 | 50% | SP-160403 |  | Huawei (Kai ZHANG, kai.zhangkai@huawei.com) | kai.zhangkai@huawei.com | 5/10/15: 28.518; 28.517; 28.516; 28.515 added; 7/12/15: 0%->10; 7/3/16: 10%->15; 13/6/16: 15%->50; 13/6/16: WID:SP-150404->SP-160403 | 28.515, 28.516, 28.517, 28.518, 32.111-1, 32.111-2, 32.111-6 | SP-69 |  |  |  | 2015-06-15 10:06 | 2016-06-13 08:00
108 | 690041 | Performance management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-PM | 3 | Rel-14 | S5 | 2015-09-16 08:00 | 2016-12-09 17:00 | 30% | SP-160402 |  | Intel (Joey Chou, joey.chou@intel.com) | joey.chou@intel.com | 5/10/15: 28.523; 28.522; 28.521; 28.520 added; 7/12/15: 0%->10; 7/3/16: 10%->15; 13/6/16: 15%->30; 13/6/16: WID:SP-150401->SP-160402 | 28.523; 28.522; 28.521; 28.520; 32.426, 32.409, 32.401 | SP-69 |  |  |  | 2015-06-15 10:06 | 2016-06-13 08:00
109 | 690042 | Lifecycle management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-LCM | 3 | Rel-14 | S5 | 2015-09-16 08:00 | 2016-12-09 17:00 | 25% | SP-160427 |  | Anatoly Andrianov (anatoly.andrianov@nokia.com), Nokia Networks | anatoly.andrianov@nokia.com | 5/10/15: 28.528; 28.527; 28.526; 28.525 added; 7/12/15: 0%->10; 7/3/16: 10%->15; 13/6/16: 15%->25; 13/6/16: WID:SP-150403->SP-160427 | 28.525, 28.526, 28.527, 28.528, 28.704, 28.705, 28.706, 28.707, 28.708, 28.709 | SP-69 |  |  |  | 2015-06-15 10:06 | 2016-06-13 08:00
110 | 710009 | Filtering of PM measurements and data volume | OAM14-FILMEAS | 2 | Rel-14 | S5 | 2016-03-01 08:00 | 2016-12-01 17:00 | 15% | SP-160022 |  | Ericsson: Robert Petersen | robert.petersen@ericsson.com | 13/6/16: 0%->15 | New 32.817, 32.425 | TSG#71 |  |  |  | 2016-03-01 13:40 | 2016-06-13 08:00
111 | 670028 | Study on OAM support for Licensed Shared Access (LSA) | FS_OAM_LSA | 2 | Rel-14 | S5 | 2015-03-12 08:00 | 2016-03-11 17:00 | 100% | SP-150056 |  | Nokia Networks, Anatoly Andrianov | anatoly<dot>andrianov<at>nokia<dot>com | June2015: Compl:0%->15; 07/09/15: 15%->70; 7/12/15: 70%->75; 7/3/16: 75%->100. 22/3/16: FCD: 09/15->03/16. Rel-13->Rel-14; 28/7/16: 28.303 added;; 28/7/16: 28.302 added;; 28/7/16: 28.301 added;; 28/7/16: 33.250 added;; 28/7/16: added; | 28.303; 28.302; 28.301; | SP-67 | PCG-34 |  |  | 2015-03-12 02:28 | 2016-07-28 08:00
112 | 720044 | OAM support for Licensed Shared Access (LSA) | OAM14-LSA | 2 | Rel-14 | S5 | 2016-06-13 08:00 | 2017-06-12 17:00 | 0% | SP-160397 |  | Nokia: Olaf Pollakowski |  | 28/7/16: 28.303 added;; 28/7/16: 28.302 added;; 28/7/16: 28.301 added; | 32.101; 28.303; 28.302; 28.301 | TSG#72 |  |  |  | 2015-03-12 02:28 | 2016-07-28 08:00
113 | 680050 | Development of super-wideband and fullband P.835 | DESUDAPS | 1 | Rel-14 | S4 | 2015-06-16 08:00 | 2016-12-14 17:00 | 60% | SP-150215 |  | Scott Isabelle (Knowles, Inc.) | sisabelle@audience.com | 06/15: FCD corrected to Dec.15; Aug2015: 0%->5; 07/09/15: 5%->20, FCD: 12/15->06.16; 7/12/15: 20%->40, MOVED TO REL-14; 7/3/16: 40%->50. 15/4/16: 6/16->12/16; 11/6/16: 50%->60 | 26.131, 26.132 | SP-68 |  |  |  | 2015-06-18 11:21 | 2016-06-11 08:00
114 | 670004 | Enhancing Location Capabilities for Indoor and Outdoor Emergency Communications | ELIOT | 1 | Rel-14 | S1 | 2015-03-11 08:00 | 2015-12-15 17:00 | 100% | SP-150044 |  | Greg Schumacher | Gregory.schumacher@sprint.com | 1/4/15: rapporteur added, Impacted TS added; June2015: Compl:0%->25; 07/09/15: 25%->80; 2/3/16: 80%->100 | 22.101, 22.071 | SP-67 | PCG-34 |  |  | 2015-03-04 10:16 | 2016-03-02 08:00
115 | 670005 | Enhancements to Domain Selection between VoLTE and CDMA CS | eDSVCC | 1 | Rel-14 | S1 | 2015-03-11 08:00 | 2015-06-15 17:00 | 100% | SP-150045 |  | China Telecom, Hongmei Zhu | zhuhongmei@gsta.com | 1/4/15: rapporteur added, Impacted TS added; June2015: Compl:0%->100 | 22.101 | SP-67 | PCG-34 |  |  | 2015-03-04 10:16 | 2015-06-15 08:00
116 | 680002 | Control of Applications when Third party Servers encounter difficulties | CATS | 1 | Rel-14 | S1 | 2015-05-11 08:00 | 2015-09-16 17:00 | 100% | SP-150273 |  | Eriko Yoshida, KDDI | er-yoshida (at) kddi (dot) com | 07/09/15: 0%->100 | 22.011 | SP-68 |  |  |  | 2015-06-09 11:05 | 2015-09-07 08:00
117 | 720074 | Password based service activation for IMS Multimedia Telephony service | PWDIMS | 1 | Rel-14 | S1 | 2015-03-11 08:00 | 2016-12-15 17:00 | 1% | SP-150041 |  | Peter Bleckert (Ericsson) |  | 1/4/15: rapporteur added, Impacted TS added. 31/07/15: 100% | 22.173 | SP-67 | PCG-34 |  |  | 2015-03-04 10:16 | 2015-07-31 08:00
118 | 670012 | Stage 1 for PWDIMS | PWDIMS | 2 | Rel-14 | S1 | 2015-03-11 08:00 | 2015-03-13 17:00 | 100% | SP-150041 |  | Peter Bleckert (Ericsson) |  | 1/4/15: rapporteur added, Impacted TS added. 31/07/15: 100% | 22.173 | SP-67 | PCG-34 |  |  | 2015-03-04 10:16 | 2015-07-31 08:00
119 | 720034 | CT aspects for PWDIMS | PWDIMS-CT | 2 | Rel-14 | ct | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | CP-160295 |  | Axell, Jörgen |  |  |  | TSG#72 |  |  |  | 2016-06-11 06:33 | NA
120 | 720035 | CT1 aspects for PWDIMS | PWDIMS-CT | 3 | Rel-14 | C1 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | CP-160295 |  | Axell, Jörgen |  |  | 24.623, 24.611 | TSG#72 |  |  |  | 2016-06-11 06:33 | NA
121 | 720036 | CT3 aspects for PWDIMS | PWDIMS-CT | 3 | Rel-14 | C3 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | CP-160295 |  | Axell, Jörgen |  |  | 29.292 | TSG#72 |  |  |  | 2016-06-11 06:33 | NA
122 | 720080 | PS Data Off Services | PS_Data_Off | 1 | Rel-14 | S1 | 2015-11-09 08:00 | 2016-09-15 17:00 | 58% | SP-150823 |  | Orange, Bruno Tossou | bruno.tossou@orange.com | 2/3/16: 0%->100 | 22.030 | SP-70 |  |  |  | 2015-12-07 11:57 | 2016-03-02 08:00
123 | 700033 | PS Data Off Services | PS_Data_Off | 2 | Rel-14 | S1 | 2015-11-09 08:00 | 2016-03-15 17:00 | 100% | SP-150823 |  | Orange, Bruno Tossou | bruno.tossou@orange.com | 2/3/16: 0%->100 | 22.030 | SP-70 |  |  |  | 2015-12-07 11:57 | 2016-03-02 08:00
124 | 720079 | Study on Stage 2 of PS Data off function | FS_PS_DATA_OFF | 2 | Rel-14 | S2 | 2016-06-17 08:00 | 2016-09-15 17:00 | 0% | SP-160318 |  | Orange, david <dot> cailliere <at> orange <dot> com | david <dot> cailliere <at> orange <dot> com | 28/7/16: 23.702 added; | TR 23.702 | SP-72 |  |  |  | 2016-06-17 07:09 | 2016-07-28 08:00
125 | 710003 | SCC AS Restoration | SCCAS_RES | 1 | Rel-14 | C4 | 2016-03-02 08:00 | 2016-12-15 17:00 | 100% | CP-160118 |  | China Mobile, Hao Zhang, | zhanghao@chinamobile.com | 13/6/16: 0%->100 | 23.380 | TSG#71 |  |  |  | 2016-03-02 11:24 | 2016-06-13 08:00
126 | 710004 | Paging Policy Enhancements and Procedure | PPEPO_LTE | 1 | Rel-14 | S1 | 2016-02-01 08:00 | 2016-03-01 17:00 | 100% | SP-160113 |  | China Unicom, Zhuoyun Zhang | zhangzy910@chinaunicom.cn |  | 22.101 | TSG#71 |  |  |  | 2016-03-01 13:09 | 2016-03-01 08:00
127 | 720077 | Enhancement to Flexible Mobile Service Steering | eFMSS | 1 | Rel-14 | S1 | 2015-05-11 08:00 | 2016-09-15 17:00 | 73% | SP-160115 |  | China Mobile, Lu Lu | lulu@chinamobile.com |  | 22.115, 22.101 | SP-72 |  |  |  | 2016-03-01 13:12 | 2016-03-01 08:00
128 | 680003 | Study on enhancement to FMSS for Rel 14 | FS_eFMSS | 2 | Rel-14 | S1 | 2015-05-11 08:00 | 2015-12-16 17:00 | 100% | SP-150280 |  | Lu Lu, China Mobile | lulu@chinamobile.com | 7/12/15: 70%->100 | 22.808 | SP-68 |  |  |  | 2015-06-09 11:19 | 2015-12-07 08:00
129 | 710005 | Stage 1 of Enhancement to Flexible Mobile Service Steering | eFMSS | 2 | Rel-14 | S1 | 2016-02-01 08:00 | 2016-03-01 17:00 | 100% | SP-160115 |  | China Mobile, Lu Lu | lulu@chinamobile.com |  | 22.115, 22.101 | TSG#71 |  |  |  | 2016-03-01 13:12 | 2016-03-01 08:00
130 | 720078 | Stage 2 of Enhancement to Flexible Mobile Service Steering | eFMSS | 2 | Rel-14 | S2 | 2016-06-17 08:00 | 2016-09-15 17:00 | 0% | SP-160314 |  | ZTE, Tricci So |  |  | 23.203 | SP-72 |  |  |  | 2016-03-01 13:12 | NA
131 | 710006 | Unlicensed Spectrum Offloading System | USOS | 1 | Rel-14 | S1 | 2016-02-01 08:00 | 2016-03-01 17:00 | 100% | SP-160117 |  | Edward Hall, Qualcomm Incorporated | edhall@qti.qualcomm.com |  | 22.101, 22.115 | TSG#71 |  |  |  | 2016-03-01 13:15 | 2016-03-01 08:00
132 | 710010 | Media Handling Extensions of IMS-based Telepresence | IMS_TELEP_EXT | 1 | Rel-14 | S4 | 2016-03-01 08:00 | 2016-12-01 17:00 | 5% | SP-160081 |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 11/6/16: 0%->10 | 26.223 | TSG#71 |  |  |  | 2016-03-01 13:35 | 2016-06-11 08:00
133 | 721005 | S4 aspects of Media Handling Extensions of IMS-based Telepresence | IMS_TELEP_EXT | 2 | Rel-14 | S4 | 2016-03-01 08:00 | 2016-12-01 17:00 | 10% | SP-160081 |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 11/6/16: 0%->10 | 26.223 | TSG#72 |  |  |  | 2016-03-01 13:35 | 2016-06-11 08:00
134 | 720061 | (IETF) Other IETF aspects of IMS_TELEP_EXT | IMS_TELEP_EXT | 2 | Rel-14 | S4-IETF | 2016-03-01 08:00 | 2016-12-01 17:00 | 0% |  |  |  | ozgur.oyman@intel.com |  | draft-ietf-payload-rtp-h265, -flexible-fec-scheme , draft-ietf-clue-framework , -datachannel, -signalling, -data-model-schema, -protocol, -rtp-mapping, draft-ietf-mmusic-sctp-sdp, -data-channel-sdpneg, draft-ietf-tsvwg-sctp-dtls-encaps | TSG#72 |  |  |  | 2016-03-01 13:35 | NA
135 | 710011 | Improved Streaming QoE Reporting in 3GPP | IQoE | 1 | Rel-14 | S4 | 2016-03-01 08:00 | 2016-12-01 17:00 | 10% | SP-160082 |  | Zhiming Li, Huawei | Lizhiming@huawei.com | 11/6/16: 0%->10 | New 26.909, 26.247, 26.346 | TSG#71 |  |  |  | 2016-03-01 13:38 | 2016-06-11 08:00
136 | 710085 | New GPRS algorithms for EASE | EASE_ALGOs_SA3 | 1 | Rel-14 | S3 | 2016-03-15 08:00 | 2016-06-15 17:00 | 60% | SP-160203 |  | Tim Evans, Vodafone |  | Discussion whether it should be Rel-13. To be concluded at SA#72.; 13/6/16: 0%->60 | 55.241, 55.242, 55.243, 55.251, 55.252, 55.253 | TSG#71 |  |  |  | 2016-03-22 16:25 | 2016-06-13 08:00
137 | 710048 | S8 Home Routing Architecture for VoLTE | V8 | 1 | Rel-14 | S2,S3 | 2015-06-18 08:00 | 2016-09-15 17:00 | 75% | SP-160315 |  |  |  | Umbrella, created by MCC to group SA2 and SA3 activities |  | TSG#71 |  |  |  | 2016-03-11 10:01 | 2016-03-11 08:00
138 | 680053 | Study on S8 Home Routing Architecture | FS_V8 | 2 | Rel-14 | S2 | 2015-06-18 08:00 | 2016-03-10 17:00 | 100% | SP-150255 |  | Motohiro ABE | motohiro(dot)abe(dot)cu(at) nttdocomo (dot) com | 07/09/15: 0%->10; 07/09/15: 10%->100; 7/12/15: 100%->10% (mistake?) then 10%->70, FCD: 12/15-?03/16; 7/3/16: 70%->80; 9/6/16: 80%->100 | New TR 23.xxx | SP-68 |  |  |  | 2015-06-18 11:42 | 2016-06-09 08:00
139 | 690049 | Study on LI in S8 Home Routing Architecture for VoLTE | FS_LIV8 | 2 | Rel-14 | S3 | 2015-09-17 08:00 | 2016-06-17 17:00 | 55% | SP-150461 |  | Greg Schumacher (SPRINT) Gregory | Schumacher@sprint.com | 7/12/15: 0%->45; 28/1/16: 33.827 added;; 7/3/16: 45%->55 | TR 33.827 | SP-69 |  |  |  | 2015-09-17 00:20 | 2016-03-07 08:00
140 | 720017 | S8 Home Routing Architecture for VoLTE | V8 | 2 | Rel-14 | S2 | 2016-06-13 08:00 | 2016-09-15 17:00 | 60% | SP-160315 |  | Motohiro ABE | motohiro(dot)abe(dot)cu(at) nttdocomo (dot) com | 11/6/16: 0%->60 | TS 23.228, TS 23.167, TS 23.203 | TSG#72 |  |  |  | 2015-06-18 11:42 | 2016-06-11 08:00
141 | 720019 | Phase 2 of the Support of Emergency services over WLAN | SEW2 | 1 | Rel-14 | S2 | 2015-09-01 08:00 | 2016-09-15 17:00 | 86% | SP-160307 |  | Nicolas Drevon | nicolas.drevon@nokia.com |  | new 23.771, TS 23.402, TS 23.167 | TSG#72 |  |  |  | 2015-04-01 18:15 | 2016-06-09 08:00
142 | 690033 | Study on Phase 2 of the Support of Emergency services over WLAN | FS_SEW2 | 2 | Rel-14 | S2 | 2015-09-01 08:00 | 2016-06-16 17:00 | 100% | SP-160173 |  | Laurent Thiebaut, Alcatel Lucent | Laurent.thiebaut@alcatel-lucent.com | June2015: Compl:0%->100, SP-150151->SP-150251; 7/12/15: 0%->30, FCD: 12/15->06/16; 7/3/16: 30%->75; 7/3/16: WID:SP-150251->SP-160173; 9/6/16: 75%->100 | new 23.771 | SP-67 | PCG-34 |  |  | 2015-04-01 18:15 | 2016-06-09 08:00
143 | 720018 | Support of Emergency services over WLAN - phase 2 | SEW2 | 2 | Rel-14 | S2 | 2016-06-13 08:00 | 2016-09-15 17:00 | 45% | SP-160307 |  | Nicolas Drevon | nicolas.drevon@nokia.com | 11/6/16: 0%->45 | TS 23.402, TS 23.167 | TSG#72 |  |  |  | 2015-04-01 18:15 | 2016-06-11 08:00
144 | 720020 | Improvements of awareness of user location change | AULC | 1 | Rel-14 | S2 | 2015-09-17 08:00 | 2016-09-15 17:00 | 75% | SP-160308 |  | Yang Xu | xuyang49@chinaunicom.cn |  |  | TSG#72 |  |  |  | 2015-09-17 00:23 | 2016-06-09 08:00
145 | 690050 | Study on improvement of awareness of user location change | FS_AULC | 2 | Rel-14 | S2 | 2015-09-17 08:00 | 2016-06-17 17:00 | 100% | SP-150517 |  | Yang Xu | xuyang49@chinaunicom.cn | 7/12/15: 0%->40; 7/3/16: 40%->70; 9/6/16: 70%->100 | 23.710 | SP-69 |  |  |  | 2015-09-17 00:23 | 2016-06-09 08:00
146 | 720021 | Improvements of awareness of user location change | AULC | 2 | Rel-14 | S2 | 2016-06-06 08:00 | 2016-09-15 17:00 | 10% | SP-160308 |  | Yang Xu | xuyang49@chinaunicom.cn | 11/6/16: 0%->10 | 23.401, 23.203, 23.060 | TSG#72 |  |  |  | 2015-09-17 00:23 | 2016-06-11 08:00
147 | 720022 | Service Domain Centralization | SeDoC | 1 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-09-15 17:00 | 54% |  |  | Chris Joul (T-Mobile USA) | chris (dot) joul (at) t (dash) mobile (dot) com |  |  | TSG#72 |  |  |  | 2015-12-07 14:16 | 2016-06-09 08:00
148 | 700040 | Study on Service Domain Centralization | FS_SeDoC | 2 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-09-15 17:00 | 70% | SP-160306 |  | Chris Joul (T-Mobile USA) | chris (dot) joul (at) t (dash) mobile (dot) com | Comes back from previous release; 28/1/16: 23.719 added;; 7/3/16: 0%->30; 7/3/16: WID:SP-150626->SP-1601679/6/16: 30%->70; 11/6/16: WID:SP-160167->SP-160306. FCD: 06/16->09/16 | 23.719 | SP-70 |  |  |  | 2015-12-07 14:16 | 2016-06-11 08:00
149 | 720023 | Service Domain Centralization | SeDoC | 2 | Rel-14 | S2 | 2016-06-13 08:00 | 2016-09-15 17:00 | 0% |  |  | Chris Joul (T-Mobile USA) | chris (dot) joul (at) t (dash) mobile (dot) com |  |  | TSG#72 |  |  |  | 2015-12-07 14:16 | 2016-06-09 08:00
150 | 720014 | Sponsored data connectivity improvements | SDCI | 1 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-09-15 17:00 | 70% | SP-160309 |  | Yang Xu | xuyang49@chinaunicom.cn |  |  | TSG#72 |  |  |  | 2015-12-07 14:20 | 2016-06-09 08:00
151 | 700041 | Study on sponsored data connectivity improvements | FS_SDCI | 2 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-150627 |  | Yang Xu | xuyang49@chinaunicom.cn | 28/1/16: 23.721 added;; 7/3/16: 10%->40; 9/6/16: 40%->100 | 23.721 | SP-70 |  |  |  | 2015-12-07 14:20 | 2016-06-09 08:00
152 | 720024 | Sponsored data connectivity improvements | SDCI | 2 | Rel-14 | S2 | 2016-06-13 08:00 | 2016-09-15 17:00 | 0% | SP-160309 |  | Yang Xu | xuyang49@chinaunicom.cn |  | 23.203, 23.682 | TSG#72 |  |  |  | 2015-12-07 14:20 | 2016-06-09 08:00
153 | 710017 | Stage-3 SAE Protocol Development - Phase 5 | SAES5 | 1 | Rel-14 | C1 | 2016-03-02 08:00 | 2017-03-15 17:00 | 7% | CP-160052 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com |  | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | TSG#71 |  |  |  | 2016-03-02 10:16 | 2016-03-02 08:00
154 | 710018 | SAES5 CS Fallback in EPS | SAES5-CSFB | 2 | Rel-14 | C1 | 2016-03-02 08:00 | 2017-03-15 17:00 | 5% | CP-160052 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com | 11/6/16: 0%->5 | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | TSG#71 |  |  |  | 2016-03-02 10:16 | 2016-06-11 08:00
155 | 710019 | SAES5 for support for non-3GPP accesses | SAES5-non3GPP | 2 | Rel-14 | C1 | 2016-03-02 08:00 | 2017-03-15 17:00 | 15% | CP-160052 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com | 11/6/16: 0%->15 | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | TSG#71 |  |  |  | 2016-03-02 10:16 | 2016-06-11 08:00
156 | 720073 | SAE Protocol Development (Stage 3) - Phase 5 | SAES5 | 2 | Rel-14 | C1 | 2016-03-02 08:00 | 2017-03-15 17:00 | 0% | CP-160052 |  |  |  | Added following CT1's chair e-mail 14/06/16 |  | CT-72 |  |  |  | 2015-03-24 11:27 | NA
157 | 720015 | System Architecture Enhancements to eMBMS for TV Video Service | AE_enTV | 1 | Rel-14 | S2 | 2016-03-11 08:00 | 2016-09-15 17:00 | 70% | [6 empty] | TSG#71 |  |  |  | 2016-03-11 11:08 | 2016-06-09 08:00
158 | 710046 | Study on System Architecture Enhancements to eMBMS for TV Video Service | FS_AE_enTV | 2 | Rel-14 | S2 | 2016-03-11 08:00 | 2016-09-15 17:00 | 70% | SP-160225 |  | Miguel Griot, Qualcomm |  | 9/6/16: 0%->70; 28/7/16: 23.746 added; | TR 23.746 | TSG#71 |  |  |  | 2016-03-11 11:08 | 2016-07-28 08:00
159 | 720016 | System Architecture Enhancements to eMBMS for TV Video Service | AE_enTV | 2 | Rel-14 | S2 | 2016-06-09 08:00 | 2016-06-09 08:00 | 0% |  |  |  |  | CHECK |  | TSG#72 |  |  |  | 2016-03-11 11:08 | NA
160 | 720012 | Group based enhancements in the network capability exposure functions | GENCEF | 1 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-09-15 17:00 | 69% | SP-160311 |  | Samsung, Sung Hwan Won | sunghwan.won@samsung.com |  |  | SP-70 |  |  |  | 2015-12-07 14:27 | 2016-06-09 08:00
161 | 700043 | Study on group based enhancements in the network capability exposure functions | FS_GENCEF | 2 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-160311 |  | Samsung, Sung Hwan Won | sunghwan.won@samsung.com | 28/1/16: 23.773 added;; 28/1/16: 23.742 added;; 7/3/16: 0%->10; 9/6/16: 10%->100 | 23.xyz; 23.773; 23.742 | SP-70 |  |  |  | 2015-12-07 14:27 | 2016-06-09 08:00
162 | 720013 | Group based enhancements in the network capability exposure functions | GENCEF | 2 | Rel-14 | S2 | 2016-06-09 08:00 | 2016-09-15 17:00 | 0% | SP-160311 |  | Samsung, Sunghoon Kim | s.hun.kim@samsung.com |  | 23.682 | TSG#72 |  |  |  | 2015-12-07 14:27 | 2016-06-09 08:00
163 | 720084 | Robust Call Setup for VoLTE subscriber in LTE | RobVoLTE | 1 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-09-15 17:00 | 71% | SP-160312 | [5 empty] | SP-72 |  |  |  | 2015-12-07 14:29 | NA
164 | 700044 | Study on Robust Call Setup for VoLTE subscriber in LTE | FS_RobVoLTE | 2 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-150632 |  | Xiaobo Wu, Huawei | wuxiaobo@ huawei.com | 28/1/16: 23.750 added;; 7/3/16: 0%->20; 9/6/16: 20%->100 | 23.8xx; 23.750 | SP-70 |  |  |  | 2015-12-07 14:29 | 2016-06-09 08:00
165 | 721006 | Robust Call Setup for VoLTE subscriber in LTE | RobVoLTE | 2 | Rel-14 | S2 | 2016-06-17 08:00 | 2016-09-15 17:00 | 0% | SP-160312 |  | Xiaobo Wu, Huawei | wuxiaobo@ huawei.com |  | 23.228, 23.237 | SP-72 |  |  |  | 2015-12-07 14:29 | NA
166 | 720028 | Extension of UE Delay test methods and requirements | EXT_UED | 1 | Rel-14 | S4 | 2016-06-13 08:00 | 2017-03-15 17:00 | 0% | SP-160271 |  | Stéphane Ragot, ORANGE | stephane.ragot@orange.com |  | 26.131, 26.132 | TSG#72 |  |  |  | 2016-06-11 05:48 | NA
167 | 720076 | T-ADS supporting WLAN Access | TADS_WLAN | 1 | Rel-14 | S2 | 2016-06-09 08:00 | 2016-09-15 17:00 | 0% | SP-160488 |  | Jiang Yi | jiangyi (at) chinamobile (dot) com |  | TS 23.292, TS 23.221, TS 23.402 | SP-72 |  |  |  | 2016-06-17 03:25 | NA
168 | 720037 | Improved operator control using new UE configuration parameters | IOC_UE_conf | 1 | Rel-14 | C1 | 2016-06-13 08:00 | 2017-03-15 17:00 | 5% | CP-160296 |  | Sedlacek, Ivo | ivo.sedlacek@ericsson.com | 11/6/16: 0%->10 | 24.167, 24.229, 24.301, 24.302, 24.312, 24.341, 24.368, 24.607, 24.623, TS 24.XXX, TS 24.YYY | TSG#72 |  |  |  | 2016-06-11 06:37 | 2016-06-11 08:00
169 | 720038 | CT1 aspects of IOC_UE_conf | IOC_UE_conf | 2 | Rel-14 | C1 | 2016-06-13 08:00 | 2017-03-15 17:00 | 10% | CP-160296 |  | Sedlacek, Ivo | ivo.sedlacek@ericsson.com | 11/6/16: 0%->10 | 24.167, 24.229, 24.301, 24.302, 24.312, 24.341, 24.368, 24.607, 24.623, TS 24.XXX, TS 24.YYY | TSG#72 |  |  |  | 2016-06-11 06:37 | 2016-06-11 08:00
170 | 720039 | CT6 aspects of IOC_UE_conf | IOC_UE_conf | 2 | Rel-14 | C6 | 2016-06-13 08:00 | 2017-03-15 17:00 | 0% | CP-160354 |  | Adrian Buckley | abuckley@blackberry.com | 11/6/16: 0%->10 | 31.102, 31.103 | TSG#72 |  |  |  | 2016-06-11 06:37 | 2016-06-11 08:00
171 | 720001 | Shared Subscription Data Update | eSDU | 1 | Rel-14 | C4 | 2016-06-13 08:00 | 2016-12-15 17:00 | 25% | CP-160243 |  | Nokia, Ulrich Wiehe | ulrich.wiehe@nokia.com | 13/6/16: 0%->25 | 29.272, 29.002, 29.305, 29.230 | TSG#72 |  |  |  | 2016-06-13 02:14 | 2016-06-13 08:00
172 | 720075 | Security Assurance Specification for PGW network product class | SCAS_PGW | 1 | Rel-14 | S3 | 2016-06-17 08:00 | 2017-06-15 17:00 | 0% | SP-160481 |  | Peng Jin, China Mobile | pengjin@chinamobile.com | 28/7/16: 33.250 added; | TS 33.zzz; 33.250 | SP-72 |  |  |  | 2016-06-17 02:28 | 2016-07-28 08:00
173 | 710012 | Rel-14 Charging | CH14 | 1 | Rel-14 | S5 | 2016-03-01 08:00 | 2017-03-15 17:00 | 3% | SP-160021 |  |  |  | Umbrella Feature |  | TSG#71 |  |  |  | 2016-03-01 14:31 | 2016-03-01 08:00
174 | 710008 | Resource Optimization for PS Domain Online | CH14-ROPOCH | 2 | Rel-14 | S5 | 2016-03-01 08:00 | 2017-03-15 17:00 | 10% | SP-160021 |  | Shrader, David(Ericsson) | david.shrader@ericsson.com | 13/6/16: 0%->10. FCD:09/16->03/17 | 32.251, 32.299 | TSG#71 |  |  |  | 2016-03-01 13:40 | 2016-06-13 08:00
175 | 720045 | Determination of Completeness of Charging Information in IMS | CH14-DCCII | 2 | Rel-14 | S5 | 2016-06-13 08:00 | 2017-03-15 17:00 | 0% | SP-160398 |  | Jesske, Roland (Deutsche Telekom) |  |  | 32.240, 32.260, 32.298, 32.299 | TSG#72 |  |  |  | 2016-06-13 03:07 | NA
176 | 720049 | Charging Aspects of Enhanced Proximity-based Services | CH14-ProSe | 2 | Rel-14 | S5 | 2016-06-13 08:00 | 2017-03-15 17:00 | 0% | SP-160428 |  | Chen, Shan | chenshan@huawei.com |  | 32.240, 32.251, 32.277, 32.298, 32.299 | TSG#72 |  |  |  | 2016-06-13 03:20 | NA
177 | 720050 | Charging Aspects of S8 Home Routing Architecture for VoLTE | CH14-V8 | 2 | Rel-14 | S5 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | SP-160429 |  | Chen, Ai (China Mobile) | chenai(at) chinamobile (dot) com |  | 32.240, 32.251, 32.260 | TSG#72 |  |  |  | 2016-06-13 03:23 | NA
178 | 700060 | Enhanced LAA for LTE | LTE_eLAA | 1 | Rel-14 | R1 | 2015-12-15 08:00 | 2017-03-15 17:00 | 23% | RP-152272 |  | Ericsson |  |  |  | RP-70 |  |  |  | 2016-01-07 10:48 | 2015-12-22 08:00
179 | 700160 | Core part: Enhanced LAA for LTE | LTE_eLAA-Core | 2 | Rel-14 | R1 | 2015-12-15 08:00 | 2016-09-15 17:00 | 60% | RP-160881 |  | Ericsson |  | 22/3/16: Compl:0%->20%22/3/16: WID: RP-152272->RP-1604071/7/16: Compl:20%->60%1/7/16: WID: RP-160407->RP-160881 |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
180 | 700260 | Perf. part: Enhanced LAA for LTE | LTE_eLAA-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 0% | RP-160881 |  | Ericsson |  | 22/3/16: WID: RP-152272->RP-160407; 1/7/16: WID: RP-160407->RP-160881 |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
181 | 700062 | RRC optimization for UMTS | UTRA_RRCopt | 1 | Rel-14 | R2 | 2015-12-15 08:00 | 2016-09-15 17:00 | 70% | RP-152267 |  | Ericsson |  |  |  | RP-70 |  |  |  | 2016-01-07 10:49 | 2015-12-22 08:00
182 | 700162 | Core part: RRC optimization for UMTS | UTRA_RRCopt-Core | 2 | Rel-14 | R2 | 2015-12-15 08:00 | 2016-09-15 17:00 | 70% | RP-160287 |  | Ericsson |  | 22/3/16: Compl:0%->8%; ;...; 1/7/16: Compl:8%->70% |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
183 | 700063 | DTX/DRX enhancements in CELL_FACH | FACH_DTXDRX | 1 | Rel-14 | R2 | 2015-12-15 08:00 | 2016-09-15 17:00 | 50% | RP-152286 |  | Huawei |  |  |  | RP-70 |  |  |  | 2016-01-07 10:49 | 2015-12-22 08:00
184 | 700163 | Core part: DTX/DRX enhancements in CELL_FACH | FACH_DTXDRX-Core | 2 | Rel-14 | R2 | 2015-12-15 08:00 | 2016-09-15 17:00 | 50% | RP-160601 |  | Huawei |  | 22/3/16: Compl:0%->20%; ...1/7/16: Compl:20%->50% |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
185 | 700077 | AWS-3/4 Band for LTE | LTE_AWS_3_4 | 1 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-151731 |  | Dish Network |  |  |  | RP-70 |  |  |  | 2016-01-07 10:59 | 2015-12-22 08:00
186 | 700177 | Core part: AWS-3/4 Band for LTE | LTE_AWS_3_4-Core | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-160783 |  | Dish Network |  | ; 22/3/16: Compl:0%->60%; 1/7/16: Compl:60%->100%; 1/7/16: CD:Th... | 36.749 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
187 | 700277 | Perf. part: AWS-3/4 Band for LTE | LTE_AWS_3_4-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-160783 |  | Dish Network |  | 1/7/16: Compl:0%->100%1/7/16: CD:Thu 15/09/16->Wed 15/06... |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
188 | 700078 | LTE FDD in the Bands 1980-2010 MHz and 2170-2200MHz for Region 3 | LTE_1980_2170_REG3 | 1 | Rel-14 | R4 | 2015-12-15 08:00 | 2015-12-15 17:00 | 0% | RP-152238 |  | KT Corp. |  |  |  | RP-70 |  |  |  | 2016-01-07 10:59 | 2015-12-22 08:00
189 | 700178 | Core part: LTE FDD in the Bands 1980-2010 MHz and 2170-2200MHz for Region 3 | LTE_1980_2170_REG3-Core | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2015-12-15 17:00 | 0% | RP-152238 |  | KT Corp. |  |  |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2015-12-22 08:00
190 | 700079 | LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1 | LTE_FDD_2600_CA_B3 | 1 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-152253 |  | Orange |  |  |  | RP-70 |  |  |  | 2016-01-07 10:59 | 2015-12-22 08:00
191 | 700179 | Core part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1 | LTE_FDD_2600_CA_B3-Core | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-161200 |  | Orange |  | 28/1/16: 36.858 added;22/3/16: Compl:0%->40%22/3/16: WID: RP-152253->RP-160378; 1/7/16: Compl:40%->100%;... | 36.858 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
192 | 700279 | Perf. part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1 | LTE_FDD_2600_CA_B3-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-161200 |  | Orange |  | ; 22/3/16: WID: RP-152253->RP-1603781/7/16: Compl:0%->100%1/7/16... |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
193 | 700080 | Multi-Band Base Station testing with three or more bands | MB_BS_test_3B | 1 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-09-15 17:00 | 60% | RP-152205 |  | Alcatel-Lucent |  |  |  | RP-70 |  |  |  | 2016-01-07 10:59 | 2015-12-22 08:00
194 | 700180 | Core part: Multi-Band Base Station testing with three or more bands | MB_BS_test_3B-Core | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-09-15 17:00 | 90% | RP-160063 |  | Alcatel-Lucent |  | 22/3/16: Compl:0%->50%22/3/16: WID: RP-152205->RP-1600631/7/16: Compl:50%->90% | 37.871 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
195 | 700280 | Perf. part: Multi-Band Base Station testing with three or more bands | MB_BS_test_3B-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-09-15 17:00 | 30% | RP-160063 |  | Alcatel-Lucent |  | 22/3/16: Compl:0%->5%22/3/16: WID: RP-152205->RP-160063; 1/7/16: Compl:5%->30% |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
196 | 700081 | Performance enhancements for high speed scenario in LTE | LTE_high_speed | 1 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 22% | RP-152263 |  | NTT DOCOMO |  |  |  | RP-70 |  |  |  | 2016-01-07 10:59 | 2015-12-22 08:00
197 | 700181 | Core part: Performance enhancements for high speed scenario in LTE | LTE_high_speed-Core | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-12-15 17:00 | 25% | RP-160172 |  | NTT DOCOMO |  | 22/3/16: Compl:0%->5%22/3/16: WID: RP-152263->RP-160172; 1/7/16: Compl:5%->25% |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
198 | 700282 | Perf. part: Performance enhancements for high speed scenario in LTE | LTE_high_speed-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 20% | RP-160172 |  | NTT DOCOMO |  | 22/3/16: WID: RP-152263->RP-1601721/7/16: Compl:0%->20% |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
199 | 710047 | Remote UE access via relay UE | REAR | 1 | Rel-14 | S1 | 2016-03-01 08:00 | 2016-06-15 17:00 | 100% | SP-160371 |  | Huawei, Laurence Meriau | laurence.meriau@huawei.com | Previously known as "wearable devices"; 9/6/16: 0%->100; 9/6/16: WID:SP-160231->SP-160371 | 22.278, 22.115 | TSG#71 |  |  |  | 2016-03-11 11:18 | 2016-06-09 08:00
200 | 710072 | Further Indoor Positioning Enhancements for UTRA and LTE | UTRA_LTE_iPos_enh2 | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2017-03-15 17:00 | 13% | RP-160538 |  | Huawei |  | follow-up WI of REL-13 WI UTRA_LTE_iPos_enh |  | TSG#71 |  |  |  | 2016-03-22 11:01 | 2016-03-22 08:00
201 | 710172 | Core part: Further Indoor Positioning Enhancements for UTRA and LTE | UTRA_LTE_iPos_enh2-Core | 2 | Rel-14 | R2 | 2016-03-15 08:00 | 2016-12-15 17:00 | 30% | RP-160538 | - | Huawei |  | follow-up WI of REL-13 WI UTRA_LTE_iPos_enh1/7/16: Compl:0%->30% |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
202 | 710272 | Perf. part: Further Indoor Positioning Enhancements for UTRA and LTE | UTRA_LTE_iPos_enh2-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-03-15 17:00 | 0% | RP-160538 | - | Huawei |  |  |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-03-22 08:00
203 | 710073 | Signalling reduction to enable light connection for LTE | LTE_LIGHT_CON | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2017-03-15 17:00 | 10% | RP-160540 |  | Huawei |  | no Perf. part |  | TSG#71 |  |  |  | 2016-03-22 11:01 | 2016-03-22 08:00
204 | 710173 | Core part: Signalling reduction to enable light connection for LTE | LTE_LIGHT_CON-Core | 2 | Rel-14 | R2 | 2016-03-15 08:00 | 2017-03-15 17:00 | 10% | RP-160937 | - | Huawei |  | no Perf. part; 1/7/16: Compl:0%->10%; 1/7/16: CD:Thu 15/12/16->Wed 15/03/17; 1/7/16: WID: RP-160540->RP-160937 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
205 | 710075 | Enhanced LTE-WLAN Aggregation (LWA) | LTE_WLAN_aggr | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2017-03-15 17:00 | 25% | RP-160600 |  | Intel |  | follow-up WI of REL-13 WI LTE_WLAN_radio; no Perf. part |  | TSG#71 |  |  |  | 2016-03-22 11:01 | 2016-03-22 08:00
206 | 710175 | Core part: Enhanced LTE-WLAN Aggregation (LWA) | LTE_WLAN_aggr-Core | 2 | Rel-14 | R2 | 2016-03-15 08:00 | 2017-03-15 17:00 | 25% | RP-160923 | - | Intel |  | follow-up WI of REL-13 WI LTE_WLAN_radio; no Perf. part1/7/16: Compl:0%->25%1/7/16: WID: RP-160600->RP-160923 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
207 | 710076 | Radiated performance requirements for the verification of multi-antenna reception of UEs in LTE | LTE_MIMO_OTA | 1 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-03-15 17:00 | 10% | RP-160603 |  | Intel |  | follow-up WI of REL-13 WI UTRA_LTE_MIMO_OTA-Core; no Perf. part |  | TSG#71 |  |  |  | 2016-03-22 11:01 | 2016-03-22 08:00
208 | 710176 | Core part: Radiated performance requirements for the verification of multi-antenna reception of UEs in LTE | LTE_MIMO_OTA-Core | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-03-15 17:00 | 10% | RP-160914 | - | Intel |  | follow-up WI of REL-13 WI UTRA_LTE_MIMO_OTA-Core; no Perf. part1/7/16: Compl:0%->10%1/7/16: WID: RP-160603->RP-160914 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
209 | 710077 | Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-09-15 17:00 | 10% | RP-160623 |  | Samsung |  |  |  | TSG#71 |  |  |  | 2016-03-22 11:01 | 2016-03-22 08:00
210 | 710177 | Core part: Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO-Core | 2 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-03-15 17:00 | 25% | RP-160623 | - | Samsung |  | ; 1/7/16: Compl:0%->25% |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
211 | 710277 | Perf. part: Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-09-15 17:00 | 0% | RP-160623 | - | Samsung |  |  |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-03-22 08:00
212 | 710078 | Further mobility enhancements in LTE | LTE_eMob | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2016-12-15 17:00 | 25% | RP-160636 |  | ZTE |  | no Perf. part |  | TSG#71 |  |  |  | 2016-03-22 11:01 | 2016-03-22 08:00
213 | 710178 | Core part: Further mobility enhancements in LTE | LTE_eMob-Core | 2 | Rel-14 | R2 | 2016-03-15 08:00 | 2016-12-15 17:00 | 25% | RP-160921 | - | ZTE |  | no Perf. part; 1/7/16: Compl:0%->25%; 1/7/16: WID: RP-160636->RP-160921 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
214 | 710079 | Uplink Capacity Enhancements for LTE | LTE_UL_CAP_enh | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-09-15 17:00 | 10% | RP-160664 |  | Ericsson |  |  |  | TSG#71 |  |  |  | 2016-03-22 11:01 | 2016-03-22 08:00
215 | 710179 | Core part: Uplink Capacity Enhancements for LTE | LTE_UL_CAP_enh-Core | 2 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-03-15 17:00 | 25% | RP-160664 | - | Ericsson |  | 1/7/16: Compl:0%->25% |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
216 | 710279 | Perf. part: Uplink Capacity Enhancements for LTE | LTE_UL_CAP_enh-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-09-15 17:00 | 0% | RP-160664 | - | Ericsson |  |  |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-03-22 08:00
217 | 710080 | L2 latency reduction techniques for LTE | LTE_LATRED_L2 | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2016-09-15 17:00 | 80% | RP-160667 |  | Ericsson |  | no Perf. part; follow-up WI of SI FS_LTE_LATRED |  | TSG#71 |  |  |  | 2016-03-22 11:01 | 2016-03-22 08:00
218 | 710180 | Core part: L2 latency reduction techniques for LTE | LTE_LATRED_L2-Core | 2 | Rel-14 | R2 | 2016-03-15 08:00 | 2016-09-15 17:00 | 80% | RP-160667 | - | Ericsson |  | no Perf. part; follow-up WI of SI FS_LTE_LATRED; 1/7/16: Compl:0%->80% |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
219 | 710081 | eMBMS enhancements for LTE | MBMS_LTE_enh2 | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-09-15 17:00 | 4% | RP-160675 |  | Ericsson |  |  |  | TSG#71 |  |  |  | 2016-03-22 11:01 | 2016-03-22 08:00
220 | 710181 | Core part: eMBMS enhancements for LTE | MBMS_LTE_enh2-Core | 2 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-03-15 17:00 | 10% | RP-161297 | - | Ericsson |  | 1/7/16: Compl:0%->10%1/7/16: CD:Tue 15/03/16->Wed 15/03/171/7/16: WID: RP-160675->RP-161297 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
221 | 710281 | Perf. part: eMBMS enhancements for LTE | MBMS_LTE_enh2-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-09-15 17:00 | 0% | RP-161297 | - | Ericsson |  | ; 1/7/16: CD:Wed 15/06/16->Fri 15/09/17; 1/7/16: WID: RP-160675->RP-161297 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
222 | 710082 | SRS (sounding reference signal) switching between LTE component carriers | LTE_SRS_switch | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-03-15 17:00 | 15% | RP-160676 |  | Huawei |  |  |  | TSG#71 |  |  |  | 2016-03-22 11:01 | 2016-03-22 08:00
223 | 710182 | Core part: SRS (sounding reference signal) switching between LTE component carriers | LTE_SRS_switch-Core | 2 | Rel-14 | R1 | 2016-03-15 08:00 | 2016-12-15 17:00 | 35% | RP-160935 | - | Huawei |  | 1/7/16: Compl:0%->35%1/7/16: WID: RP-160676->RP-160935 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
224 | 710282 | Perf. part: SRS (sounding reference signal) switching between LTE component carriers | LTE_SRS_switch-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-03-15 17:00 | 0% | RP-160935 | - | Huawei |  | 1/7/16: WID: RP-160676->RP-160935 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
225 | 710084 | Downlink Multiuser Superposition Transmission for LTE | LTE_MUST | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-09-15 17:00 | 13% | RP-160680 |  | MediaTek |  |  |  | TSG#71 |  |  |  | 2016-03-22 11:01 | 2016-03-22 08:00
226 | 710184 | Core part: Downlink Multiuser Superposition Transmission for LTE | LTE_MUST-Core | 2 | Rel-14 | R1 | 2016-03-15 08:00 | 2016-12-15 17:00 | 40% | RP-161019 | - | MediaTek |  | ; 1/7/16: Compl:0%->40%; 1/7/16: WID: RP-160680->RP-161019 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
227 | 710284 | Perf. part: Downlink Multiuser Superposition Transmission for LTE | LTE_MUST-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-09-15 17:00 | 0% | RP-161019 | - | MediaTek |  | 1/7/16: WID: RP-160680->RP-161019 |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
228 | 720040 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 1 | Rel-14 | C1 | 2016-06-14 08:00 | 2017-03-15 17:00 | 0% | CP-160294 |  |  |  | 11/6/16: 0%->15 |  | TSG#72 |  |  |  | 2016-06-11 06:31 | 2016-06-11 08:00
229 | 720070 | CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 2 | Rel-13 | C1 | 2016-06-14 08:00 | 2017-03-15 17:00 | 0% | CP-160294 |  | Alcatel-Lucent | Keith Drage | Mar.15: 0->10%; June2015: Compl:10%->30; 07/09/15: 30%->70; 7/12/15: 70%->100 |  | CT-72 |  |  |  | 2014-12-04 09:56 | 2015-12-07 08:00
230 | 720071 | (IETF) CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 2 | Rel-13 | C1-IETF | 2016-06-14 08:00 | 2017-03-15 17:00 | 0% | CP-160294 |  | Alcatel-Lucent | Keith Drage |  | draft-ietf-mmusic-dtls-sdp, draft-ietf-mmusic-4572-update | CT-72 |  |  |  | 2014-12-04 09:56 | 2015-12-07 08:00
231 | 720072 | CT3 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 2 | Rel-13 | C3 | 2016-06-14 08:00 | 2017-03-15 17:00 | 0% | CP-160294 |  | Alcatel-Lucent | Keith Drage | 2/4/15: added, following CT3 chair's info that the WID also has a CT3 part; June2015: Compl:0%->20; 07/09/15: 20%->40; 7/12/15: 40%->100 |  | CT-72 |  |  |  | 2015-04-02 14:12 | 2015-12-07 08:00
232 | 720094 | Multi-Carrier Enhancements for UMTS | UTRA_MCe | 1 | Rel-14 | R2 | 2015-12-15 08:00 | 2016-12-15 17:00 | 50% | RP-161259 |  | Huawei, HiSilicon |  | no Perf. part; follow-up WI of REL-14 SI FS_UTRA_MCe |  | TSG#72 |  |  |  | 2016-07-08 16:07 | 2016-06-22 08:00
233 | 700059 | Study on Multi-Carrier Enhancements for UMTS | FS_UTRA_MCe | 2 | Rel-14 | R1 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-152290 |  | Huawei |  | 22/3/16: Compl:0%->20%; 1/7/16: Compl:20%->100%; 28/7/16: 25.707 added; | 25.707 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-28 08:00
234 | 720194 | Core part: Multi-Carrier Enhancements for UMTS | UTRA_MCe | 2 | Rel-14 | R2 | 2016-06-15 08:00 | 2016-12-15 17:00 | 0% | RP-161259 |  | Huawei, HiSilicon |  | no Perf. part; follow-up WI of REL-14 SI FS_UTRA_MCe |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
235 | 720095 | Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States | LTE_TDD_3550_CBRS_US | 1 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 0% | RP-161219 |  | Nokia |  |  |  | TSG#72 |  |  |  | 2016-07-08 16:09 | 2016-06-22 08:00
236 | 720195 | Core part: Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States | LTE_TDD_3550_CBRS_US-Core | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 0% | RP-161219 |  | Nokia |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
237 | 720295 | Perf. part: Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States | LTE_TDD_3550_CBRS_US-Perf | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 0% | RP-161219 |  | Nokia |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
238 | 720096 | LTE Band 41 UE power class 2 operation | LTE_B41_UE_PC2 | 1 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 0% | RP-161221 |  | Sprint |  | follow-up WI of SI FS_LTE_B41_HPUE |  | TSG#72 |  |  |  | 2016-07-08 16:09 | 2016-06-22 08:00
239 | 720196 | Core part: LTE Band 41 UE power class 2 operation | LTE_B41_UE_PC2-Core | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 0% | RP-161221 |  | Sprint |  | follow-up WI of SI FS_LTE_B41_HPUE |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
240 | 720296 | Perf. part: LTE Band 41 UE power class 2 operation | LTE_B41_UE_PC2-Perf | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 0% | RP-161221 |  | Sprint |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
241 | 721002 | Dedicated Core Networks for GERAN | DECOR_GERAN | 1 | Rel-14 | R6 | 2016-06-15 08:00 | 2016-12-15 17:00 | 0% | RP-161029 |  | Ericsson |  | no Perf. part; DECOR was a REL-13 SA2 feature |  | TSG#72 |  |  |  | 2016-07-08 16:17 | 2016-06-22 08:00
242 | 721102 | Core part: Dedicated Core Networks for GERAN | DECOR_GERAN-Core | 2 | Rel-14 | R6 | 2016-06-15 08:00 | 2016-12-15 17:00 | 0% | RP-161029 |  | Ericsson |  | no Perf. part; DECOR was a REL-13 SA2 feature |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
243 | 721003 | Positioning Enhancements for GERAN | ePOS_GERAN | 1 | Rel-14 | R6 | 2016-06-15 08:00 | 2017-03-15 17:00 | 0% | RP-161260 |  | Ericsson |  |  |  | TSG#72 |  |  |  | 2016-07-08 16:18 | 2016-06-22 08:00
244 | 721103 | Core part: Positioning Enhancements for GERAN | ePOS_GERAN-Core | 2 | Rel-14 | R6 | 2016-06-15 08:00 | 2017-03-15 17:00 | 0% | RP-161260 |  | Ericsson |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
245 | 721203 | Perf. part: Positioning Enhancements for GERAN | ePOS_GERAN-Perf | 2 | Rel-14 | R6 | 2016-06-15 08:00 | 2017-03-15 17:00 | 0% | RP-161260 |  | Ericsson |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
246 | 680099 | (Small) Technical Enhancements and Improvements for Rel-14 | TEI14 | 1 | Rel-14 | SP,CP,RP,R4 | 2015-05-11 08:00 | 2015-06-18 17:00 | 100% | [6 empty] | SP-68 |  |  |  | 2015-06-15 20:45 | 2015-06-15 08:00
247 | 709998 | Rel-14 LTE Carrier Aggregation | LTE_CA_Rel14 | 1 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | - | - | - | - | Acronym changed from "LTE_CA_Rel-13" to "LTE_CA_Rel13" |  | RP-58 | PCG-30 |  |  | 2012-12-14 14:55 | 2015-01-15 08:00
248 | 690086 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12 | LTE_CA_B4_B5_B12_B12 | 2 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151521 | - | US Cellular |  |  |  | RP-69 |  |  |  | 2015-09-29 11:16 | NA
249 | 690186 | Core part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12 | LTE_CA_B4_B5_B12_B12-Core | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151521 | - | US Cellular |  |  |  | RP-69 |  |  |  | 2015-09-29 10:40 | 2016-01-01 08:00
250 | 690286 | Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12 | LTE_CA_B4_B5_B12_B12-Perf | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151521 | - | US Cellular |  |  |  | RP-69 |  |  |  | 2015-09-29 10:40 | 2016-01-01 08:00
251 | 690087 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12 | LTE_CA_B4_B4_B12_B12 | 2 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151522 | - | US Cellular |  |  |  | RP-69 |  |  |  | 2015-09-29 11:16 | NA
252 | 690187 | Core part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12 | LTE_CA_B4_B4_B12_B12-Core | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151522 | - | US Cellular |  |  |  | RP-69 |  |  |  | 2015-09-29 10:40 | 2016-01-01 08:00
253 | 690287 | Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12 | LTE_CA_B4_B4_B12_B12-Perf | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151522 | - | US Cellular |  |  |  | RP-69 |  |  |  | 2015-09-29 10:40 | 2016-01-01 08:00
254 | 690088 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12 | LTE_CA_B2_B4_B12_B12 | 2 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151523 | - | US Cellular |  |  |  | RP-69 |  |  |  | 2015-09-29 11:16 | NA
255 | 690188 | Core part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12 | LTE_CA_B2_B4_B12_B12-Core | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151523 | - | US Cellular |  |  |  | RP-69 |  |  |  | 2015-09-29 10:40 | 2016-01-01 08:00
256 | 690288 | Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12 | LTE_CA_B2_B4_B12_B12-Perf | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151523 | - | US Cellular |  |  |  | RP-69 |  |  |  | 2015-09-29 10:40 | 2016-01-01 08:00
257 | 709999 | Rel-14 LTE Advanced inter-band Carrier Aggregation | LTE_AIBCA_Rel14 | 1 | Rel-14 | R4 | 2015-12-15 08:00 | 2018-03-15 17:00 | 24% | - | - | - | - | Acronym changed from "LTE_CA_Rel-13" to "LTE_CA_Rel13" |  | RP-58 | PCG-30 |  |  | 2012-12-14 14:55 | 2015-01-15 08:00
258 | 700069 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 5DL/1UL | LTE_CA_R14_5DL1UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 20% | RP-151671 |  | Nokia Networks |  |  |  | RP-70 |  |  |  | 2016-01-07 10:56 | 2015-12-22 08:00
259 | 700169 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 5DL/1UL | LTE_CA_R14_5DL1UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 40% | RP-161052 |  | Nokia Networks |  | 28/1/16: 36.714-05-01 added;; 22/3/16: Compl:0%->15%; 22/3/16: WID: RP-151671->RP-1606151/7/16: Compl:15%->40%... | 36.714-05-01 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
260 | 700269 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 5DL/1UL | LTE_CA_R14_5DL1UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 0% | RP-161052 |  | Nokia Networks |  | 22/3/16: WID: RP-151671->RP-1606151/7/16: WID: RP-160615->RP-161052 |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
261 | 700070 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL | LTE_CA_R14_2DL1UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 30% | RP-152196 |  | Qualcomm |  |  |  | RP-70 |  |  |  | 2016-01-07 10:56 | 2015-12-22 08:00
262 | 700170 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL | LTE_CA_R14_2DL1UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 30% | RP-161202 |  | Qualcomm |  | 28/1/16: 36.714-02-01 added;; 22/3/16: Compl:0%->20%; 22/3/16: WID: RP-152196->RP-160616; 1/7/16: Compl:20%->30%; 1/7/16: WI... | 36.714-02-01 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
263 | 700270 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL | LTE_CA_R14_2DL1UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 30% | RP-161202 |  | Qualcomm |  | 22/3/16: WID: RP-152196->RP-1606161/7/16: Compl:0%->30%1/7/16: WID: RP-160616->RP-161202 |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
264 | 700071 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL | LTE_CA_R14_2DL2UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 20% | RP-152237 |  | Huawei |  |  |  | RP-70 |  |  |  | 2016-01-07 10:56 | 2015-12-22 08:00
265 | 700171 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL | LTE_CA_R14_2DL2UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 40% | RP-160947 |  | Huawei |  | 28/1/16: 36.714-02-02 added;22/3/16: Compl:0%->20%22/3/16: WID: RP-152237->RP-160192; 1/7/16: Compl:20%->40%... | 36.714-02-02 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
266 | 700271 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL | LTE_CA_R14_2DL2UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 0% | RP-160947 |  | Huawei |  | ; 22/3/16: WID: RP-152237->RP-1601921/7/16: WID: RP-160192->RP-160947 |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
267 | 700072 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL | LTE_CA_R14_3DL3UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 15% | RP-152241 |  | Nokia Networks |  |  |  | RP-70 |  |  |  | 2016-01-07 10:56 | 2015-12-22 08:00
268 | 700172 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL | LTE_CA_R14_3DL3UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 15% | RP-152241 |  | Nokia Networks |  | 28/1/16: 36.714-03-03 added;22/3/16: Compl:0%->1%1/7/16: Compl:1%->15% | 36.714-03-03 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
269 | 700272 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL | LTE_CA_R14_3DL3UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 15% | RP-152241 |  | Nokia Networks |  | ; 1/7/16: Compl:0%->15% |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
270 | 700073 | LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5 | LTE_CA_R14_xDL2UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 20% | RP-152246 |  | LG Electronics |  |  |  | RP-70 |  |  |  | 2016-01-07 10:56 | 2015-12-22 08:00
271 | 700173 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5 | LTE_CA_R14_xDL2UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 40% | RP-160748 |  | LG Electronics |  | 28/1/16: 36.714-00-02 added;; 22/3/16: Compl:0%->10%; 22/3/16: WID: RP-152246->RP-160148; 1/7/16: Compl:10%->40%; ... | 36.714-00-02 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
272 | 700273 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5 | LTE_CA_R14_xDL2UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 0% | RP-160748 |  | LG Electronics |  | 22/3/16: WID: RP-152246->RP-1601481/7/16: WID: RP-160148->RP-160748 |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
273 | 700074 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL | LTE_CA_R14_4DL1UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 38% | RP-152249 |  | Ericsson |  |  |  | RP-70 |  |  |  | 2016-01-07 10:57 | 2015-12-22 08:00
274 | 700174 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL | LTE_CA_R14_4DL1UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 38% | RP-160821 |  | Ericsson |  | 28/1/16: 36.714-04-01 added;22/3/16: Compl:0%->30%22/3/16: WID: RP-152249->RP-1606141/7/16: Compl:30%->38%; ... | 36.714-04-01 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
275 | 700274 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL | LTE_CA_R14_4DL1UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 38% | RP-160821 |  | Ericsson |  | ; 22/3/16: WID: RP-152249->RP-160614; 1/7/16: Compl:0%->38%; 1/7/16: WID: RP-160614->RP-160821 |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
276 | 700075 | LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R14_intra | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 50% | RP-152250 |  | Ericsson |  |  |  | RP-70 |  |  |  | 2016-01-07 10:57 | 2015-12-22 08:00
277 | 700175 | Core part: LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R14_intra-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 50% | RP-160822 |  | Ericsson |  | 28/1/16: 36.714-00-00 added;22/3/16: Compl:0%->60%22/3/16: WID: RP-152250->RP-160613; 1/7/16: Compl:60%->50%; 1/7/16: WID: RP-160613... | 36.714-00-00 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
278 | 700275 | Perf. part: LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R14_intra-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 50% | RP-160822 |  | Ericsson |  | ; 22/3/16: WID: RP-152250->RP-1606131/7/16: Compl:0%->50%1/7/16: WID: RP-160613->RP-160822 |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
279 | 700076 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL | LTE_CA_R14_3DL1UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 20% | RP-152278 |  | Huawei |  |  |  | RP-70 |  |  |  | 2016-01-07 10:57 | 2015-12-22 08:00
280 | 700176 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL | LTE_CA_R14_3DL1UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 40% | RP-160945 |  | Huawei |  | 28/1/16: 36.714-03-01 added;22/3/16: Compl:0%->15%22/3/16: WID: RP-152278->RP-1605821/7/16: Compl:15%->40%1/7/16... | 36.714-03-01 | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
281 | 700276 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL | LTE_CA_R14_3DL1UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 0% | RP-160945 |  | Huawei |  | 22/3/16: WID: RP-152278->RP-160582; 1/7/16: WID: RP-160582->RP-160945 |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00
282 | 720098 | UE Conformance Test Aspects – Rel-14 CA configurations | LTE_CA_R14-UEConTest | 2 | Rel-14 | R5 | 2016-06-15 08:00 | 2018-03-15 17:00 | 0% | RP-160754 |  | Ericsson |  | testing REL-14 CA basket WIs: LTE_CA_R14_intra-Core, LTE_CA_R14_2DL1UL-Core, LTE_CA_R14_3DL1UL-Core, LTE_CA_R14_4DL1UL-Core, LTE_CA_R14_5DL1UL-Core, LTE_CA_R14_2DL2UL-Core, LTE_CA_R14_xDL2UL-Core, LTE_CA_R14_3DL3UL-Core |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
283 | 0 | Release 14 Studies | - | 1 | Rel-14 | SP,RP,CP,GP | 2014-09-17 08:00 | 2015-12-11 17:00 | 10% | - | - |  | - | - | - |  |  |  |  | 2014-08-29 11:19 | 2014-08-29 08:00
284 | 700019 | Study on LTE support for V2X services | FS_V2XLTE | 1 | Rel-14 | S1 | 2015-02-09 08:00 | 2016-09-16 17:00 | 61% | SP-150051 |  | Ki-Dong Lee (LG electronics) | kidong.lee@lge.com | 1/4/15:TR number added; June2015: Compl:25%->50; 07/09/15: 50%->75 | New TR 22.885 | SP-67 | PCG-34 |  |  | 2015-03-04 10:20 | 2015-09-07 08:00
285 | 670009 | Study on Stage 1 of LTE support for V2X services | FS_V2XLTE | 2 | Rel-14 | S1 | 2015-02-09 08:00 | 2015-02-09 17:00 | 100% | SP-150051 |  | Ki-Dong Lee (LG electronics) | kidong.lee@lge.com | 1/4/15:TR number added; June2015: Compl:25%->50; 07/09/15: 50%->75; 7/12/15: 75%->100 | New TR 22.885 | SP-67 | PCG-34 |  |  | 2015-12-07 11:05 | 2015-12-07 08:00
286 | 700050 | Study on Stage 2 of LTE support for V2X services | FS_V2XARC | 2 | Rel-14 | S2 | 2015-09-07 08:00 | 2016-06-17 17:00 | 80% | SP-150852 |  | LG Electronics, LaeYoung Kim | laeyoung.kim@lge.com | 11/12/15: WID:SP-150625->SP-150743; 7/3/16: 10%->22; 7/3/16: WID:SP-150743->SP-150852; 9/6/16: 22%->80 | TR 23.785 | SP-70 |  |  |  | 2015-12-07 11:06 | 2016-06-09 08:00
287 | 700045 | Study on security aspects for LTE support of V2X services | FS_V2XLTE | 2 | Rel-14 | S3 | 2015-09-07 08:00 | 2016-09-16 17:00 | 10% | SP-150852 |  | Huawei, Marcus Wong | mwong@huawei.com | 11/12/15: WID:SP-150715->SP-150743. 28/01/16: typo on name corrected, WD corrected (was SP-150743); 7/3/16: 0%->10 | TR 33.885 | SP-70 |  |  |  | 2015-12-07 14:33 | 2016-03-07 08:00
288 | 680058 | RAN1 Study on LTE-based V2X Services | FS_LTE_V2X | 2 | Rel-14 | R1 | 2015-06-15 08:00 | 2016-06-15 17:00 | 100% | RP-161263 | RP-151311 | LG Electronics |  | 29/09/15: Compl:0%->5% 29/09/15: Stat Rep: -->RP-151311 ; 28/1/16: 33.885 added;22/3/16: Compl:35%->50%22/3/16: CD:Wed 15/06/16->Thu 15/09/1622/3/16: WID: RP-15...; ;... | 33.885 |  |  |  |  | 2015-07-03 16:00 | 2016-07-01 08:00
289 | 720081 | Study on extended architecture support for Cellular Internet of Things | FS_CIoT_Ext | 1 | Rel-14 | S2 | 2016-06-17 08:00 | 2017-03-15 17:00 | 0% | SP-160505 |  | Intel : Puneet Jain | puneet.jain@intel.com | 28/7/16: 23.730 added; | 23.730 | SP-72 |  |  |  | 2016-06-17 07:14 | 2016-07-28 08:00
290 | 720086 | Study on NB-IoT RF requirement for coexistence with CDMA | FS_NB_IOT_CDMA_coex | 1 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 0% | RP-161187 |  | China Telecom |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
291 | 670010 | Study on 3GPP Enhancement for TV Video service | FS_EnTV | 1 | Rel-14 | S1 | 2015-04-14 08:00 | 2015-12-15 17:00 | 100% | SP-150052 |  | Zhiming Li (Huawei) | lizhiming@huawei.com | 1/4/15:TR number added; June2015: Compl:0%->20; 07/09/15: 20%->75; 7/12/15: 75%->100 | TR 22.816 | SP-67 | PCG-34 |  |  | 2015-03-04 10:20 | 2015-12-07 08:00
292 | 610032 | Study on need for Multiple Access Point Names | FS_MAPN | 1 | Rel-14 | S1 | 2013-09-12 08:00 | 2015-06-19 17:00 | 100% | SP-130416 | S1-143308 | Giesecke & Devrient | Ilario.macchi@gi-de.com | SP#65 moved to Rel-14. Completion 12/14=>03/15. Triggered by S1-133134 LS on GSMA Connected Living Programme Request for APN Storage in the SIM. Dec.14: 50->70%, CD: 03/15->06/15. Mar.15: 90%; June2015: Compl:90%->100 | 22.802 | SP-61 | PCG-31 |  |  | 2013-08-26 14:56 | 2015-06-15 08:00
293 | 620071 | Study on Multimedia Broadcast Supplement for Public Warning System | FS_MBSP | 1 | Rel-14 | S1 | 2013-12-11 08:00 | 2014-12-12 17:00 | 100% | SP-130599 | S1-143312 | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Moved to Rel-14. TR 22.815v100 for Information. Linked to Rel-9 Feature PWS. Dec.14:70->100% | 22.815 | SP-62 | PCG-32 |  |  | 2013-11-26 10:56 | 2014-12-03 08:00
294 | 630018 | Study on service aspects for dealing with User Control over spoofed calls | FS_UC_SPOOF | 1 | Rel-14 | S1 | 2014-03-07 08:00 | 2015-03-20 17:00 | 100% | SP-140074 | S1-143314 | Sprint | Gregory.schumacher@sprint.com | SP#65 moved to Rel-14. Linked to SA3 Rel-11 TR 33.838 PUCI and Rel-12 ongoing study TR 33.831 (FS_SPOOF). Dec.14: 70->90, CD: 12/14->03/15. Mar.15: 100% | 22.898 | SP-63 | PCG-32 |  |  | 2014-02-05 11:53 | 2015-03-04 08:00
295 | 640060 | Study on User Location Reporting Support enhancements | FS_eULRS | 1 | Rel-14 | S1 | 2014-06-19 08:00 | 2015-06-17 17:00 | 100% | SP-140402 | S1-143315 | China Unicom | Zhuoyun Zhang ( zhangzy910@chinaunicom.cn) | SP#65 moved to Rel-14. Linked to Rel-12 SA2 TR 23.843 Study on Core Network Overload solutions (FS_CNO) and Rel-13 Feature Service Exposure and Enablement Support (SEES). Dec.14: 30->70%. Mar.15: 90%; June2015: Compl:90%->100 | 22.899 | SP-64 | PCG-33 |  |  | 2014-05-29 12:16 | 2015-06-15 08:00
296 | 640061 | Study on Control of Applications when Third party Servers encounter difficulties | FS_CATS | 1 | Rel-14 | S1 | 2014-06-19 08:00 | 2015-06-15 17:00 | 100% | SP-140758 | S1-143316 | KDDI | Eriko Yoshida (er-yoshida@kddi.com) | SP#65 completion 12/14=>03/15. Moved to Rel-14. Linked to Rel-13 Feature SEES and Rel-13 TR 22.806 (FS_ACDC). Dec.14: 30->60%, WID SP-140246->SP-140758, CD: 12/14->03/15. Mar.15: CD: 03/13->06/15. 60->90%; June2015: Compl:90%->100 | 22.818 | SP-64 | PCG-33 |  |  | 2014-05-29 12:16 | 2015-06-15 08:00
297 | 670011 | Study on Paging Policy Enhancements and Procedure Optimizations in LTE | FS_PPEPO_LTE | 1 | Rel-14 | S1 | 2015-04-14 08:00 | 2015-12-15 17:00 | 100% | SP-150053 |  | Zhuoyun Zhang (China Unicom) | zhangzy910@chinaunicom.cn | 1/4/15:TR number added; June2015: Compl:0%->40; 07/09/15: 40%->60; 7/12/15: 60%->100 | New TR 22.838 | SP-67 | PCG-34 |  |  | 2015-03-04 10:20 | 2015-12-07 08:00
298 | 680054 | Study on Overload Control for Diameter Charging Applications | FS_DOCME_CH | 1 | Rel-14 | S5 | 2015-06-18 08:00 | 2016-09-16 17:00 | 10% | SP-150310 |  | GUO Wenjie, ZTE | guo.wenjie1@zte.com.cn | Aug2015: moved to Rel-14 (email CT and EG); 07/09/15: 0%->5; 7/3/16: 5%->10; 13/6/16: FCD:03/16->09/16 | New TR 32.869 | SP-68 |  |  |  | 2015-06-26 12:57 | 2016-06-13 08:00
299 | 670041 | Study on Latency reduction techniques for LTE | FS_LTE_LATRED | 1 | Rel-14 | R2 | 2015-03-16 08:00 | 2016-06-15 17:00 | 100% | RP-150465 | RP-151286 | Ericsson |  | 03/07/15: Compl:0%->10% 03/07/15: Stat Rep: -->RP-150780 03/07/15: Release: Rel-13->Rel-14 29/09/15: Compl:10%->25% 29/09/15: Stat Rep: RP-150780->RP-151286 22/3/16: Compl:50%->60%;... | 36.881 | RP-67 | PCG-34 |  |  | 2015-04-01 15:50 | 2016-07-01 08:00
300 | 680057 | Study on High Power LTE UE for Band 41 | FS_LTE_B41_HPUE | 1 | Rel-14 | R4 | 2015-06-15 08:00 | 2016-06-15 17:00 | 100% | RP-160092 | RP-151436 | Sprint |  | 7/9/15: TR added 29/09/15: Compl:0%->1% 29/09/15: Stat Rep: -->RP-151436 ; 22/3/16: Compl:10%->40%; 22/3/16: WID: RP-151104->RP-1600921/7/16: Compl... | 36.886 |  |  |  |  | 2015-07-03 16:00 | 2016-07-01 08:00
301 | 690060 | Study on channel model for frequency spectrum above 6 GHz | FS_6GHz_CH_model | 1 | Rel-14 | R1 | 2015-09-15 08:00 | 2016-06-15 17:00 | 100% | RP-160210 | - | Samsung |  | will start only in RAN in Q4/15; 28/1/16: 38.900 added;; 22/3/16: Compl:10%->20%; 22/3/16: WID: RP-151606->RP-160210; 1/7/16: Compl:20%->100% | 38.900 | RP-69 |  |  |  | 2015-09-29 10:40 | 2016-07-01 08:00
302 | 680049 | Study on Media and Quality Aspects of SRVCC Enhancements | FS_SETA_S4 | 1 | Rel-14 | S4 | 2015-06-18 08:00 | 2016-03-11 17:00 | 100% | SP-150361 |  | Frédéric Gabin, Ericsson LM | frederic . gabin @ ericsson . com | Aug2015: 0%->25; 07/09/15: 25%->30; 7/12/15: 30%->80, FCD: 12/15->03/16, MOVED TO REL-14; 7/3/16: 80%->100 | New TR 26.9xx, TS 26.114 | CP-68 |  |  |  | 2015-06-18 11:17 | 2016-03-07 08:00
303 | 700047 | Study on OAM support for assessment of energy efficiency in mobile access networks | FS_OAM_EE | 1 | Rel-14 | S5 | 2015-11-02 08:00 | 2017-03-15 17:00 | 55% | SP-160430 |  | Cornily,Jean-Michel, ORANGE | jeanmichel.cornily@orange.com | 13/6/16: WID:SP-150674->SP-160430; 13/6/16: 0%->55 | TR 32.856 | SP-70 |  |  |  | 2015-12-07 14:44 | 2016-06-13 08:00
304 | 700048 | Study on OAM aspects of SON for AAS-based deployments | FS_OAM_SON_AAS | 1 | Rel-14 | S5 | 2015-11-02 08:00 | 2016-09-16 17:00 | 40% | SP-150677 |  | Nokia Networks (Yizhi Yao) | Yizhi.yao@nokia.com | 13/6/16: 0%->40 | TR (new) | SP-70 |  |  |  | 2015-12-07 14:46 | 2016-06-13 08:00
305 | 720085 | Study on SON for eCoMP for LTE | FS_LTE_SON_eCOMP | 1 | Rel-14 | R3 | 2016-06-15 08:00 | 2017-03-15 17:00 | 0% | RP-161181 |  | Nokia |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
306 | 700036 | Study on UICC power optimization for MTC | FS_UICC_MTC_OPT | 1 | Rel-14 | C6 | 2016-06-15 08:00 | 2016-12-15 17:00 | 71% | CP-150875 |  | Berionne, Michele | micheleb [at] qti [dot] qualcomm [dot] com | 7/3/16: 0%->100 | 31.970 | CP-70 |  |  |  | 2015-12-07 13:56 | 2016-03-07 08:00
307 | 710007 | Study on Implementation for the Partitioning of Itf-N | FS_IMP_ITFN | 1 | Rel-14 | S5 | 2016-03-01 08:00 | 2017-03-01 17:00 | 10% | SP-160020 |  | Hu, Yaxi, China Mobile | huyaxi@cmdi.chinamobile.com | 13/6/16: 0%->10 | New TR 32.880 | TSG#71 |  |  |  | 2016-03-01 13:40 | 2016-06-13 08:00
308 | 710013 | Study on Server and Network Assisted DASH for 3GPP | FS_SAND | 1 | Rel-14 | S4 | 2016-03-01 08:00 | 2016-12-15 17:00 | 10% | SP-160083 |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 11/6/16: 0%->10 | TR26.957 | TSG#71 |  |  |  | 2016-03-01 14:57 | 2016-06-11 08:00
309 | 710014 | Study on Virtual Reality | FS_VR | 1 | Rel-14 | S4 | 2016-03-01 08:00 | 2016-12-15 17:00 | 10% | SP-160084 |  | Gilles TENIOU, Orange | gilles.teniou@orange.com | 11/6/16: 0%->10 | TR 26.918 | TSG#71 |  |  |  | 2016-03-01 15:00 | 2016-06-11 08:00
310 | 710015 | Study on UE characteristics and performance for Video | FS_UE_VTPerf | 1 | Rel-14 | S4 | 2016-03-01 08:00 | 2016-12-15 17:00 | 10% | SP-160085 |  | Stéphane PROUST, Orange | stephane.proust@orange.com | 11/6/16: 0%->10 | TR 26.932 | TSG#71 |  |  |  | 2016-03-01 15:01 | 2016-06-11 08:00
311 | 710016 | Study on MBMS usage for mission critical communication services | FS_MBMS_MCservices | 1 | Rel-14 | S6 | 2016-03-01 08:00 | 2016-09-15 17:00 | 35% | SP-160201 |  | Magnus Tränk, Ericsson LM | magnus.trank@ericsson.com | 11/6/16: 0%->35. Name corrected | TR 23.780 | TSG#71 |  |  |  | 2016-03-01 15:07 | 2016-06-11 08:00
312 | 710032 | Study on Enhanced Isolated E-UTRAN Operation for Public Safety | FS_IOPS_LB | 1 | Rel-14 | S2 | 2016-03-07 08:00 | 2016-09-07 17:00 | 6% | SP-160171 |  | Antoine Mouquet, Orange | antoine.mouquet@orange.com | 9/6/16: 0%->6; 28/7/16: 23.798 added; | 23.798 | TSG#71 |  |  |  | 2016-03-07 09:27 | 2016-07-28 08:00
313 | 720082 | Study on Complementary Features for Voice services over WLAN | FS_VoWLAN | 1 | Rel-14 | S2 | 2016-06-13 08:00 | 2017-03-15 17:00 | 0% | SP-160506 |  | Nokia (Nicolas Drevon | nicolas.drevon@nokia.com | 28/7/16: 23.751 added; | 23.751 | SP-72 |  |  |  | 2016-06-17 07:16 | 2016-07-28 08:00
314 | 710049 | Study on Energy Efficiency Aspects of 3GPP Standards | FS_ENEFF | 1 | Rel-14 | SP | 2016-03-11 08:00 | 2016-12-15 17:00 | 0% | SP-160224 |  | Orange, Xiaobao Chen | xiaobao.chen@orange.com | 28/7/16: 21.866 added; | TR 21.866 | TSG#71 |  |  |  | 2016-03-11 11:13 | 2016-07-28 08:00
315 | 710056 | Study on flexible eNB-ID and Cell-ID in E-UTRAN | FS_LTE_FNBID | 1 | Rel-14 | R3 | 2016-03-15 08:00 | 2016-09-15 17:00 | 60% | RP-160534 | - | China Telecom |  | 1/7/16: Compl:0%->60% | New TR 36.896 | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
316 | 710057 | Study on enhancement of VoLTE | FS_LTE_eVoLTE | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2016-09-15 17:00 | 75% | RP-160902 | - | CMCC |  | 1/7/16: Compl:0%->75%1/7/16: WI...; 28/7/16: 36.750 added; | 36.750 | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-28 08:00
317 | 710058 | Study on HSPA and LTE Joint Operation | FS_UTRA_LTE_JOP | 1 | Rel-14 | R3 | 2016-03-15 08:00 | 2016-09-15 17:00 | 30% | RP-160571 | - | China Unicom |  | ; 1/7/16: Compl:0%->30% | New 37.805 | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
318 | 710059 | Study on LTE Advanced Carrier Aggregation of Band 3 and Band 39 | FS_LTE_CA_B3_B39 | 1 | Rel-14 | R4 | 2016-03-15 08:00 | 2016-12-15 17:00 | 30% | RP-160632 | - | ZTE |  | intention to capture results in existing TR 36.714-02-01 ; 1/7/16: Compl:0%->30%; ... |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
319 | 710060 | Study on Context Aware Service Delivery in RAN for LTE | FS_LTE_context | 1 | Rel-14 | R3 | 2016-03-15 08:00 | 2016-12-15 17:00 | 25% | RP-160906 | - | CMCC |  | 1/7/16: Compl:0%->25%1/... |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
320 | 710061 | Study on further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE | FS_feCOMP_LTE | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-03-15 17:00 | 15% | RP-160954 | - | Intel |  | ; 1/7/16: Compl:0%->15%... |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
321 | 710063 | Study on further enhancements to LTE Device to Device (D2D), UE to network relays for IoT (Internet of Things) and wearables | FS_feD2D_IoT_relay_wearable | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2017-03-15 17:00 | 2% | RP-161303 | - | Qualcomm |  | 1/7/16: Compl:0%->2%;... |  | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-01 08:00
322 | 710064 | Study on LTE bandwidth flexibility enhancements | FS_LTE_BW_flex | 1 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-06-15 17:00 | 50% | RP-161328 | - | Huawei |  | 1/7/16: Compl:0%->50%; ...; 28/7/16: 36.740 added; | 36.740 | TSG#71 |  |  |  | 2016-03-22 10:28 | 2016-07-28 08:00
323 | 670015 | Study on Determination of Completeness of Charging Information in IMS | FS_DCCHII | 1 | Rel-14 | S5 | 2015-03-05 08:00 | 2016-03-11 17:00 | 100% | SP-150106 |  | Jesske, Roland | r.jesske@telekom.de | 11/03/15: WID changed from FS_DCCII to FS_DCCHII as per SA5 chair request; June2015: Compl:0%->7; 07/09/15: 7%->15; 7/12/15: 15%->60, FCD: 09/15->03/16; 7/3/16: 60%->100. 22/3/16: Rel-13->Rel-14 | 32.xyz | SP-67 | PCG-34 |  |  | 2015-03-05 13:16 | 2016-03-22 08:00
324 | 660037 | Study on KQIs for Service Experience | FS_KQISE | 1 | Rel-14 | S5 | 2014-12-03 08:00 | 2016-03-11 17:00 | 100% | SP-150676 |  | Li, Hui (hui.li(at)huawei.com) | hui.li(at)huawei.com | Mar 15: 0->5%; June2015: Compl:0%->40; 07/09/15: 40%->50; 14/09/15: WID:SP-140784->SP-150405; 7/12/15: 50%->75; 7/12/15: WID:SP-150405->SP-150676 ; 7/3/16: 75%->100. 22/3/16: FCD: 09/15->03/16. Rel-13->Rel-14 | TR 32.8xy | SP-66 | PCG-34 |  |  | 2014-12-04 11:35 | 2016-03-22 08:00
325 | 660058 | Study on Interactivity Support for 3GPP-based Streaming and Download Services | FS_IS3 | 1 | Rel-14 | S4 | 2014-12-12 08:00 | 2016-09-23 17:00 | 50% | SP-140742 |  | Lo, Charles, Qualcomm | clo@qti.qualcomm.com | TR number added. Mar. 15: 0->5%; June2015: Compl:5%->10; Aug2015: 10%->15; 07/09/15: 15%->30, FCD: 12/15->03/16; 7/3/16: 30%->40. 15/4/16: moved from Rel-13. FCD: 11/3/16->23/9/16; 11/6/16: 40%->50 | 26.953 | SP-66 | PCG-34 |  |  | 2014-12-12 21:28 | 2016-06-11 08:00
326 | 590045 | Study on Enhanced Acoustic Test Specifications | FS_SEATS | 1 | Rel-14 | S4 | 2013-03-18 08:00 | 2016-12-14 17:00 | 70% | SP-130028 | - | Knowles, Intel | Scott Isabelle (Knowles), David Isherwood (Intel) | SP#65 completion 09/14=>12/14. Moved to Rel-13. Dec.14: 30->35%, CD 12/14->03/15. Mar.15: CD: 06/16. 40%; June2015: Compl:40%->45. FCD: 06/15->09/15. 7/9/15: FCD: 09/15->12/15; 7/12/15: 50%->60, FCD: 12/15->06/16; 7/3/16: 60%->65. 15/4/16: moved from R... | 26.931 | SP-59 | PCG-30 |  |  | 2013-02-20 16:11 | 2016-06-11 08:00
327 | 720025 | Study on User Services Enhancements in 3GPP for TV Services | FS_USE_3GPP_4_TV | 1 | Rel-14 | S4 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | SP-160273 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com |  | TR 26.9xx | TSG#72 |  |  |  | 2016-06-11 05:41 | NA
328 | 720026 | Study on MBMS usage and codecs for MCPTT call and MC Video Service | FS_MCP_V | 1 | Rel-14 | S4 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | SP-160274 |  | Zhiming Li, Huawei | lizhiming@huawei.com | 28/7/16: 26.880 added; | 26.880 | TSG#72 |  |  |  | 2016-06-11 05:43 | 2016-07-28 08:00
329 | 720027 | Study on MBMS Extensions for Provisioning and Content Ingestion | FS_xMBMS | 1 | Rel-14 | S4 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | SP-160275 |  | Kyungmo Park, Samsung Electronics Co., Ltd | kyungmo.park@samsung.com | 28/7/16: 26.981 added; | TR 26.981 | TSG#72 |  |  |  | 2016-06-11 05:43 | 2016-07-28 08:00
330 | 720041 | Study on Technical Requirements for a new secure platform for 3GPP applications | FS_NG_SP | 1 | Rel-14 | C6 | 2016-06-13 08:00 | 2016-12-15 17:00 | 0% | CP-160371 |  | Heiko Kruse | heiko.kruse@safrangroup.com |  | TR 31.xxx | TSG#72 |  |  |  | 2016-06-13 02:35 | NA
331 | 720088 | Study on global application of LTE Band 11 and of LTE Band 21 UEs | FS_LTE_B11_B21_global | 1 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 0% | RP-161220 |  | SoftBank |  |  |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
332 | 720089 | Study on Downlink MIMO for GERAN | FS_DOMIMO_RAN6 | 1 | Rel-14 | R6 | 2016-06-15 08:00 | 2016-09-15 17:00 | 0% | RP-161261 |  | Nokia, Alcatel-Lucent Shanghai Bell |  | continuation of GERAN SI UID 590034, DOMIMO under RAN6 |  | TSG#72 |  |  |  | 2016-07-01 15:41 | 2016-06-22 08:00
333 | 700018 | Release 14 studies on 5G MObile Network for Advanced communications |  | 1 | Rel-14 | S1 | 2015-02-02 08:00 | 2016-12-15 17:00 | 72% | SP-150142 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com | 11/3: WID: SP-150050->150142; June2015: Compl:0%->20; 07/09/15: 20%->60. 07/12/15: Created by MCC as BB to dissociate SA1 versus SA2 aspects | New TR 22.891 | SP-67 | PCG-34 |  |  | 2015-03-04 10:20 | 2015-09-07 08:00
334 | 700022 | Study on Stage 1 for New Services and Markets Technology Enablers | FS_SMARTER | 1 | Rel-14 | S1 | 2015-02-02 08:00 | 2016-06-10 17:00 | 91% | SP-150142 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com |  | New TR 22.891 | SP-67 | PCG-34 |  |  | 2015-03-04 10:20 | 2015-09-07 08:00
335 | 670008 | General aspects of FS_SMARTER SA1 | FS_SMARTER | 2 | Rel-14 | S1 | 2015-02-02 08:00 | 2016-02-12 17:00 | 95% | SP-150142 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com | 7/12/15: 60%->85; 2/3/16: 85%->95 | New TR 22.891 | SP-67 | PCG-34 |  |  | 2015-03-04 10:20 | 2016-03-02 08:00
336 | 700023 | FS_SMARTER – massive Internet of Things | FS_SMARTER-mIoT | 2 | Rel-14 | S1 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-150817 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com | 2/3/16: 35%->65; 9/6/16: 65%->100 | New TR 22.861 | SP-70 |  |  |  | 2015-12-07 11:37 | 2016-06-09 08:00
337 | 700024 | FS_SMARTER – Critical Communications | FS_SMARTER-CRIC | 2 | Rel-14 | S1 | 2015-11-02 08:00 | 2016-06-10 17:00 | 95% | SP-150818 |  | Kanerva, Mikko | mikko.kanerva@nokia.com | 2/3/16: 15%->60; 9/6/16: 60%->95 | New TR 22.862 | SP-70 |  |  |  | 2015-12-07 11:37 | 2016-06-09 08:00
338 | 700025 | FS_SMARTER – enhanced Mobile Broadband | FS_SMARTER-eMBB | 2 | Rel-14 | S1 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-150819 |  | Laurence Meriau | laurence.meriau@huawei.com | 2/3/16: 40%->75; 9/6/16: 75%->100 | New TR 22.863 | SP-70 |  |  |  | 2015-12-07 11:37 | 2016-06-09 08:00
339 | 700026 | FS_SMARTER – Network Operation | FS_SMARTER-NEO | 2 | Rel-14 | S1 | 2015-11-02 08:00 | 2016-06-10 17:00 | 60% | SP-150820 |  | Lu Lu | lulu@chinamobile.com | 2/3/16: 30%->60 | New TR 22.864 | SP-70 |  |  |  | 2015-12-07 11:37 | 2016-03-02 08:00
340 | 700017 | Study on Architecture and Security for next Generation System | FS_NextGen | 1 | Rel-14 | S2 | 2015-12-07 08:00 | 2016-09-09 17:00 | 35% | SP-160227 |  | suntao@chinamobile.com, devaki.chandramouli@nokia.com | suntao@chinamobile.com, devaki.chandramouli@nokia.com | 28/1/16: 23.799 added; Acronym corrected ("NexGen"->"NextGen"); 7/3/16: 5%->15; 10/3/16: WID:SP-150853->SP-160200. Name changed from "Study on Architecture for next Generation System"; 9/6/16: 15%->35 | TR 23.799 | SP-70 |  |  |  | 2015-12-07 10:54 | 2016-06-09 08:00
341 | 710045 | Study on Architecture and Security for Next Generation System | FS_NSA | 1 | Rel-14 | S3 | 2016-03-01 08:00 | 2016-12-15 17:00 | 0% | SP-160227 |  | Vesa Torvinen, Ericsson | vesa.torvinen@ericsson.com |  | TR 33.899 | SP-71 |  |  |  | 2016-03-01 14:35 | 2016-03-10 08:00
342 | 700058 | Study on Scenarios and Requirements for Next Generation Access Technologies | FS_NG_SReq | 1 | Rel-14 | RP | 2015-12-15 08:00 | 2016-06-15 17:00 | 80% | RP-160811 |  | CMCC |  | 22/3/16: Compl:0%->80%1/7/16: WID: RP-152257->RP-160811 |  | RP-70 |  |  |  | 2016-01-01 18:48 | 2016-07-01 08:00