## Slide 1: FS_FRMCS Status Update Study on Future Railway Mobile Communication System
Jürgen Merkel
Nokia
FS_FRMCS Rapporteur
3GPP TSG-SA WG1 Meeting #75
San Francisco, CA, USA, 22-26 August 2016
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_FRMCS Status
Is this a new WI? <no>
Notes: 1

## Slide 3: FS_FRMCS Progress
Progress made at this meeting
  Introduction, Scope and Overview sections agreed
  Introduced Use Cases on
    Location services
    FRMCS-user communication handling
    Initialisation and shut-down
    Assured voice communication
    Role management and presence
  Added Annex on Roles and Identities
Notes: 1

## Slide 4: FS_FRMCS Progress
Work/Study Item Completion: 25%
Draft TR 22.989 Completion: 25%
Controversial issues
  N/A
Notes: 1

## Slide 5: FS_FRMCS Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 0
Number of slots requested for next meeting
  sum of plenary and drafting slots: 6
Notes: 1

## Slide 6: FS_FRMCS Completion Date
Current expected dates to send TR to SA plenary:
  For information: SA#73 (12/2016)
  For approval: SA#74 (03/2017)
Have these dates been changed at this meeting? No
  If yes, previous target completion dates:
    For information: <09/2016> SP#73
    For approval: <12/2016> SP#74
Notes: 1

## Slide 7: FS_FRMCS Planning/Progress
  Guide: if WID is 100% complete or if SA1 agreed to stop the work, delete this slide
Topics to focus on at next SA1 meeting:
  Introduction of new use cases
  Gap analysis
Planning for subsequent meetings
  SA1#75+2
    Use Cases
    Consolidation of Requirements
Notes: 1

## Slide 8: Work plan between meetings
  Guide: if WID is 100% complete or if SA1 agreed to stop the work, delete this slide
Email discussion
  Companies providing views on gap analysis
    Format of gap analysis see attached example
  Tentative start date: Soon after the meeting
Notes: 1

## Slide 9: FS_FRMCS Progress Estimate
  Guide: if WID is 100% complete or if SA1 agreed to stop the work, delete this slide
Estimated percentage completion:
  now: 25%
  Next meeting: 60 %
  In two meetings: 100%
Notes: 1

## Slide 10: FS_FRMCS Agreed documents
  Guide: List agreed CRs. For draft TR/TS, list agreed contributions – document details can be copied from meeting Agenda
List of agreed documents at this meeting:
Tdoc number | Sourcing company | Title
Tdoc number | Sourcing company | Title
Tdoc number | Sourcing company | Title
Tdoc number | Sourcing company | Title
Notes: 1