## Slide 1: FS_CAV Status Update Study on Communication for Automation in Vertical Domains
Michael Bahr
Siemens AG
FS_CAV Rapporteur
3GPP TSG-SA WG1 Meeting #77
Jeju Island, South Korea, 13-17 February 2017
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_CAV Status
Is this a new WI? <yes>
This WI has not been approved by SP
  The following slides assume approval at SP#75
Notes: 1

## Slide 3: FS_CAV Progress
Progress made at this meeting
  Study Item description aggreed
Work/Study Item Completion: 0%
Draft <TR> 22.xxx Completion: 0%
Controversial issues
  n/a
Notes: 1

## Slide 4: FS_CAV Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 0
Number of slots requested for next meeting
  sum of plenary and drafting slots: tbd
Notes: 1

## Slide 5: FS_CAV Completion Date
Current expected dates to send TR to SA plenary:
  For information: SA#77 (09/2017)
  For approval: SA#78 (12/2017)
Have these dates been changed at this meeting? No
Notes: 1

## Slide 6: FS_CAV Planning/Progress
Topics to focus on at next SA1 meeting:
  Skeleton of TR, first new use cases and potential requirements
Planning for subsequent meetings
  SA1#79 (08/2017)
    Use cases and potential requirements
  SA1#80 (11/2017)
    Use cases and potential requirements
    Consolidation of Use Cases and potential requirements
    Finalization of TR
  <Until close of WI as defined in WID>
Notes: 1

## Slide 7: Work plan between meetings
  Guide: if WID is 100% complete or if SA1 agreed to stop the work, delete this slide
Email discussion
  Focus items in previous slide
  <other topics/items to be covered>
  <e.g. introduction of new topics>
  <e.g. review of incoming LS>
  <e.g. planning next meeting>
  Tentative start date: <dd/mm/yyyy>
Notes: 1

## Slide 8: FS_CAV Progress Estimate
  Guide: if WID is 100% complete or if SA1 agreed to stop the work, delete this slide
Estimated percentage completion:
  now: 0
  Next meeting: 30%
  In two meetings: 60%
  <Until expected Completion Date>
Notes: 1

## Slide 9: FS_CAV Agreed documents
  Guide: List agreed CRs. For draft TR/TS, list agreed contributions – document details can be copied from meeting Agenda
List of agreed documents at this meeting:
Tdoc number | Sourcing company | Title
Tdoc number | Sourcing company | Title
Tdoc number | Sourcing company | Title
Tdoc number | Sourcing company | Title
Notes: 1