## Slide 1: 5G_HYPOS Status Update Study on positioning use cases
Lionel Ries
ESA
FS_5G_HYPOS Rapporteur
3GPP TSG-SA WG1 Meeting #79
Guilin, China, 21-25 August 2017
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_5G_HYPOS Status
Is this a new WI? n
This WI has been approved at SP#76
  Approved SID : SP-170589
Notes: 1

## Slide 3: FS_5G_HYPOS Progress
Progress made at this meeting
  Skeleton of TR 22.872 “Study on positioning use cases”
  Scope, Overview, Use cases’ KPI and attributes
  Use cases (2):
    Accurate positioning for bike sharing
    Patient location in hospital
Work/Study Item Completion: 10%
Draft TR 22.872 Completion: 10%
  V0.2.0
Controversial issues
  None
Notes: 1

## Slide 4: FS_5G_HYPOS Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 4
  number of drafting session participants: [15-20]
Number of slots requested for next meeting
  sum of plenary and drafting slots: [5]
Notes: 1

## Slide 5: FS_5G_HYPOS Completion Date
Current expected dates to send TR to SA plenary:
  For information: SA#78 (12/2017)
  For approval: SA#79 (03/2018)
Have these dates been changed at this meeting? No
Notes: 1

## Slide 6: FS_5G_HYPOS Planning/Progress
Topics to focus on at next SA1 meeting:
  Use cases definition and consolidation
  Use cases synthesis (clause 6)
  Input and assumptions for clause 7
Planning for subsequent meetings
  SA1#81 (02/2018)
    Suitability of positioning technologies for use cases (clause 7)
    Potential requirements (clause 8)
    Finalization of TR and recommendations
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  Topics in preparation of SA1#80
    Use cases: gather use cases and draft their description
    Preliminary list of technologies and related background material (input / assumptions for clause 7)
      The objective is to prepare an email discussion on clause 7 that will be held after SA1#80 (only a few weeks available between SA1#80 and SA1#81)
  Tentative start date : [18/09/2017]
Notes: 1

## Slide 8: FS_5G_HYPOS Progress Estimate
Estimated percentage completion:
  now: 10%
  Next meeting: [60%]
  In two meetings: [100%]
Notes: 1

## Slide 9: FS_5G_HYPOS Agreed documents
List of agreed documents at this meeting:
Tdoc Number | Sourcing Company | Document Title
S1-173498 | ESA | TR22.872 skeleton (v0.1.1)
S1-173416 | ESA, Intel, Thales, NextNav | 5G_HYPOS Proposal for the Scope of the Technical Report
S1-173417 | ESA | 5G_HYPOS Proposal for the overview of the Technical Report (clause 4)
S1-173499 | ESA, Intel, Thales, NextNav, Sprint | 5G_HYPOS Proposal for positioning use cases KPI (clause 5.1.1)
S1-173419 | Orange | Patient location in hospitals use case (5G_HYPOS)
S1-173420 | China Mobile | Accurate positioning for shared bikes
S1-173239 | ESA | TR 22.872 (v0.2.0) to include agreements at this meeting
Notes: 1