## Slide 1: FS_5GSAT Status Update Study on using Satellite Access in 5G
Cyril MICHEL
Thales
FS_5GSAT Rapporteur
3GPP TSG-SA WG1 Meeting #81
FUKUOKA, Japan, February 5th – February 9th -2018
Notes: 1

## Slide 2: FS_5GSAT Status
Is this a new WI? yes
This WI has been approved at SA#77
  Approved WID is in tdoc SP-170702
Notes: 1

## Slide 3: FS_5GSAT Progress
Progress made at this meeting, approval of
  Editorial cleaning and sections added (definitions, 5QIs, Considerations, Potential Requirements, Conclusion and Recommendations)
  Use cases added
    Global satellite overlay
    Indirect connections through relay UE
    5G Backhaul
Work/Study Item Completion: 70%
Draft TR 22.822 Completion: 70%
Controversial issues  None
Notes: 1

## Slide 4: FS_5GSAT Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 3
Number of slots requested for next meeting
  sum of plenary and drafting slots: 3
Number of Drafting session participants: #20
Notes: 1

## Slide 5: FS_5GSAT Completion Date
Current expected dates to send TR to SA plenary:
  For information: SA#79 (03/2018)
  For approval: SA#80 (06/2018)
Have these dates been changed at this meeting? yes
  If yes, previous target completion dates:
    For information: 12/2017 SA#78
    For approval: 03/2018 SA#79
Notes: 1

## Slide 6: FS_5GSAT Planning/Progress
Topics to focus on at next SA1 meeting:
  Review of summary of requirements and considerations
  Finalization of TR 22.822
  Report to SA plenary for decision
Planning for subsequent meetings
  None
Notes: 1

## Slide 7: FS_5GSAT Progress Estimate
Estimated percentage completion:
  now: 70%
  Next meeting (SA1 #82, 05/2018): 100%
Notes: 1

## Slide 8: FS_5GSAT Agreed documents
List of agreed documents at this meeting:
S1-180400 | THALES, TNO, Fraunhofer IIS, Nomor Research Gmbh, Hughes Network System Ltd, CNES CTTC | 'Editorial' corrections for TR22.822
S1-180401 | THALES, Fraunhofer IIS, Nomor Research Gmbh, Hughes Network System Ltd, CNES, CTTC | FS_5GSAT: Addition of sections to the Table of Content
S1-180556 | THALES, TNO, Fraunhofer IIS, Nomor Research Gmbh, Hughes Network System Ltd, , CNES, CTTC | FS-5GSAT - Global Satellite Overlay
S1-180566 | THALES, TNO, KPN, Fraunhoffer IIS, Nomor Research Gmbh, Hughes Network System Ltd, FirstNet, Suomen Virveverkko Oy, CNES, CTTC, Alibaba | FS_5GSAT – Use case: Indirect connection through a 5G satellite access
S1-180420 | THALES, TNO, Fraunhofer IIS, Nomor Research Gmbh, Hughes Network System Ltd, FirstNet, CNES, CTTC | FS-5GSAT - QCI for a 5G system with satellite access
S1-180582 | SES S.A., Airbus DS SLC, VT iDirect Solutions Ltd, Avanti Communications Ltd | FS_5GSAT Use Cases for 5G Backhaul
S1-180422 | THALES, TNO, KPN, Fraunhofer IIS, Nomor Research Gmbh, Hughes Network System Ltd, CNES, CTTC | FS-5GSAT - Proposed definitions in TR 22.822
S1-180542 | THALES, Fraunhofer IIS, Nomor Research Gmbh Hughes Network System Ltd, CNES, CTTC | FS-5GSAT - Proposed clarifications in TR 22.822
Notes: 1