## Slide 1: 5G_HYPOS Status Update 5G positioning services
Lionel Ries
ESA (European Space Agency)
5G_HYPOS Rapporteur
3GPP TSG-SA WG1 Meeting #83
West Palm Beach, Florida, USA, 20 - 24 August 2018
Notes: 1

## Slide 2: 5G_HYPOS Progress
Progress made at this meeting
  Agreement to build a single set of KPIs for TS 22.261 coming from TR 22.872, TR 22.804 and TR 22.889
    TS22.261-CR0269-rev2: Horizontal/Vertical positioning accuracy – a single table (7 service levels) to cover the needs expressed in TR 22.872, TR 22.804 and TR 22.889
    TS22.261-CR0270-rev2: Other KPIs (TTFF, velocity vector, heading as per TR 22.804, power consumption)
  TS22.261-CR0271-rev2: Security-related requirements (TR 22.872: anti-spoofing, anti-tampering, privacy)
  TS22.261-CR0272-rev2: Update of description and general requirements to align with TRs content (use cases description, multiple working points, hybridisation)
Work Item Completion: 50%
Controversial issues
  none
Notes: 1

## Slide 3: 5G_HYPOS Completion Date
Current expected dates to send TS to SA plenary:
  For information: SA#81 (09/2018)
  For approval: SA#82 (12/2018)
Have these dates been changed at this meeting? Yes
Estimated percentage completion:
  SA#81: 50%
  SA#82: 100%
Notes: 1

## Slide 4: 5G_HYPOS Planning/Progress
Topics to focus on at next SA1 meeting:
  Normative work on the remaining requirements and related aspects (for instance, but not limited to, remaining general requirements and operational requirements, consideration of alignment with 22.071 when relevant, etc.).
  Update of the annex of TS 22.261 on use case descriptions
  Other relevant aspects to 5G_HYPOS normative work
Note: following the work and agreement performed in SA1#83, no additional work on KPIs is expected for SA1#84
Planning for subsequent meetings
Notes: 1

## Slide 5: Work plan between meetings
[Email discussion or Telephone conference]
  Update of 22.261 annex to report use cases
  Options for alignment with TS 22.071
Notes: 1

## Slide 6: 5G_HYPOS Essential Info
This WI has been approved at SP#80
  Approved WID is in tdoc SP-180329
Notes: 1