## Slide 1: REFEC Status Update Feasibility Study on enhanced relays for energy efficiency and extensive coverage.
Jose Almodovar
KPN
5GLAN Rapporteur
3GPP TSG-SA WG1 Meeting #83
West Palm Beach, Florida, USA, 20 - 24 August 2018
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: REFEC Status
This WI has not been approved by SP
  The following slides assume approval at SP#81
Notes: 1

## Slide 3: REFEC Progress
Progress made at this meeting
  Approved the study item
Work/Study Item Completion: 0%
Draft <TS/TR> 22.xxx Completion: 0%
Controversial issues
  none
Notes: 1

## Slide 4: REFEC Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 0
Number of slots requested for next meeting
  sum of plenary and drafting slots: 1
Notes: 1

## Slide 5: REFEC Completion Date
Current expected dates to send <TR/TS> to SA plenary:
  For information: SA#83 (03/2019)
  For approval: SA#84 (06/2019)
Notes: 1

## Slide 6: REFEC Planning/Progress
Topics to focus on at next SA1 meeting:
  First set of use cases.
Planning for subsequent meetings
  SA1#85 (02/2019)
    Use cases
  SA1#86 (05/2019)
    Use cases, consolidation.
Notes: 1

## Slide 7: REFEC Progress Estimate
Estimated percentage completion:
  now: <0%>
  Next meeting: <30%>
  In two meetings: <80%>
  Complete 05/2019
Notes: 1

## Slide 8: REFEC Agreed documents
List of agreed documents at this meeting:
S1-182748 | KPN | Study on MUltihop RElays
Notes: 1