## Slide 1: FS_EAV Status Update Study on enhancement for UAVs
Qun Wei
China Unicom
FS_EAV Rapporteur
Remember: present only slides 3, 6, 7
3GPP TSG-SA WG1 Meeting #85
Tallinn, Estonia, 18 - 22 February 2019
Notes: 1

## Slide 2: FS_EAV Status
Is this a new WI? <yes>
Notes: 1

## Slide 3: FS_EAV Progress
Progress made at this meeting
  TR is agreed to send to SA plenary for information
  14 use cases are agreed
Work/Study Item Completion: 70%
Draft TR 22.829 Completion: 70%
Controversial issues
  none
Notes: 1

## Slide 4: FS_EAV Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 3
Number of slots requested for next meeting
  sum of plenary and drafting slots: 3
Notes: 1

## Slide 5: FS_ EAV Completion Date
Current expected dates to send TR to SA plenary:
  For information: SA#83 (after SA1#85)
  For approval: SA#84 (after SA1 #86)
Have these dates been changed at this meeting? <y>
  If yes, previous target completion dates:
    For information: SA#85
    For approval: SA#86
Notes: 1

## Slide 6: FS_ EAV Planning/Progress
Plan for TR completion at SA1#86
  New use cases and requirements
  Additional considerations, Consolidated potential requirements, Conclusions and Recommendations
  Editorial modifications
Preparation of WID for SA1#86
Notes: 1

## Slide 7: FS_ EAV Progress Estimate
Estimated percentage completion:
  now: 70%
  Next meeting: 95%
Notes: 1

## Slide 8: FS_EAV Agreed documents
List of agreed documents at this meeting:
S1-190473 | ZTE Corporation, CATT?, China Unicom? | Supplement for Use case of UBS
S1-190474 | Intel | Resolving EN for Use case of C2 communication
S1-190275 | China Unicom | Discussion of Time Delay Calculation of Unmanned Aerial Vehicle
S1-190260 | China Unicom | Discussion of Computation of UAV Density and Range of Inspection
S1-190276 | LG Electronics | Isolated deployment of Radio Access through UAV
S1-190475 | LG Electronics | Radio Access through UAV
S1-190476 | LG Electronics | Separation of UAV service area
S1-190484 | China Unicom, Huawei | Use case for simultaneously support data transmission for UAVs and eMBB users
S1-190478 | China Unicom, Huawei | Use case for autonomous UAVs controlled by AI
S1-190479 | ZTE Corporation, China Unicom | Use Case of modification UAV controller
S1-190480 | China Unicom | Use case for user path optimization of UAVs
S1-190517 | China Unicom | Use case for network resource adaptation to UAV needs
S1-190482 | InterDigital | Use case for UAV control
S1-190483 | CATT，China Unicom | Swarm of UAVs in logistics
S1-190015 | Rapporteur (China Unicom) | Cover page for presentation of TS22.829v1.0.0
Notes: 1