## Slide 1: FS_AVPROD Status Update Feasibility Study on Audio-Visual Service Production
Dr. Konstantin Septinus
Sennheiser
FS_AVPROD acting Rapporteur
3GPP TSG-SA WG1 Meeting #86
Suzhou, China, 6-10 May 2019
Notes: 1

## Slide 2: FS_AVPROD Progress
Progress made at this meeting
  Multiple definitions updated
  Update, clean-up and clarification of 7 use cases
  Update and clean-up of 2 informative annexes
  Consolidation of KPI and non-KPI requirements
  Additional considerations for A/V introduced
Work/Study Item Completion: 95%
No Controversial issues
Notes: 1

## Slide 3: FS_AVPROD Planning
Topics to focus on at next SA1 meeting:
  Clarification of 1 requirement
  Editorial clean-up and finalizing report
Notes: 1

## Slide 4: FS_AVPROD Completion Date
Current expected dates to send TR 22.827 to SA plenary:
  for approval: SA#84 (06/2019)
Have these dates been changed at this meeting? y
Estimated percentage completion:
  SA#84: 95%
    Last clean-up and finalizing of report
  SA#85: 100%
Notes: 1

## Slide 5: FS_AVPROD History
This WI has been approved at SP#80
  Approved SI WID is in TDoc SP-180340
This WI has later been revised at SP#82
  Updated SI WID is in TDoc SP-181015
    Addition of new editor (K. Septinus, Sennheiser)
History of completion rates @ SA WG1
  SA1#86 (05/2019): 95%
  SA1#85 (02/2010): 80%
  SA1#84 (11/2018): 50%
  SA1#83 (08/2018): 10%
  SA1#82 (05/2018): 0%
Notes: 1

## Slide 6: FS_AVPROD Agreed Documents
List of agreed documents at this meeting:
Work status prior to this meeting: Latest version: TR 22.827v1.0.0 Target completion date: SA#84 (06/2019) Percentage completion: 80% |  |  |  |  | 
Scope, overview, definitions |  |  |  |  | 
Cont | S1-191362 | Sennheiser | Input for clause 3 “Definitions, Abbreviations and Symbols” | Agreed | 
Cont | S1-191363 | Deutsche Telekom | Adding the definition of network operator | Agreed | 
Use case updates |  |  |  |  | 
Cont | S1-191364 | Sennheiser | Clean-up (Review) of the “On-site Live Audio Presentation” use case | Agreed | 
Cont | S1-191365 | Sennheiser | Clean-up (Review) of the “Audio Streaming in Live Performances” use case | Agreed | 
Cont | S1-191367 | Sennheiser | Clean-up (Review) of the “Intercom system for large live events” use case | Agreed | 
Cont | S1-191366 | Sennheiser | Clean-up (Review) of the “Live production with integrated audience services” use case | Noted | 
Cont | S1-191368 | Ericsson | New accuracy requirement for video use case and some clean-up | Agreed | 
Cont | S1-191369 | Qualcomm Incorporated | Clarifications and corrections to AVPROD NPN onboarding and authentication requirements | Agreed | 
Cont | S1-191560 | Intel | NPN access authentication based on PLMN subscription and credentials | Agreed | 
Cont | S1-191370 | Sennheiser | Review of Informative annex “ Real-time audio-streaming latency budget” of AV_PROD | Agreed | 
Cont | S1-191361 | Tencent | Clarification of Potential Requirements for Live Immersive Media Service | Agreed | 
New use cases, considerations |  |  |  |  | 
Cont | S1-191376 | NICT | Multi-angle camera video production in dense user environments | Agreed | 
Cont | S1-191372 | Sennheiser | Informative annex about group scenarios in AV_PROD | Agreed | 
Cont | S1-191162 | Sennheiser, EBU | Proposal for TR 22.827, Section 7: Additional Consideration | Agreed | 
Consolidation |  |  |  |  | 
Cont | S1-191567 | EBU, BBC | Proposal for consolidated performance requirements of AVPROD | Agreed | 
Cont | S1-191568 | EBU, BBC | Proposal for consolidated service requirements of AVPROD | Agreed | 
Notes: 1