## Slide 1: FS_CMED Status Update Study on Communication Services for Critical Medical Applications
Mathieu Lagrange
B>com
FS_CMED Rapporteur
3GPP TSG-SA WG1 Meeting #86
Suzhou, China, 6-10 May 2019
Notes: 1

## Slide 2: FS_CMED Progress
Progress made at this meeting
  Addition of a new use on Telemetry
  Update use cases with KPIs associated to transmitted data
  Addition of consolidation sections (Performances and Service level)
Work/Study Item Completion: 90%
Controversial issues
  None
Notes: 1

## Slide 3: <WI Code> Planning
Planning for subsequent meetings
  SA1#87 (08/2019): 100%
    TR’s Clean-up
    General sections: Symbols, Abbreviations, Conclusion and Recommendation
    Removal of section 5.4 which has no use cases
    Remove square brackets for bit-rate requirements on compressed video (guidance from SA4 requested)
  <Until close of WI as defined in WID>
Notes: 1

## Slide 4: Work plan between meetings
  Guide: this optional slide is an opportunity for rapporteurs to indicate what activities are proposed between meetings
Email discussion
  N/A
Telephone conference
  N/A
Notes: 1

## Slide 5: FS_CMED Completion Date
Current expected completion dates:
  For information: SA#84 (06/2019)
  For approval: SA#85 (09/2019)
Have these dates been changed at this meeting? No
Notes: 1

## Slide 6: FS_CMED History
This WI has been approved at SA1#83 / SP#81
  Agreed/Approved WID is in tdoc S1-182745 / SP-180783
History of completion rates
  SA1#85 (02/2019): <65%>
  SA1#84 (11/2018): <15%>
  <Until start of WI>
Notes: 1