## Slide 1: Status Update MONASTERYEND
Gach, Guillaume
UIC International Union of Railways
MONASTERYEND Rapporteur
3GPP TSG-SA WG1 Meeting #87
Sophia Antipolis, France, 19 - 23 August 2019
Notes: 1

## Slide 2: MONASTERYEND Progress
Progress made at this meeting
  14 tdocs: 6 agreed, 6 noted & 2 withdrawn
  Enhancement of TS 22.280
    Request a list of functional aliases in a certain area
    Support the UC for Arbitration when a user is registered to multiple UEs
    Clarify routing location dependent communications as part of handling MCX Service Private Communication requests
    Extend Functional Alias binding to MCX Service Private Communication
    Support location services while operating in off-net
    Support recording of media content while operating in off-net
Work/Study Item Completion: 70%
Controversial issues
  None
Notes: 1

## Slide 3: MONASTERYEND Planning
Planning for subsequent meetings
  SA1#88 (11/2019): 100%
    Remaining normative work not handled in previous SA1 based on results from gap analysis on remaining requirements for Off-Network MCX Service communications, interworking between MCX and other networks (e.g. public networks), and refinement of QoS (SID FS_FRMCS3)
Notes: 1

## Slide 4: MONASTERYEND Completion Date
Current expected completion dates:
  For approval: SA#86 (12/2019)
Have these dates been changed at this meeting? n
Notes: 1

## Slide 5: MONASTERYEND History
This WI has been agreed/approved at SA1#86 / SA#84
  Agreed/approved WID is in tdoc <S1-191587 / SP-190312>
History of completion rates
  SA1#86 (05/2019): <20%>
Notes: 1