## Slide 1: FS_SACI_MCS Status Update Study sharing administrative configuration between interconnected MCX Service systems
Jens Toobe
BDBOS
FS_SACI_MCS Rapporteur
3GPP TSG-SA WG1 Meeting #87
Sophia Antipolis, France, 19 - 23 August 2019
Notes: 1

## Slide 2: FS_SACI_MCS Progress
Progress made at this meeting
  SID was agreed
Work/Study Item Completion: 0%
Controversial issues
  none
Notes: 1

## Slide 3: FS_SACI_MCS Planning
Planning for subsequent meetings
  SA1#87+1 (Nov 2019)
    Definition of use cases and potential new service reqs.
  SA1#87+2 (Feb 2020)
    Definition of use cases and potential new service reqs.
    Identification of potential security reqs
  SA1#87+3 (May 2020): 100%
    Identification of potential security reqs
    Evaluation of existing reqs and gap analysis
Notes: 1

## Slide 4: Work plan between meetings
Email discussion
  Definition of use cases & discussions about potential new service requirements
Telephone conference
  TBC
Notes: 1

## Slide 5: FS_SACI_MCS Completion Date
Current expected completion dates:
  For information: SA#87 (03/2020)
  For approval: SA#88 (06/2020)
Notes: 1

## Slide 6: FS_SACI_MCS History
This WI has been agreed at SA1#87
  Agreed SID is in tdoc S1-192829
Notes: 1