## Slide 1: 5MBS_eMC Status Update Broadcast / multicast requirements supporting Mission Critical Services in 5G
Jens Toobe
BDBOS
5MBS_eMC Rapporteur
3GPP TSG-SA WG1 Meeting #88
Reno, Nevada, USA, 18 – 22 November 2019
Notes: 1

## Slide 2: 5MBS_eMC Progress
Progress made at this meeting
  CR#0384 in tdoc S1-193270 with minor revisions agreed to 3GPP TS 22.261
  The CR adds seven new requirements under 6.13 Flexible broadcast/multicast service contributed by mission critical verticals
Work/Study Item Completion: 100%
Controversial issues
  none
Notes: 1

## Slide 3: 5MBS_eMC Completion Date
Current expected completion dates:
  For approval: SA#86 (12/2019)
Notes: 1

## Slide 4: 5MBS_eMC History
This WI has been agreed at SA1#87
  WID in tdoc S1-192855 was agreed at SA1#87
  CR#0384 to 3GPP TS 22.261 in tdoc S1-192826. Was not treated at SA1#87 due to lack of time at the meeting
  CR#0384 to 3GPP TS 22.261 in tdoc S1-193270 was agreed with minor revisions in SA1#88
Notes: 1