## Slide 1: FS_eCAV Status Update Enhancements for cyber-physical control applications in vertical domains
Michael Bahr
Siemens
FS_eCAV Rapporteur
3GPP TSG-SA WG1 Meeting #88
Reno, Nevada, USA, 18 - 22 Nov 2019
Notes: 1

## Slide 2: FS_eCAV Progress
Progress made at this meeting
  Consolidation of TR 22.832
    Tracking of consolidation of requirements
    Editorial corrections
    Update of material for further information/clarification
  New use case on 5G clock synchronicity budget
Work/Study Item Completion: 95%
Controversial issues
  none
Notes: 1

## Slide 3: FS_eCAV Planning
  Guide: if WID is 100% complete or if SA1 agreed to stop the work, delete this slide
Planning for subsequent meetings
  SA1#89 (Feb 2020): 100%
    Resolve any remaining editor notes and tbds, e.g. in use cases
    Resolve remaining FFS in requirements
Notes: 1

## Slide 4: Work plan between meetings
  Guide: this optional slide is an opportunity for rapporteurs to indicate what activities are proposed between meetings
Email discussion
  Remaining editor notes, corrections of TR 22.832
  December 2019, January 2020
Telephone conference
  Remaining editor notes, corrections of TR 22.832
  December 2019, January 2020
Notes: 1

## Slide 5: FS_eCAV Completion Date
Current expected completion dates:
  For information: SA#84 (06/2019)
  For approval: SA#85 (09/2019)
Have these dates been changed at this meeting? n
Notes: 1

## Slide 6: FS_eCAV History
This WI has been approved at SA#83
  Approved WID is in tdoc SP-190092
History of completion rates
  SA1#87 (Aug 2019): 85%
  SA1#86 (May 2019): 60%
  SA1#85 (Feb 2019): 5%
Notes: 1