## Slide 1: Chairman’s views on Rel-18
Number of SIDs in Rel-18
Rel-18 Stage 1 freeze date
S1-203008

## Slide 2: Number of SIDs in Rel-18 (1/2)
Let’s take a look at the past
  Total Rel-17: 11 studies
  Total Rel-16: 15 studies
  Total Rel-15: 2 studies (SMARTER study item)
  Total Rel-14: 12 studies
  Total Rel-13: 7 studies
  Total Rel-12: 11 studies
Where are we now?
  We already approved 12 SIDs for Rel-18.
  In SA1#91e 14 proposals will be presented.
Impact of Covid-19
  Meetings are less efficient: no physical interactions make discussions challenging and affects the ability to get consensus.
  Other groups are also affected and may need more time and/or lighter workload. This will impact the quantity of SA1 work that they can absorb.

## Slide 3: Number of SIDs in Rel-18 (2/2)
  Conclusion: Given past experience, and given the Covid-19 situation, about 15 SIDs maximum are manageable for Release 18
  SA1 chairman’s Proposal:
    If more than 15 SIDs are agreed for Rel-18 (including the ones agreed at SA1#91e), then SA1 might have to go through a prioritization process.
      If it takes place, this prioritization process will be established after SA#89 and should be completed by SA1#92e and ratified in SA#90.
      Lower priority SIDs might be delayed to Rel-19.
    New SIDs agreed after SA1#91e will be by default targeted to Rel-19.

## Slide 4: Rel-18 Stage 1 freeze date (1/2)
SA discussions about Rel-18 schedule will start in September (in RAN possibly in December).
About Rel-17, there is a high probability that Stage-2 will be shifted from Dec 2020 to March 2021
SA1 chair’s Proposal on Rel-18 Stage 1 freeze date:
  80% complete by June 2021
    This leaves 4 regular meeting including SA#91e (SA1#91,92,93,94) + 1 adhoc (Q1 2021)).
  100% complete by September 2021
    This is one additional meeting (SA1#95) after 80% completion
Depending on discussions in SA plenary and further possible delays from Rel-17, these deadlines can be later changed.

## Slide 5: Rel-18 Stage 1 freeze date (2/2)
2021
2022
Rel-17 RAN Content Def.
100%
Rel-16 RAN Completion
83
84
85
86
87
88
89
90
Release 16
2019
2020
Rel-16 Stage 2
Rel-16 Stage 3
Today
Release 17
Rel-16 ASN.1
Rel-17 Stage 1 80%
91
92
93
94
TSG#
Release 18
RAN4
RAN4 Perf
95
ASN.1
Rel-17 RAN Completion (RAN2/3/4core)
Rel-17 Stage 3
Rel-17 Stage 2
100%
Rel-18 Stage 1 80%
Stage 2 expected to be moved 3 months
SA1 chair’s proposal:
Freeze SA#93, (80% ready SA#92)
St 2 extension