## Slide 1: FS_5TRS Status Update Feasibility Study on 5G Timing Resiliency System
Betsy Covell
Nokia
FS_5TRS Rapporteur
3GPP TSG-SA WG1 Meeting #93e
Electronic Meeting, 22 February – 4 March 2021
Notes: 1

## Slide 2: FS_5TRS Progress
Progress made at this meeting
  Editorial and other clean-ups
  Security and charging requirements
  Consolidation of potential requirements
  Conclusion
Work/Study Item Completion: 97%
Controversial issues
  none
Notes: 1

## Slide 3: FS_5TRS Planning
Planning for subsequent meetings
  SA1#94
    CR to clean up inclusive language
Notes: 1

## Slide 4: Work plan between meetings
Email discussion
  none
Notes: 1

## Slide 5: FS_5TRS Completion Date
Current expected completion dates:
  For information: SA#91e (03/2021)
  For approval: SA#91e (03/2021)
Have these dates been changed at this meeting? n
Notes: 1

## Slide 6: FS_5TRS History
This WI has been revised at SA1#93e / SA1#92e / SA#90e
History of completion rates
  SA1#90e (05/2020): 0%
  SA1#91e (08/2020): 10%
  SA1#92e (11/2020): 75%
Notes: 1