## Slide 1: FS_TACMM Status Update Study on supporting tactile and multi-modality communication services
Xiaonan Shi
China Mobile
FS_TACMM Rapporteur
3GPP TSG-SA WG1 Meeting #93e
Electronic Meeting, 22 February – 4 March 2021
Notes: 1

## Slide 2: FS_TACMM Progress
Progress made at this meeting
  Skeleton, scope and overview added
  4 new use cases agreed
Work/Study Item Completion: 30%
Controversial issues
  Potential new requirement on synchronization
Notes: 1

## Slide 3: FS_TACMM Planning
Planning for subsequent meetings
  SA1#94e (05/2021): 80%
    Complete use cases and potential requirements
    Consolidation and conclusions
  SA1#95e (08/2021): 100%
    Final TR cleanup.
Notes: 1

## Slide 4: Work plan between meetings
Email discussion
  Potential new use cases
  Potential new requirements
  Before next meeting, probably 04/2021
Notes: 1

## Slide 5: FS_TACMM Completion Date
Current expected completion dates:
  For information: SA#91
  For approval: SA#92
  Have these dates been changed at this meeting? N
Notes: 1

## Slide 6: FS_TACMM History
This WI has been <agreed/approved/revised> at <SA1#92 / SA#90>
  Agreed WID is in tdoc < S1-204384 / SP-201039 >
History of completion rates
Notes: 1