## Sheet1
SA WG2 Meeting #114 | [14 empty] | S2-162162
23 – 26 Feb 2016, Sophia Antipolis, FR
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Discussion
Agenda Item: 7.2
Work Item / Release: All / Rel-13 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[9 empty] | Oct 15 |  | Nov 15 |  | Jan 16 |  | Feb 16 |  | Apr 16 |  | May 16 |  | Jul 16 |  | Aug 16 |  | Oct 16 |  | Nov 16
status (%) |  |  |  |  | Target |  | planned | accumul. | SA2#111 |  | SA2#112 |  | SA2#113 |  | SA2#113AH |  | SA2#114 |  | SA2#115 |  | SA2#116 |  | SA2#116bis |  | SA2#117 |  | SA2#118 |  |  | percentage of planned resources
4/15 | 1/16 | #114 | 2/16 | Work Item | date |  | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | 113AH | 114 | 115 | 116 | 116bis | 117 | 118
95 | 100 |  |  | FS_AE_CIoT / R13 | 2016-12-15 |  | 5 | 5 | 4 | 4 | 1 | 1 | [16 empty] | 113AH: 100; percentage of planned resources 114: 100
| 95 |  |  | CIOT_stage2 / R13 |  | O7 V6 | 11 | 15 |  |  | 3 | 3 | 3 | 3 | 5 | 9 | [12 empty] | 113AH: 100; percentage of planned resources 114: 100
70 | 80 | 90 |  | FS_eDECOR | 2016-03-16 | O4 V5 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | [11 empty] | 113AH: 75; percentage of planned resources 114: 100
20 | 40 | 75 |  | FS_CUPS | 2016-06-16 | O7 V13 | 9.3 | 6 | 1 | 2 | 2 | 2 | 2 | 2 |  |  | 2.3 |  | 2 | [9 empty] | 113AH: 53.7634; percentage of planned resources 114: 78.4946
5 | 15 | 20 |  | FS_NextGen | 2016-09-16 | many | 56 | 15 |  |  | 1 | 2 | 4 | 4 | 9 | 9 | 6 |  | 7 |  | 6 |  | 9 |  | 6 |  | 8 |  | 113AH: 25; percentage of planned resources 114: 35.7143
10 | 22 | 50 |  | FS_V2XARC | 2016-06-16 | O9 V18 | 7.7 | 3 |  |  | 1 | 1 | 2 | 2 |  |  | 2.7 |  | 2 | [9 empty] | 113AH: 38.961; percentage of planned resources 114: 74.026
| 10 | 85 |  | FS_GENCEF | 2016-06-16 | O3 V7 | 2.7 | 0.5 |  |  |  |  | 1 | 0.5 |  |  | 0.7 |  | 1 | [9 empty] | 113AH: 37.037; percentage of planned resources 114: 62.963
|  | 6 |  | FS_IOPS_LB |  | O7 V5 | 5 | 0 | [8 empty] | 1 |  | 2 |  | 2 | [7 empty] | 113AH: 0; percentage of planned resources 114: 20
|  | 35 |  | FS_AE_enTV |  | O4 V5 | 5 | 0 | [8 empty] | 1 |  | 2 |  | 2 | [7 empty] | 113AH: 0; percentage of planned resources 114: 20
|  | 50 |  | NonIP_GPRS |  | O1 V8 | 0.6 | 0 | [8 empty] | 0.3 |  | 0.3 | [9 empty] | 113AH: 0; percentage of planned resources 114: 50
70 | 80 | 95 |  | FS_V8 | 2016-03-16 | O11 V8 | 7.3 | 6 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 1.3 | [11 empty] | 113AH: 82.1918; percentage of planned resources 114: 100
|  |  |  | V8 | [14 empty] | 1
60 | 75 | 95 |  | FS_SEW2 | 2016-06-16 | O5 V9 | 7 | 4 | 2 | 1.5 | 2 | 1 | 1 | 1.5 |  |  | 2 | [11 empty] | 113AH: 71.4286; percentage of planned resources 114: 100
|  |  |  | SEW2 | [14 empty] | 1
40 | 70 | 90 |  | FS_AULC | 2016-06-16 | O6 V7 | 5.3 | 2.5 | 1 | 1 | 1 | 1 | 1 | 0.5 |  |  | 1.3 |  | 1 | [9 empty] | 113AH: 56.6038; percentage of planned resources 114: 81.1321
| 30 | 50 |  | FS_SeDoC | 2016-06-16 | O5 V3 | 4 | 1 |  |  | 1 |  | 1 | 1 |  |  | 1 |  | 1 | [9 empty] | 113AH: 50; percentage of planned resources 114: 75
10 | 40 | 85 |  | FS_SDCI | 2016-06-16 | O6 V7 | 4.3 | 2.5 |  |  | 1 | 1 | 1 | 1.5 |  |  | 1.3 |  | 1 | [9 empty] | 113AH: 46.5116; percentage of planned resources 114: 76.7442
| 20 | 50 |  | EIEI | 2016-06-16 | O4 V5 | 3 | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1 | [9 empty] | 113AH: 33.3333; percentage of planned resources 114: 66.6667
45 | 60 | 100 |  | EWE | 2016-06-16 | O4 V5 | 2.8 | 0.75 |  |  | 1 | 0.5 | 1 | 0.25 |  |  | 0.3 |  | 0.5 | [9 empty] | 113AH: 71.4286; percentage of planned resources 114: 82.1429
| 20 | 45 |  | FS_RobVoLTE | 2016-06-16 | O6 V8 | 3 | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1 | [9 empty] | 113AH: 33.3333; percentage of planned resources 114: 66.6667
|  |  |  | Maint 5.1 |  |  |  | 9 | 2 | 3 | 2 | 3 | 3 | 3 |  |  | 4.7 |  | 4 |  | 4
|  |  |  | Maint 5.2 |  |  |  | 1 |  |  |  |  | 1 | 1 |  |  | 1.3 |  | 1 |  | 1
|  |  |  | Maint 5.3 |  |  |  | 9.5 | 2 | 3.5 | 2 | 3.5 | 3 | 2.5 |  |  | 2.7 |  | 2 |  | 2
|  |  |  | Maint 5.4 |  |  |  | 2 | 1 | 0.5 | 1 | 1 | 1 | 0.5 |  |  | 1 |  | 0.5 |  | 0.5
|  |  |  | TEI14 3GPP acc |  |  |  | 1 | 1 | 1
|  |  |  | TEI14 PCC/QoS |  |  |  | 0.5 | 0.5 | 0.5
|  |  |  | TEI14 n3GPP | [14 empty] | 0.5
|  |  |  | TEI14 IMS/rel. |  |  |  | 0 | 0.5 | [9 empty] | 1
|  |  |  | sum |  |  |  |  | 18 | 22 | 22 | 23 | 30 | 28.25 | 14 | 18 | 33.9 | 0 | 32.8 | 0 | 17.5 | 0 | 9 | 0 | 0 | 0 | 8 | 0