## Sheet1
SA WG2 Meeting #133
May 13-17, 2019, Reno, USA
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Endorsement
Agenda Item: 7.2
Work Item / Release: All / Rel-15 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[13 empty] | Jul 18 |  | Aug 18 |  | Oct 18 |  | Nov 18 |  | Jan 19 |  | Feb 19 |  | Apr 19 |  | May 19 |  | Q3 / Jun 19 |  | Q4 | Q4 | potential | Q1 | Q2 | Q2
|  |  | Target | status estimation (%) | [5 empty] | acc./plan. | planned | accumul. | SA2#128 |  | SA2#128-bis |  | SA2#129 |  | SA2#129-bis |  | SA2#130 |  | SA2#131 |  | SA2#132 |  | SA2#133 |  | SA2#134 |  | #135 | #136 | #136AH | #137 | #138 | #139
| Work Item | Supporter | date | Q1/18 | Q2/18 | Q3/18 | Q4/18 | Q1/19 | Q2/19 | TUs (%) | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Req | Grant | Plan | Plan | Plan | Plan | Plan | Plan | updated |  | before SA#81 | #129bis planning input | #131 planning input | #133 planning input
| FS_5GSAT_ARCH | 36 | 2019-09-01 |  |  | 15 |  |  |  | 68 | 10 | 6.8 | 1 | 1 | 1 | 0.7 | 1 | 0.5 | 2 | 1.3 | 1 | 1 | 1 | 0.8 | 1 | 0.5 | 1 |  | 1 | 1 | [7 empty] | 28.5.18 updated by rapporteur | 23.8.18 agreed during SA2 work planning to move 1TU from Oct to Jan | 18.11. rapporteur proposes to distribute the remaining 7TUs to 1 TU per meeting until Sep 2019
| 5G_URLLC |  | 2019-06-01 |  |  |  |  | 30 |  | 66.6667 | 9 | 6 | [8 empty] | 2 | 1 | 2 | 2 | 2 | 2 | 2 |  | 1 | 1 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 5.11. rapporteur input, possibly additional study conclusions in Q1 | 11.2. rapporteur confirms 2 + 2 | 7.5. rapporteur: 1 TU for maintenance in Q3
| CIOT_5G |  | 2019-06-01 |  |  |  |  | 50 |  | 97.1429 | 14 | 13.6 | [8 empty] | 3 | 3.5 | 3 | 3.5 | 3 | 3.6 | 3 |  | 2 | 3 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 28.11. rapporteur input | 9.2. rapporteur confirms 3 + 3 | 18.4. rapporteur: 2 TUs for maintenance in Q3
| eV2XARC |  | 2019-06-01 |  |  |  |  | 30 |  | 83.3333 | 15 | 12.5 | [8 empty] | 3 | 3.5 | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 30.10. rapporteur input | 7.2. rapporteur confirms 3 + 3 | 19.4. rapporteur: 3 TUs in Q3
| eNA |  | 2019-06-01 |  |  |  |  | 65 |  | 92.5926 | 13.5 | 12.5 | [8 empty] | 3 | 3.3 | 3 | 3.6 | 3 | 3.6 | 3 |  | 1.5 | 2 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 3.11. rapporteur input | 12.2. rapporteur confirms 3 + 3 | 18.4. rapporteur: 1,5 TUs for maintenance in Q3
| R17 FS_eNA_phase 2 | 30? | 2020-03-01 |  |  |  |  | 45 |  | 0 | 10.5 | 0 | [16 empty] | 1.5 |  | #135: 3; #136: 3; #137: 3 | [5 empty] | 18.4. rapporteur: 1,5 TUs in Q3 + 3 TUs per meeting until finalisation in Q1
| eNS |  | 2019-06-01 |  |  |  |  | 60 |  | 40 | 5 | 2 | [8 empty] | 1.5 | 0.5 | 1.5 | 1 | 1 | 0.5 | 1 |  | 0 | [7 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 17.11. rapporteur input, includes one TUs in Q1 for additional study conclusions, if required | 7.2. rapporteur confirms 1 + 1 | 26.4. rapporteur: 0 TU in Q3
| V_LAN |  | 2019-06-01 |  |  |  |  | 18 |  | 104.1379 | 14.5 | 15.1 | [8 empty] | 3 | 3.6 | 3 | 4 | 3 | 4 | 3 |  | 2.5 | 3.5 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 6.11. rapporteur input, possibly additional study conclusions in Q1 | 6.2. rapporteur confirms 3 + 3 | 26.4. rapporteur: 2,5 TUs in Q3, possible some shared with URLLC
| R17 FS_IIoT (V_LAN) | 12? | 2020-03-01 |  |  |  |  | 18 |  | 0 | 1 | 0 | [16 empty] | 1 | [12 empty] | 26.4. rapporteur: 1 TU in Q3
| R17 FS_eNPN (V_LAN) | 6? | 2020-03-01 |  |  |  |  | 18 |  | 0 | 6 | 0 | [16 empty] | 0.5 |  | 2 | 1.5 | 1 | 1 | [7 empty] | 6.5. rapporteur: 0.5 TUs in Q3, then 2 + 1.5 + 1 + 1 until finalisation in Q1
| R17 FS_5GLAN enh (V_LAN) | 12? | 2020-03-01 |  |  |  |  | 18 |  | 0 | 5 | 0 | [16 empty] | 1 | [12 empty] | 7.5. rapporteur: 1 TU per meeting until finalisation in Q1 | bar: #135 to #137
| ATSSS |  | 2019-06-01 |  |  |  |  | 45 |  | 86.6667 | 12 | 10.4 | [8 empty] | 2 | 2 | 2 | 2.4 | 3 | 3 | 2 |  | 3 | 3 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 17.11. rapporteur input, includes Q1 time for additional study conslusions in Q1 | 11.2. rapporteur updates 2 + 2 to 3 + 2 | 26.4. rapporteur: 3 TU in Q3
| R17 FS_eATSSS | 15? | 2020-06-01 |  |  |  |  | 45 |  | 0 | 6 | 0 | [16 empty] | 1 | [12 empty] | 26.4. rapporteur, initial estimate: 1 TU every meeting until finalisation in Q2 | bar: #135 to #136; #137 to #139
| eLCS |  | 2019-06-01 |  |  |  |  | 45 |  | 79.0909 | 11 | 8.7 | [8 empty] | 2 | 2 | 3 | 2.9 | 2 | 2.3 | 3 |  | 1 | 1.5 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 5.11. rapporteur input, budget incl. continuing also the study in 1H19 | 8.2. rapporteur confirms 2 + 3 | 26.4. rapporteur: 1 TU in Q3
| R17 FS_eeLCS | 22? | 2019-06-01 |  |  |  |  | 45 |  | 48 | 15 | 7.2 | [8 empty] | 2 | 2 | 3 | 2.9 | 2 | 2.3 | 3 |  | 1 |  | #135: 2; #136: 2 | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 5.11. rapporteur input, budget incl. continuing also the study in 1H19 | 8.2. rapporteur confirms 2 + 3 | 26.4. rapporteur: 1 TU in Q3 and 2*2 TUs in Q4
| eSBA |  | 2019-06-01 |  |  |  |  | 50 |  | 74.0741 | 13.5 | 10 | [8 empty] | 3 | 2.7 | 3 | 3 | 3 | 2.8 | 3 |  | 1.5 | 1.5 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 14.11. rapporteur input | 12.2. rapporteur confirms 3 + 3
| 5WWC |  | 2019-06-01 |  |  |  |  | 50 |  | 89.1667 | 12 | 10.7 | [8 empty] | 2 | 2.2 | 3 | 3.5 | 2 | 2.5 | 3 |  | 2 | 2.5 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 14.11. rapporteur input | 8.2. rapporteur confirms 2 + 3 | 2.5. rapporteur: 2 TUs in Q3
| R17 FS_5WWC follow-up |  | 2020-06-01 |  |  |  |  | 45 |  | #DIV/0! | 0 | 0
| ETSUN |  | 2019-06-01 |  |  |  |  | 45 |  | 76 | 5 | 3.8 | [8 empty] | 1 | 1 | 1 | 1 | 1.5 | 1.3 | 1 |  | 0.5 | 0.5 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 12.11. rapporteur input | 11.2. rapporteur updates 2 + 1 to 1.5 + 1 | 23.4. rapporteur: 0,5 TUs in Q3
| FS_eIMS5G continuation |  | 2019-06-01 | 20 | 40 | 40 |  | 70 |  |  | 6 |  | [2] |  | [2] |  |  |  | [1] |  | 2 | 2 | 0 | [5 empty] | 1 | [7 empty] | 2018-02-06 | 7.5.18 rapporteur confirmed | 9.8.18 rapporteur considers to un-pause in Nov | 29.10. rapporteur input, striving for normative results in Q2 as considered with the earlier updated SID and WF in S2-188023 |  | 22.4. rapporteur: 1 TU per meeting until finalisation in Q1 | bar: #135 to #136; #137
| eIMS5G |  | 2019-06-01 | [6 empty] | 42.8571 | 3.5 | 1.5 | [12 empty] | 1.5 | 1 | 1.5 |  | 0.5 | 0.5 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 12.11. rapporteur input | 6.2. rapporteur updates 2 + 1 to 1.5 + 1.5 for a normative WI
| RACS |  | 2019-06-01 | [6 empty] | 88 | 2.5 | 2.2 | [12 empty] | 1 | 1.2 | 1 |  | 0.5 | 1 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 13.11. rapporteur input | 12.2. rapporteur confirms 1 + 1 | 25.4. rapporteur: 0,5 TUs in Q3
| FS_LLC_Mob |  | 2018-09-01 | 35 | 75 | 75 |  |  |  | #DIV/0! | 0 | 0 | [1] |  | [1] |  | [0.5] |  | [0.5] | [9 empty] | 0 | [7 empty] | no change | 10.5.18 rapporteur confirmed | 13.8.18 rapporteur considers to un-pause in Q4 for some conclusions |  |  | 23.4. rapporteur: 0 TUs in Q3
| FS_FLADN |  | Mar 19 | [6 empty] | #DIV/0! | 0 | 0 | [0.5] |  | [0.5] |  | [0.5] |  | [0.5] |  | [0,5] |  | [0,5] | [14 empty] | 9.5.18 initial estimates by rapporteur to be | 7.8.18 rapporteur shifts budget by a quarter | 30.10. rapporteur input, all on study | 7.2. rapporteur confirms 1 + 1
| R17 WI FLADN | 24? | Dec 19 | [6 empty] | 0 | 1 | 0 | [16 empty] | 0.5 |  | #135: 0.5 | [5 empty] | 22.4. rapporteur: 2 * 0,5 TUs until finalisation in Q4
| FS_EPS_URACE |  | 2018-12-17 |  | 10 | 10 |  |  |  | #DIV/0! | 0 | 0 | [1] |  | [1] |  | [1] |  | [1] | [9 empty] | 0 | [8 empty] | 10.5.18 rapporteur confirmed | 13.8.18 rapporteur considers to un-pause in Q4 |  |  | 23.4. rapporteur: 0 TUs in Q3
| xBDT |  | 2018-12-17 | [6 empty] | 62.5 | 0.8 | 0.5 | [0.5] |  | [0.5] |  | [0.5] |  | [0.5] |  | [0,5] |  | [0,5] |  | 0.5 | 0.5 | 0.3 | [11 empty] | 10.8.18 rapporteur shifts budget by a quarter | 3.11. rapporteur input | 6.2. rapporteur requests 0.5 + 0.3
| Parlos |  | Mar 19 |  |  |  |  | 95 |  | 56 | 2.5 | 1.4 |  |  |  |  | [1] |  | [1] |  | 1 | 1 | 1 | 0.1 | 0.5 | 0.3 | [13 empty] | 7.11. rapporteur input | 7.2. rapporteur updates 1 + 1 to 0.5 + 0
| FS_ENTRADE |  | 2018-09-01 | 20 | 70 | 70 |  |  |  | #DIV/0! | 0 | 0 | [1] |  | [1] | [5 empty] | [0,5] |  | [0,5] | [5 empty] | 0 | [7 empty] | 2018-02-08 | 15.5.18 rapporteur confirmed | 10.8.18 rapporteur assumes will be considered for Q1 | 5.11. rapporteur: 1 TU in Jan or Feb concluding the TR and 1 TU in Apr or May for normative | 11.2. rapporteur confirms | 23.4. rapporteur: 0 TUs in Q3
| FS_AAI_LTE_NR | 14? | Dec 19 |  | 30 | 30 |  |  |  | 0 | 3 | 0 | [1] |  | [1] |  | [1] |  | [1] |  | [2] |  | [2] | [5 empty] | 1 | [7 empty] | 2018-02-13 | 16.5.18 rapporteur confirmed | 7.8.18 rapporteur confirms remaining budget | 7.11. rapporteur input, normative work in Q2 | 18.2. rapporteur confirms 1 + 1 | 22.4. rapporteur: 1 TU per meeting until finalisation in Q4 | bar: #135 to #136
| FS_NG_RTC | ?? | Mar 19 | [6 empty] | 0 | 3 | 0 | [1] |  | [2] |  |  |  | [1] |  | [1] |  | [1] | [5 empty] | 1 | [8 empty] | 7.5.18 initial estimates by rapporteur to be | 13.8.18 rapporteur considers to un-pause in Q4; reducing earlier requested budget | 5.11. rapporteur input, 3 meetings SI and 1 on WI |  | 19.4. rapporteur: 1 TU per meeting until finalisation in Q4 | bar: #135 to #136
| UDICoM |  | 2019-06-01 |  |  |  | 80 | 100 |  | 140 | 0.5 | 0.7 | [12 empty] | 0.5 | 0.7 |  |  | 0 | [7 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 28.11. Rapporteur: conclude in Jan and do related normative work in Feb | 15.2. rapporteur requests 0.5 + 0, which depends also on study conclusions | 23.4. rapporteur: 0 TUs in Q3
| R16 WI N10_PGWReg |  | 2019-06-01 |  |  |  | 80 | 100 |  | 0 | 0.5 | 0 | [14 empty] | 0.5 | [9 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 28.11. Rapporteur: conclude in Jan and do related normative work in Feb | 15.2. rapporteur requests 0.5 + 0, which depends also on study conclusions | this is a small R16 WI where WI and CRs are cretaed together within a plenary cycle
| R16 WI IAB CN support |  | 2020-03-01 |  |  |  | 80 | 100 |  | #DIV/0! | 0 | 0 | [24 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 28.11. Rapporteur: conclude in Jan and do related normative work in Feb | 15.2. rapporteur requests 0.5 + 0, which depends also on study conclusions
| R17 FS_ID_UAS-SA2 | 20 | 2020-03-01 | [6 empty] | 0 | 7 | 0 | [16 empty] | 2 |  | #135: 2; #136: 1.5; #137: 1.5 |  | 7.5.18 initial estimates by rapporteur to be | 13.8.18 rapporteur considers to un-pause in Q4; reducing earlier requested budget | 28.11. rapporteur input: no work in Q1 | 7.2. rapporteur requests 2 + 2 + 2 | 26.4. rapporteur: 2 TUs each #134/135 and 1..2 each #136/137 for finalisation in Q1
| R17 FS_MUSIM | 23 | 2020-03-01 | [6 empty] | 0 | 4.5 | 0 | [16 empty] | 1.5 | [11 empty] | 11.2. rapporteur requests 1 + 1.5 | 18.4. rapporteur: 1,5 TUs in Q3 + 3*1 TUs until finalisation | bar: #135 to #136; #137
| R17 FS_enh_EC Edge Comp | 32 | 2020-03-01 | [6 empty] | 0 | 9.5 | 0 | [16 empty] | 2 |  | #135: 2.5; #136: 2.5; #137: 2.5 | [5 empty] | 24.4. rapporteur: 2 TUs in Q3 + 3*2,5 TUs until finalisation in Q1
| R17 FS_SB_SMS | 13 | 2019-12-01 | [6 empty] | 0 | 3 | 0 | [16 empty] | 1 |  | #135: 0.5; #136: 0.5; #137: 1 | [5 empty] | 26.4. rapporteur: 1 TUs in Q3 + 2 TUs until finalisation in Q4
| R17 FS_5G_ProSe | 27 | 2020-06-01 | [6 empty] | 0 | 17 | 0 | [16 empty] | 2 |  | 3 | 3 |  | 3 | 3 | 3 | [5 empty] | 19.4. rapporteur: 2 TUs in Q3 + 3 TUs per meeting until finalisation in Q2
| R17 FS_UPCAS UPF enhSBA | 14 | 2020-03-01 | [6 empty] | 0 | 10 | 0 | [16 empty] | 2 |  | 2 | 2 | 2 | 2 | [7 empty] | 23.4. rapporteur: 2 TUs every meeting until finalisation in Q1
| R17 FS_5MBS | 24 | 2020-06-01 | [6 empty] | 0 | 12 | 0 | [16 empty] | 2 |  | 2 | 2 |  | 2 | 2 | 2 | [5 empty] | 25.4. rapporteur: 2 TUs every meeting until finalisation in Q2
| R17 FS_UUI5 usage ID | 9? | 2020-06-01 | [6 empty] | 0 | 11 | 0 | [16 empty] | 1 |  | 2 | 2 | 1 | 1 | 2 | 2 | [5 empty] | 19.4. rapporteur: 1 TUs in Q3 + about TUs per meeting until finalisation in Q2
| R17 FS_5G-enTV | 8? | 2020-06-01 | [6 empty] | 0 | 6 | 0 | [16 empty] | 1 | [12 empty] | 23.4. rapporteur: 1 TU per meeting until finalisation in Q2 | bar: #135 to #136; #137 to #139
| R17 FS_5G_ICS interact. cloud | 8? | 2020-06-01 | [6 empty] | 0 | 6 | 0 | [16 empty] | 1 | [12 empty] | 7.5. rapporteur: 1 TU per meeting until finalisation in Q2 | bar: #135 to #136; #137 to #139
| R17 FS_eUEPO enh UE policy | 11? | 2020-03-01 | [6 empty] | 0 | 7 | 0 | [16 empty] | 1 |  | #135: 2; #136: 2; #137: 2 | [5 empty] | 18.4. rapporteur: 1 TUs in Q3 + 3*2 TUs until finalisation in Q1
| Maint 5.1 / 6.1 on 5GS |  |  | 98 | 100 |  |  |  |  | 112.5974 | 77 | 86.7 | 12 | 15 | 12 | 15 | 10 | 13.7 | 10 | 11.5 | 8 | 9 | 8 | 9.3 | 6 | 8.2 | 6 |  | 5 | 5
| Maint 5.1 / 6.1 | [11 empty] | 2 | 1.5 | 2 | 1 | 2 | 2 | 2 | 1.3 | 1 | 0.7 | 1 | 0.4 | 1 | 1 | 1 |  | 2 | 2
| Maint 5.2 / 6.2 | [11 empty] | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  |  |  |  | 0.1 |  | 0.7 |  |  | 1 | 1
| Maint 5.3 / 6.3 | [11 empty] | 0 |  | 0 |  | 0 |  | 0
| Maint 5.4 / 6.4 | [11 empty] | 0.5 |  | 0.5 | 0.2 | 0.5 | 1 | 0.5 | 0.2 |  | 0.2 |  | 0.4 |  | 0.3 |  |  | 1 | 1
| TEI16 EPS RFSPext | [8 empty] | 100 | 0.5 | 0.5 | [8 empty] | [0,5] |  | 0.5 | 0.5
| TEI16 EPS EtherType | [8 empty] | 120 | 1 | 1.2 | [8 empty] | [1] |  | 0.5 | 0.5 | 0.5 | 0.7
| TEI16 slice based overload control | [8 empty] | 40 | 1 | 0.4 | [12 empty] | 0.5 | 0.4 | 0.5
| TEI16 Monitoring Event Config | [8 empty] | 40 | 1 | 0.4 | [12 empty] | 0.5 | 0.4 | 0.5
| TEI16 PCF selection | [8 empty] | 50 | 1 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5
| TEI16 on EATF | [8 empty] | 100 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5
| TEI16 serialisation RDS | [8 empty] | 0 | 0.5 | 0 | [14 empty] | 0.5
| sum | [11 empty] | 16 | 17.5 | 16 | 16.9 | 14 | 17.2 | 15 | 14.3 | 40.5 | 41.2 | 42.5 | 44.9 | 43 | 47.8 | 43.3 | 0 | 55 | 33 | 31.5 | 30 | 5 | 25 | 10 | 10
There should be not more than 42 planned TUs!