## Sheet1
| SA WG2 Meeting #134 | [10 empty] | S2-1908590
June 24-28, 2019, Sapporo, Japan
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Endorsement
Agenda Item: 7.2
Work Item / Release: All / Rel-15 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[7 empty] | Jun, 19 | Oct, 19 | Nov, 19 | Jan, 20 | Feb, 20 | Apr, 20 | May, 20 | Jul, 20 | Aug, 20
[5 empty] | Target | Total TU | #134 | #135 | #136 | #136AH | #137 | #138 | #139 | #139AH | #140
|  | Title | Rapporteur | WID | date | Estimate | Req | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan
Rel-15/Rel-16 maintenance
Maint 5.1 / 6.1 | bar: #135 to #139; #140
Maint 5.2 / 6.2 | bar: #135 to #139; #140
Maint 5.3 / 6.3
Maint 5.4 / 6.4 | bar: #135 to #139; #140
| Maint 5GS_ph1 | [6 empty] | 5 | 5 | 4 | 4 | 3 | 3 |  | 2
| Maint other (URLLC, eNS, RACS, eIMS5G, UDCOM, ETSUN) | [6 empty] | 3 | 3 | 2 | 2 | 1 | 1 |  | 1
| Sum | [6 empty] | 11 | 11 | 9 | 9 | 7 | 7 |  | 6
Rel-16 maintenance
| eV2XARC | [5 empty] | #135: 2; #136: 2; #136AH: 1; #137: 1
| ATSSS | [5 empty] | #135: 1.5; #136: 1.5; #136AH: 1; #137: 1
| 5WWC | [5 empty] | #135: 1.5; #136: 1.5; #136AH: 1; #137: 1
| 5G_CIoT | [5 empty] | #135: 2; #136: 2; #136AH: 1; #137: 1
| Vertical_LAN | [5 empty] | #135: 2; #136: 2; #136AH: 1; #137: 1
| eNA | [5 empty] | #135: 2; #136: 1.5; #136AH: 1; #137: 1
| eLCS | [5 empty] | #135: 1; #136: 1; #136AH: 0.5; #137: 0.5
| eSBA | [5 empty] | #135: 1.5; #136: 1.5; #136AH: 0.5; #137: 0.5
| Rel-16 Maint (combined) | [5 empty] | #138: 4; #139: 4; #140: 3
| Sum | [6 empty] | 13.5 | 13 | 7 | 7 | 4 | 4 |  | 3
Rel-16 Alignment
| IAB | [6 empty] | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
| MT EDT | [6 empty] | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
| Sum | [6 empty] | 1 | 1 | 0 | 0 | 0 | 0 |  | 0
Buffer (TEI17, overflow, other)
| Buffer | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 |  | 3
Total Sum | [7 empty] | 28.5 | 28 | 19 | 19 | 14 | 14 |  | 12
Rel- 17 Study/Work items
| FS_5GSAT_ARCH | Study on architecture aspects for using satellite access in 5G | Cyril Michel (Thales) | SP-181253 | 2019-09-01 | 3 | bar: #134 to #136
| FS_eNA_ph2 | Study on Enablers for Network Automation for 5G - phase 2 | Xiaobo Wu (Huawei), Aihua Li (China Mobile) | SP-190557 | 2020-03-01 | 11 + 9 |  | 2 | 3 | 3 | 3 | 3 | 3 |  | 3
| FS_eNPN | Study on enhanced support of Non-Public Networks | Peter Hedman (Ericsson) | SP-190453 | 2020-03-01 | 7 + 3.5 |  | 2 | 2 | 1.5 | 1.5 | 1 | 1.5 |  | 1
| FS_5GLAN enh | Study on enhancement of support for 5G LAN-type service | Runze Zhou (Huawei) | SP-190454 | 2020-03-01 | 7 + 7 |  | 2 | 2 | 2 | 1 | 2 | 2 |  | 3
| FS_eATSSS | Study Extended Access Traffic Steering, Switch and Splitting support in the 5G system architecture | Tricci So (ZTE) | SP-190558 | 2020-06-01 | 9 + 6 |  | 1 | 2 | 0 | 2 | 2 | 2 |  | 2 | 2 | 2
| FS_eLCS_ph2 | Study on Enhancement to the 5GC LoCation Services - Phase 2 | Ming Ai (CATT) | SP-190452 | 2020-03-01 | 8 + 6 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
| FS_5WWC_enh | Study on enhancement of support for 5WWC | Huan Li (Huawei) | SP-190562 | 2020-06-01 | 10 + 8 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 3 | 3
| FS_eIMS5G | Study on Enhanced IMS to 5GC Integration | Joul, Chris (T-Mobile USA) | SP-190440 | 2020-03-01 | 4 + 3 | bar: #134 to #139; #140
| WI FLADN | Supporting Flexible Local Area Data Network | Hyunsook Kim (LG Electronics) | SP-190563 | 2019-12-31 | 1 | #138: 0.5; #139: 0.5
| FS_AAI_LTE_NR | Study on Application Awareness Interworking between LTE and NR | Biao Long (China Telecom) | SP-190543 | 2019-12-31 | 3 + 2 | 0 | 1 | 1 | 1 | 1 | 1
| FS_NG_RTC | Study on system architecture for next generation real time communication services | Yi Jiang (China Mobile) | SP-190444 | 2020-03-01 | 4.5 + 2 | 0 | 1 | 1.5 | 1 | 1 | 1 | 1
| FS_ID_UAS-SA2 | Study on supporting UAS Connectivity, Identification, and Tracking | Stefano Faccin (Qualcomm) | SP-181114 | 2020-03-01 | 8 + 6 | 0 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
| FS_MUSIM | Study on system enablers for multi-USIM devices | Sašo Stojanovski (Intel) | SP-190248 | 2020-03-01 | 5 + 2 | 0 | 1 | 1.5 | 1.5 | 1 | 1 | 1
| FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | Hui Ni (Huawei), Changhong Shan (Intel) | SP-190185 | 2020-03-01 | 10 + 9 | 0 | 2 | 2 | 2 | 2 | 2 | 3 |  | 3 | 3
| FS_SB_SMS | Study on service-based support for SMS in 5GC | George Foti (Ericsson) | SP-190184 | 2019-12-01 | 3 + 1 | #134: 0; #135: 1; #136: 1; #136AH: 1; #137: 1
| FS_5G_ProSe | Study on system enhancement for Proximity based Services in 5GS | Qiang Deng (CATT), Jianhua Liu (OPPO) | SP-190443 | 2020-06-01 | 17 + 12 | 0 | 2 | 3 | 3 | 3 | 3 | 3 |  | 4 | 4 | 4
| FS_UPCAS | Study on UPF enhancement for control and SBA | Dan Wang (China Mobile) | SP-190187 | 2020-03-01 | 10 + 7 | 0 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 3
| FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | Dario Serafino Tonesi (Huawei) | SP-190442 | 2020-06-01 | 16 + 10 | 0 | 2 | 3 | 3 | 3 | 3 | 2 |  | 3 | 3 | 4
| FS_UUI5 | Study on the Usage of User Identifiers in the 5G System | Michael Starsinic (Convida Wireless) | SP-190450 | 2020-06-01 | 11 + 4 | 0 | 2 | 2 | 1 | 2 | 2 | 2 |  | 2 | 2
| 5G_AIS | 5G System Enhancement for Advanced Interactive Services | Lei Yixue (Tencent) | SP-190564 | 2020-03-01 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| FS_eUEPO | Study on enhancement of 5G UE Policy | Changhong Shan (Intel) | SP-190449 | 2020-03-01 | 9 + 6 | 0 | 1 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2
| sum | [5 empty] | 1 | 30 | 36 | 31 | 32.5 | 33.5 | 33 |  | 33 | 22 | 10
Rel- 17 Study/Work items (Not yet approved by TSG SA)
| FS_eNS_ph2 |  |  |  | 2020-03-01 | 6 + 3 |  | 1 | 1 | 2 | 2 | 1 | 1 |  | 1
| FS_eV2XARC_ph2 |  |  |  | 2020-06-01 | 4 + 2 | [9 empty] | 1 | bar: #136AH to #139; #140
| FS_MPS |  |  |  | 2020-06-01 | 4 + 2 |  | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 1 |  | 1 | 1
| FS_IIoT |  |  |  | 2020-03-01 | 6 + 3 |  | 1 | 1 | 2 | 2 | 1 | 1 |  | 1
| sum | [6 empty] | 3 | 2.5 | 5.5 | 5.5 | 3.5 | 4 |  | 4 | 2
NOTE: On Rel-17 Study/Work items tables above, black numbers denotes TU estimates for the study phase while red numbers denotes TU estimates for the normative work.