## Slide 1: FS_5G_ProSe Status Report
Deng Qiang (CATT), Jianhua Liu (OPPO)

## Slide 2: FS_5G_ProSe Status at SA#87
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 30% > 55% | Jun, 20 | SP-190443
Progress since SA#86:
  Only one SA2 WG meeting in Q1
  Total TUs requested for Study Phase in 2020 is 7. 2 TUs are used and 5 TUs are remaining.
  New solutions and solution updates are captured into TR 23.752, and for all key issues we have solutions on table.
  RAN impacts and dependencies:
  All the key issues may have RAN impact and coordination with RAN may be necessary.
Contentious Issue:
  Whether support of service continuity for UE-to-Network Relay in Release 17 needs SA#87 decision..
Next steps:
  Consolidate the solutions, make overall evaluation and conclusions for each key issue at Q2.
  For UE-to-Network Relay and UE-to-UE Relay, consolidate technical issues and conclusions on SA2 aspect, pending RAN-related issues and wait for RAN progress.

## Slide 3: FS_5G_ProSe status after SA2#136AH (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 30% > 55% | Jun, 20 | SP-190443
General
  FS_5G_ProSe TR 23.752 v0.3.0 is available here.
  Total TUs requested for Study Phase in 2020 is 7. 2 TUs are used and 5 TUs are remaining.
  New solutions and solution updates are captured into TR 23.752, and for all key issues we have solutions on table.
Key Issue 4 (UE-to-UE Relay):
  4 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#4 is 4.
  Next Steps: Consolidate the solutions and make overall evaluation and conclusions on SA2 aspect, wait for RAN NR sidelink relay SI progress.
Key Issue 5 (Path Selection):
  1 new solution was agreed for inclusion in the TR. Total number of solutions for KI#5 is 1.
  Next Steps: Resolve the ENs in this solution, discuss other solutions if available and make evaluation and conclusion.
Key Issue 7 (Charging):
  3 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#7 is 3.
  Solutions can be categorized as AMF-based and SMF-based solutions.
  Next Steps: Resolve the ENs in these solutions, discuss other solutions if available and make overall evaluation and conclusion.
Key Issue 8 (Service Authorization):
  2 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#8 is 2.
  Next Steps: Resolve the ENs in these solutions, discuss other solutions if available and make overall evaluation and conclusion.

## Slide 4: FS_5G_ProSe status after SA2#136AH (2/3)
Key Issue 1 (Direct Discovery):
  For DDNMF location, UP-based and CP-based were agreed for inclusion in the TR.
  For UE-to-Network discovery, 1 solution was agreed for inclusion in the TR.
  Total number of (related) solutions for KI#1 are 7.
  Next Steps: Consolidate the solutions and make overall evaluation and conclusions.
Key Issue 2 (Direct Communication):
  2 new solutions on ProSe QoS were agreed for inclusion in the TR.
  1 new solution on group communication was agreed for inclusion in the TR.
  Total number of (related) solutions for KI#2 is 5.
  Next Steps: Consolidate the solutions and make overall evaluation and conclusions.
Key Issue 3 (UE-to-Network Relay):
  Solutions for Layer-3 Relay (sol#6) and Layer-2 Relay (sol#7) were captured in the TR.
  Next Steps: Consolidate technical issues and conclusions on SA2 aspect, pending RAN-related issues and wait for RAN progress.

## Slide 5: FS_5G_ProSe status after SA2#136AH (3/3)
  RAN impacts and dependencies:
  All the key issues may have RAN impact and coordination with RAN may be necessary.
Contentious Issue:
  UE-to-Network Relay and UE-to-UE Relay regarding Layer-2 or Layer-3 Relay depends on RAN decision.
Focus for the Next Meeting (SA2#138):
  Consolidate the solutions, make overall evaluation and conclusions for key issues whose solutions are deemed stable at SA2#138.
  For UE-to-Network Relay and UE-to-UE Relay, consolidate technical issues and conclusions on SA2 aspect, pending RAN-related issues and wait for RAN progress.
Overall Plan:
  SA2#138 (Apr) & SA2#139 (May): Consolidate the solutions, make overall evaluation and conclusions for each key issue. Submit TR 23.752 to SA#88 plenary (June 2020) for one-stop approval. Agree a WID.