## Slide 1: FS_eNPN Status Report
Peter Hedman
Ericsson

## Slide 2: FS_eNPN status after SA2#139E (1/2)
General
  FS_eNPN TR 23.700-07 v0.4.0 is available here.
  Total TUs requested for Study Phase in 2020 is 5. 2 TUs and one e-meeting is used.
  Key Issues #4 (UE Onboarding and remote provisioning) updated (re-structured and scope clarified).
Key Issue 1 (Enhancements to Support SNPN along with credentials owned by an entity separate from the SNPN):
  4 existing solutions updated, and 5 new added solutions were agreed for inclusion in the TR. Total number of solutions for KI#1 is 9.
  Solutions identified with a need to confirm network selection aspects with CT1 and SA1.
  Potential need to get clarification from GSMA identified for one solution.
  Next Steps: Next meeting (SA2#140E) will focus on resolving open issues/ENs, evaluation and attempts to reach interim conclusions (as far as possible).
Key Issue 2 (NPN support for Video, Imaging and Audio for Professional Applications (VIAPA))
  6 new added solutions were agreed for inclusion in the TR, and 2 updated solutions for KI#1 now also indicated as addressing KI#2.
  Next Steps: Next meeting (SA2#140E) will focus on resolving open issues/ENs, evaluation and attempts to reach interim conclusions (as far as possible).
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 35% -> 55% | Jun, 20 -> Sep, 20 | SP-200094

## Slide 3: FS_eNPN status after SA2#139E (1/2)
Key Issue 3 (Support of IMS voice and emergency services for SNPN)
  8 new solutions were agreed for inclusion in the TR, i.e. in total 8 solutions for key issue.
  Next Steps: Next meeting (SA2#140E) will focus on resolving open issues/ENs, evaluation and attempts to reach interim conclusions (as far as possible).
Key Issue 4 (UE Onboarding and remote provisioning)
  Updated key issue description (re-structured and scope clarified).
  Received LS from SA1 that clarified the requirements, especially for PNI-NPN.
  Agreed 14 new solutions for inclusion in the TR, and updated 2 of the existing 3 solutions. In total 17 solutions for key issue.
  Next Steps: Next meeting (SA2#140E) will focus on resolving open issues/ENs, evaluation and attempts to reach interim conclusions (as far as possible).
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 35% -> 55% | Jun, 20 -> Sep, 20 | SP-200094

## Slide 4: FS_eNPN status after SA2#139E (2/2)
  RAN impacts and dependencies:
  Key issues 1, 2 and 4 may potentially lead to solutions with RAN impact and may require RAN coordination.
  Impacts are SIB related for solutions related to Key issues 1 and 4, new RRC indications for solutions related to Key issues 4 and additional NGAP impacts for solutions related to Key issues 2 and 4
SA3 dependencies
  One SA3 dependencies identified for solutions related to key issue 1 and LS sent to SA3 in S2-2004385, but also other SA3 dependencies identified by ENs for solutions related to key issue 1, 3 and 4. One solution (#17) for key issue 2 has security related ENs, but FFS whether to be resolved by SA2.
Contentious Issue:
  None
Focus for the Next Meeting (SA2#140E):
  Organize a conference call before SA2#140E to discuss Way Forward proposals.
  Resolve major open issues for the solutions and find way forward for concluding the key issues (i.e. evaluations and attempt interim conclusions as far as possible).
  If show-stoppers found e.g. related to other WG dependencies that cannot be resolved by SA2, send LS with explicit question
  Find a way to resolve RAN as well as SA3 dependencies as given the delayed start of eNPN related work in RAN and SA3.
Overall Plan:
  SA2#140E (Aug): Last meeting for new solutions, complete description of solutions. Initial evaluation and interim conclusions. Send TR for information. Based on input from RAN2/3 and SA3, new solutions/options may be proposed after SA2#140E.
  SA2#141E (xxx): Final evaluation and conclusions. Submit TR 23.700-07 to SA#90 plenary for approval. Agree a WID.
Risks:
  Completion of the study may not be possible in Q3 for all key issues, due to RAN and SA3 dependencies

## Slide 5: FS_eNPN Status at SA#88
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 35% -> 55% | Jun, 20 -> Sep, 20 | SP-200094
Progress since SA#87-e:
  Clarified KI#4
  Existing solutions updated and 33 new solutions added. TR 23.700-07 now includes 40 solutions and there are solutions for all Key Issues agreed to be prioritized for Rel-17 at SA#86
  SA1 clarified in LS reply (cc: SA, CT1, SA3, CT6) the scope of provisioning of UE credentials, related to KI#4
  Dependencies to SA3 identified by Editor’s notes and LS sent to SA3 for one of the aspects
  Dependencies to SA1 and CT1 identified by Editor’s notes regarding network selection and roaming/service continuity
  RAN impacts and dependencies:
  RAN impact depends on the conclusions of the KIs (e.g. KI#1, KI#2, KI#4).
Next steps:
  Complete description of existing solutions, and add any new solutions
  Evaluation and agree on conclusions
  Target Completion: There is risk that several Key Issues will not conclude by Sep, 20 due to RAN/SA3 dependencies, and due to TU under-estimation.

## Slide 6: FS_eNPN status after SA2#136AH (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 15% > 35% | June, 20 | SP-190453
General
  FS_eNPN TR 23.700-07 v0.3.0 is available here.
  Total TUs requested for Study Phase in 2020 is 5. 2 TUs are used and 3 TUs are remaining.
  Key Issues #5 (Support for equivalent SNPNs) and #6 (Support of non-3GPP access for SNPN services) marked as not addressed within Rel-17 timeframe as a result of down-scoping exercise.
Key Issue 1 (Enhancements to Support SNPN along with credentials owned by an entity separate from the SNPN):
  One solution updated, and 3 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#1 is 4.
  Next Steps: Next meeting (SA2#138) should be the last meeting to propose new solutions for KI. Proceed with evaluations and (interim) conclusions.
Key Issue 2 (NPN support for Video, Imaging and Audio for Professional Applications (VIAPA))
  KI clarified
  No solutions focused on this KI could be handled due to lack of time.
Key Issue 3 (Support of IMS voice and emergency services for SNPN)
  No contributions focused on this KI could be handled due to lack of time.
Key Issue 4 (UE Onboarding and remote provisioning)
  Sent LS to SA1 (cc: SA, CT1, SA3, CT6) asking clarifications from SA1
  Agreed 3 solutions for inclusion in the TR.

## Slide 7: FS_eNPN status after SA2#136AH (2/2)
  RAN impacts and dependencies:
  Key issues 1 and 4 may potentially lead to solutions with RAN impact and may require RAN coordination.
  RAN impacts due to key issues 2 and 3 are still unknown
  RAN intended to discuss NPN enhancements related work at TSG RAN#87
Contentious Issue:
  Scope for UE provisioning in relation to IMSI and AKA (see Q1 in S2-2001729)
  Scope for KI#4 in relation to PNI-NPN (see Q2 and Q3 in S2-2001729)
Focus for the Next Meeting (SA2#138):
  New solutions for key issues 2 and 3
  Solutions and possibly way forward for key issues 1 and 4
  Find a way to resolve RAN as well as SA3 dependencies as given the delayed start of eNPN related work in RAN and SA3.
    Collect open issues / questions and seek RAN WGs’ and SA3 feedback with LS OUT from SA2#138.
  Any new Key Issue will be low priority unless supported by large number of companies.
Overall Plan:
  SA2#137E (Feb): Agree revised SID
  SA2#138 (Apr): Complete description of existing solutions, and add new solutions (i.e. all submitted solutions should be complete). Start initial evaluation, and possibly interim conclusions.
  SA2#139 (May): Final evaluation and conclusions. Submit TR 23.700-07 to SA#87 plenary for approval. Agree a WID.
  SA2#140 (Aug):