## Slide 1: FS_ATSSS_Ph2 WG2 Status Report
Tricci So
ZTETX Inc.

## Slide 2: FS_ATSSS_Ph2 after SA2#139E

## Slide 3: 2.4) Rel-17 Study/Work (12/12)
Progress since SA#87E:
  Latest TR 23.700-93v1.1
  3 KIs have been introduced.
  8 new solutions have been proposed to address various KIs.
  Strong dependency on IETF progress on QUIC/MP-QUIC development for some proposed solutions. These solutions require tighter collaboration between 3GPP and IETF to address SA2 requirements in a timely manner
RAN impacts or dependencies:
    None identified.
Next steps:
  Complete solution, evaluation and conclusion(s) for each Key Issue.
  Target Completion: There is risk that study item will not conclude by Sep, 20 due to IETF dependency dependencies.
WI Code | Work Item Title | WP | Target Date | WID#
FS_ATSSS_Ph2 | Study on Access Traffic Steering, Switch and Splitting support in the 5G system architecture Phase 2 | 0% -> 35% | Jun, 20 -> Sep, 20 | SP-200095

## Slide 4: FS_ATSSS_Ph2 status after SA2#139E (1/4)
Solutions | Title | Key Issue(s)
#1 | QUIC-LL Steering Functionality | 2
#2 | New steering mode – Autonomous steering mode | 1
#3 | New steering mode – Autonomous steering mode with advanced PMF | 1
#4 | New steering mode – Redundant steering mode | 1
#5 | Replacing 3GPP access leg of MA-PDU Session with PDN connection in EPC | 3
#6 | MPQUIC-LL Steering Functionality | 2
#7 | Proposed solution based on MP-QUIC | 2
#8 | Proposed solution based on QUIC | 2

## Slide 5: FS_ATSSS_Ph2 status after SA2#139E (2/4)
  RAN and/or IETF impacts and dependencies:
  None for RAN
  Strong dependency on IETF progress on QUIC/MP-QUIC development for some proposed solutions. These solutions require tighter collaboration between 3GPP and IETF to address SA2 requirements in a timely manner
Contentious Issue:
  None
Focus for the Next Meeting (SA2#140E):
  Complete solution, prepare evaluation.
  Last meeting to accept new solutions
  May prioritize KI#s to ensure sufficient time to conclude the KI#s that are relative stable
  Target Completion: Study may be slipped and be completed after Sep, 20.
Overall Plan:
  After SA2#139E (May2020): Organize 2 CCs to review any new and revised solutions, to work on merging solutions, and to prepare for the evaluation and conclusion for each KI .
    NOTE-1: KI#1 may have none or more than one solution dependent for which proposed steering mode(s) are to support
  SA2#140E (Aug2020): Solution clean up to finalize any existing solutions. It is the last meeting for any new solution for all KIs. Start the evaluation.
  SA2#141E (Oct.2020): Complete evaluation and conclusions. Submit TR 23.700-93 to SA#90E plenary for approval.

## Slide 6: FS_ATSSS_Ph2 status after SA2#139E (3/4)
Key Issue | Key Issue Descriptions & Status | Associated Solutions
#1 | Additional Steering Methods | #2, #3, #4,
 | 1 solution proposes a new steering mode, called Autonomous steering mode, provides to both the UE and the UPF flexibility on the traffic splitting control when two accesses are applicable for this traffic. 1 solution proposes to enhance the PMF as defined in Rel-16 needs to support the measurement according to the target QoS requirements of the traffic. 1 solution proposes new steering mode to allow the traffic transmitted via 3GPP and non-3GPP accesses in a redundant way to achieve the lowest latency and lower the loss rate. Status: Average of solutions’ completeness is ~30% External Dependency (e.g. RAN, IETF): None Contentious Issue: None Next Steps: Complete solutions and start the evaluation and conclusion Target Completion: Study most likely will not be completed by Sep. 20, will need one more meeting cycle | 

## Slide 7: FS_ATSSS_Ph2 status after SA2#139E (4/4)
#3 | Supporting MA PDU with 3GPP access leg over EPC and Non-3GPP access leg over 5GC | #6
 | 1 solution proposes to enable a capable UE and network to replace the 3GPP access leg of a normal MA PDU Session with a PDU connection in EPC, while keeping the non-3GPP access leg in 5GC Status: Average of solutions’ completeness is ~35% External Dependency (e.g. RAN, IETF): None Contentious Issue: None Next Steps: Complete solution and to align the similar existing solution that supports 5G-RG, start the evaluation and conclusion Target Completion: Study most likely will not be completed by Sep. 20, will need one more meeting cycle, but the normative work should be able to complete by Dec.2020. | 
#2 | Additional Steering Functionalities | #1, #6, #7, #8
 | 1 solution proposes a new ATSSS steering functionality referred as QUIC-Low Layer (QUIC-LL) because it operates below the IP layer (such as ATSSS-LL) by leveraging QUIC as the transport tunnel between UE and its serving UPF. 1 solution proposes a new ATSSS steering functionality referred as MPQUIC-Low Layer (MPQUIC-LL) because it operates below the IP layer (such as ATSSS-LL) by leveraging MPQUIC as the transport tunnel between UE and its serving UPF. 1 solution proposes a new ATSSS steering functionality, MPQUIC, with the similar principle as MPTCP, but for enabling traffic splitting support for UDP traffic which was not explicitly supported by ATSSS-LL in Rel-16 1 solution proposes a new ATSSS steering functionality, QUIC, to be combined with ATSSS-LL transport to enable traffic splitting support for UDP traffic which was not explicitly supported by ATSSS-LL in Rel-16 Status: Average of solutions’ completeness is ~35% External Dependency (e.g. RAN, IETF): Strong dependency on IETF progress on QUIC/MP-QUIC development for some proposed solutions. These solutions require tighter collaboration between 3GPP and IETF to address SA2 requirements in a timely manner. Contentious Issue: TBD – if all solutions are determined as the viable new steering functionalities, then show hands may be needed for final conclusion. Next Steps: Complete solutions, start the evaluation and conclusion Target Completion: Study most likely will not be completed by Sep. 20, will need one more meeting cycle |