## Slide 1: SA2 Q3/Q4 Work Planning
Puneet Jain
SA2 Chairman

## Slide 2: SA2 Meeting Planning
C
H
N
E
W
Y
E
A
R
C
H
G
O
L
D
E
N
W E
E
K
W32
October
December
September
August
W33
W34
W35
W36
W37
W38
W39
W40
W41
W42
W43
W44
W45
W46
W47
W48
W49
W50
W51
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
November
January
February
March
TSG
TSG
WG
WG
TSG
WG
WG
WG
Old obsolete
T
H
A
N
K
S
G
I
V
I
N
G
TSG
TSG
TSG
WG
Option 2
WG
#141E
TSG
TSG
TSG
WG
Option 1
WG
#141E
#142E
SA2#140E
SA2#140E
Proposal: Agree on Option 1
RAN 2/3
RAN 1

## Slide 3: SA2#140E Dates/Agenda
Docs request | 13 Aug 2020 (Thursday) | 2400 UTC
Docs submission | 13 Aug 2020 (Thursday) | 2400 UTC
Start of e-meeting | 19 Aug 2020 (Wednesday), CC#1 | 0000 UTC
Deadlines#1 | Applies to AI# 4.X, 5.X, 7.X | 
Revisions by | 24 Aug 2020 (Monday) | 1700 UTC
Final Comments | 25 Aug 2020 (Tuesday) | 1700 UTC
Close of AI# 4.X, 5.X, 7.X | 26 Aug 2020 (Wednesday), CC#2 | 1700 UTC
Upload Approved docs | 27 Aug 2020 (Thursday), CC#3 | 1700 UTC
Deadlines#2 | Applies to AI# 8.X, 9.X | 
Revisions | 28 Aug 2020 (Friday) | 1700 UTC
Final Comments | 31 Aug 2020 (Monday) | 1700 UTC
Close of e-meeting | 01 Sep 2020 (Tuesday), CC#4 | 1700 UTC
Upload Approved docs | 02 Sep 2020 (Wednesday) | 1700 UTC
Agenda:
  All agenda items (except 6.X, TEI17)
  LS on all Agenda items
  8.X (All Rel-17 SIDs + 5GSAT_ARCH WID)
Single Docs Request/Submission deadline for all Agenda Items
Meeting starts on 19-Aug-2020 for all Agenda Items
Deadlines on providing Revisions/Final comments -
  Deadline#1 applies to AI# 4.X, 5.X, 7.X
  Deadline#2 applies to AI# 8.X, 9.X
General guidance on Rel-17 SIDs :
  No New KI
  Last meeting to bring any new solutions. New solution proposals should be reasonably complete.
  Start solution evaluations/interim conclusions.
  Draft LS to other WGs (e.g. RAN2/3) for feedback.
  Draft CR for 5GSAT_ARCH WID

## Slide 4: SA2#141E Dates/Agenda
Docs request | 02 Oct 2020 (Friday) | 2400 UTC
Docs submission | 02 Oct 2020 (Friday) | 2400 UTC
Start of e-meeting | 12 Oct 2020 (Monday), CC#1 | 0000 UTC
Deadlines#1 | Applies to AI# 4.X, 5.X, 6.X, 7.X | 
Revisions by | 14 Oct 2020 (Wednesday) | 1700 UTC
Final Comments | 15 Oct 2020 (Thursday) | 1700 UTC
Close of AI# 4.X, 5.X, 6.X, 7.X | 16 Oct 2020 (Friday), CC#2 | 1700 UTC
Upload Approved docs | 19 Oct 2020 (Monday), CC#3 | 1700 UTC
Deadlines#2 | Applies to AI# 8.X, 9.X | 
Revisions by | 21 Oct 2020 (Wednesday) | 1700 UTC
Final Comments | 22 Oct 2020 (Thursday) | 1700 UTC
Close of e-meeting | 23 Oct 2020 (Friday), CC#4 | 1700 UTC
Upload Approved docs | 26 Oct 2020 (Monday) | 1700 UTC
Agenda:
  All agenda items (except TEI17)
  8.X (All Rel-17 SIDs + 5GSAT_ARCH WID)
Single Docs Request/Submission deadline for all Agenda Items
Meeting starts on 12-Oct-2020 for all Agenda Items
Deadlines on providing Revisions/Final comments -
  Deadline#1 applies to AI# 4.X, 5.X, 6.X, 7.X
  Deadline#2 applies to AI# 8.X, 9.X
General guidance on Rel-17 SIDs :
  No new solution. Merge of existing solutions to generated new merged solution is allowed.
  Focus on solution evaluations/interim conclusions. Conclusion should be achieved at least on KI with no RAN dependency.
  Draft any additional LS to other WGs (e.g. RAN2/3) for feedback.
  New WID proposal based on agreed conclusion(s).
  CRs for all TSG SA approved WID

## Slide 5: SA2#142E Dates/Agenda
Docs request | 06 Nov 2020 (Friday) | 2400 UTC
Docs submission | 06 Nov 2020 (Friday) | 2400 UTC
Start of e-meeting | 16 Nov 2020 (Monday), CC#1 | 0000 UTC
Revisions by | 18 Nov 2020 (Wednesday) | 1700 UTC
Final deadline | 19 Nov 2020 (Thursday) | 1700 UTC
Close | 20 Nov 2020 (Friday), CC#2 | 1700 UTC
Upload Approved docs | 23 Nov 2020 (Monday) | 1700 UTC
Agenda:
  Urgent LSs on all agenda items
  8.X (All Rel-17 SIDs + All Rel-17 WIDs)
  TEI17? (TBD)
Single Docs Request/Submission deadline for all Agenda Items. Meeting starts on 16-Nov-2020
General guidance on Rel-17 SIDs :
  No new solution. Merge of existing solutions to generated new merged solution is allowed.
  Only papers related to KI conclusion will be handled.
  After submission deadline moderated email discussion to merge conclusion paper (more details later)
  New WID proposal based on agreed conclusion(s).
General guidance on Rel-17 WIDs :
  CR for all TSG SA approved WIDs
  Draft CR for all SA2 approved WIDs

## Slide 6: Agenda Items
AI# | Topic
1 | Opening of the meeting
2 | Approval of the agenda
3 | Meeting Reports
4.X | General (Common issues and Incoming LSs)
5.X | Pre-Rel-17 Maintenance (excluding all 5G topics) NOTE: FASMO criterion will be strictly enforced.
6.X | Rel-15/Rel-16 Maintenance for 5G (only related to 5GS_Ph1 Work Item) NOTE: FASMO criterion will be strictly enforced.
7.X | Rel-16 Maintenance for 5G (excluding 5GS_Ph1) NOTE: FASMO criterion will be strictly enforced.
8.X | Rel-17 SIDs + WIDs
9.X | Project Planning and Management
10 | AOB
11 | Close of the Meeting

## Slide 7: Thank You !
Puneet Jain
Chairman of 3GPP SA2
puneet.jain@intel.com
www.3gpp.org