## Slide 1: FS_MUSIM Status Report
Sašo Stojanovski
Intel Corporation

## Slide 2: FS_MUSIM Status at SA#88
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 46% > 60% | Jun, 20 -> Sep, 20 | SP-200091
Progress since SA#87-e:
  14 new solutions agreed for inclusion in TR 23.761
  There are now 22 solutions in TR 23.761 on all the three prioritized key issues.
  RAN impacts and dependencies:
  All three key issues may potentially lead to solutions with RAN impact and may require RAN coordination
  Whether normative phase can be completed in Q4 depends on the interactions with RAN in Q4
Next steps:
  Complete description of existing solutions and add any new solutions
  Solution evaluation and conclusion
  Target Completion: There is risk that study item may not conclude by Sep, 20 as all of the KI have RAN dependencies.

## Slide 3: FS_MUSIM status after SA2#139E (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 46% > 60% | Jun, 20 -> Sep, 20 | SP-200091
General
  FS_MUSIM TR 23.761 v0.4.0 is available here.
Key Issue 1 (Handling of MT Service):
  5 new solutions were agreed in SA#139E and several solutions revised. Total number of KI#1 solutions is 10.
  Next Steps: SA2#140E meeting will focus on updating existing solutions to remove ENs, initial evaluations and interim conclusions (where possible). No newly proposed solutions for the basic functionality. Solution updates and optimizations for the case “on the same network” will be considered. Based on the initial evaluations and/or interim conclusions liaise with impacted groups (RAN2, RAN3 or SA3 identified thus far) with specific questions so that final evaluations and conclusions can be drawn in Q4.
Key Issue 2 (Enable Paging reception):
  8 new solutions were agreed in SA#139E. Total number of KI#2 solutions is 8. In addition, several solutions on KI#1 (e.g. #7, #12) indirectly address KI#2.
  Next Steps: SA2#140E meeting will be the last meeting for new solutions. Even though this KI has strong RAN dependency, companies are invited to attempt initial evaluation. Based on the initial evaluations liaise with RAN2/RAN3 with specific questions so that final evaluations and conclusions can be drawn in Q4.
Key Issue 3 (Co-ordinated leaving):
  1 new solution (which is a subset of an existing solution) was agreed in SA#139E. Total number of KI#3 solutions is 4.
  Next Steps: SA2#140E meeting will focus on updating existing solutions to remove ENs, initial evaluations and interim conclusions (where possible). No newly proposed solutions for the basic functionality. Based on the initial evaluations and/or interim conclusions liaise with impacted groups with specific questions so that final evaluations and conclusions can be drawn in Q4.

## Slide 4: FS_MUSIM status after SA2#139E (2/2)
  RAN impacts and dependencies:
  All three key issues may potentially lead to solutions with RAN impact and may require RAN coordination.
Contentious Issue:
  None
Focus for the Next Meeting (SA2#140E):
  Ahead of SA2#140E: Organize a conference call to discuss Way Forward proposals.
  During SA2#140E:
    Focus on resolving ENs, technically completing solutions, initial evaluations and interim conclusions (where possible).
    Focus on agreeing high-level principles (possibly stemming from multiple solutions) rather than updating individual solutions to make them « perfect »
    Based on the initial evaluations and/or interim conclusions liaise with impacted groups (RAN2, RAN3 or SA3 identified thus far) with specific questions so that final evaluations and conclusions can be drawn in Q4.
Overall Plan:
  SA2#140E (Aug-Sep): Initial evaluations and agree high-level principles. Submit TR 23.761 to SA#89 plenary for information.
  SA2#141 (Oct): Final evaluations and conclusions. Submit TR 23.761 to SA#90 plenary for approval.
Risks:
  Completion of the study may not be possible in Q3 for all key issues, due to RAN dependencies and meeting timings between SA2 and RAN.

## Slide 5: BACKUP Previous FS_MUSIM Status Report (S2-2001825) for information

## Slide 6: FS_MUSIM Status at SA#87
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 29% > 46% | Jun, 20 | SP-190248
Progress since SA#86:
  Only one SA2 WG meeting in Q1
  Total TUs requested for Study Phase in 2020 is 4.5. 1 TU is used and 3.5 TUs are remaining.
  Key Issue #4 (Emergency services) removed as a result of downscoping exercise.
  RAN impacts and dependencies:
  All three key issues may potentially lead to solutions with RAN impact and may require RAN coordination.
  RAN has delayed start on MUSIM (in Q3), SA2 need to finish FS_MUSIM by Q2.
Next steps:
  Find a way to resolve RAN dependencies given the delayed start (Q3) of MUSIM work in RAN. Collect open issues / questions and seek RAN WGs’ feedback with LS OUT from SA2#138.

## Slide 7: FS_MUSIM status after SA2#136AH (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 29% > 46% | Jun, 20 | SP-190248
General
  FS_MUSIM TR 23.761 v0.3.0 is available here.
  Total TUs requested for Study Phase in 2020 is 4.5. 1 TU is used and 3.5 TUs are remaining.
  Key Issue #4 (Emergency services) removed as a result of downscoping exercise.
Key Issue 1 (Handling of MT Service):
  2 new solutions were agreed for inclusion in the TR at SA2#136AH. Total number of solutions for KI#1 is 5.
  Next Steps: SA2#138 meeting should be the last meeting to propose new solutions for the basic functionality (i.e. other than optimizations). Proceed with initial solution evolutions and interim conclusions. Liaise with RAN on solution impacts so final evaluations and conclusions can be drawn.
Key Issue 2 (Enable Paging reception):
  No contributions focused on this KI could be handled due to lack of time. Solution #7 addresses this KI indirectly.
Key Issue 3 (Co-ordinated leaving):
  3 solutions were added at SA2#136AH. Solutions can be categorized as NAS-level and RRC-level solutions. RRC-level solution require feedback from RAN.
  Next Steps: SA2#138 meeting should be the last meeting to propose new solutions for the basic functionality (i.e. other than optimizations). Proceed with initial solution evolutions and interim conclusions. Liaise with RAN on solution impacts so final evaluations and conclusions can be drawn.

## Slide 8: FS_MUSIM status after SA2#136AH (2/2)
  RAN impacts and dependencies:
  All three key issues may potentially lead to solutions with RAN impact and may require RAN coordination.
  RAN has delayed start on MUSIM (in Q3), SA2 need to finish FS_MUSIM by Q2.
  No interleaving of RAN and SA2 meetings, which will make obtaining feedback quickly impossible (i.e. LSs sent from SA2#138 may not get a reply until SA2#140 in Q3, unless extraordinary steps are taken at SA2/RAN2 meetings).
Contentious Issue:
  None
Focus for the Next Meeting (SA2#138):
  Find a way to resolve RAN dependencies given the delayed start (Q3) of MUSIM work in RAN. Collect open issues / questions and seek RAN WGs’ feedback with LS OUT from SA2#138.
  Prioritize handling of contributions that complete the spectrum of possible RAN impacts. Specifically:
    Try to agree solutions on KI#2 that summarize the main RAN-impacting options.
    Clarify solutions in the TR that have significant RAN impact, but are not yet documented in sufficient detail (e.g. Solution #2).
  Any new Key Issue will be low priority unless supported by large number of companies. Optimizations for the case where multiple USIMs are served by the same network will be handled with low priority.
Overall Plan:
  SA2#138 (Apr): Complete description of existing solutions. Start initial evaluation. New solutions can still be proposed.
  SA2#139 (May): Final evaluation and conclusions. Submit TR 23.761 to SA#87 plenary for one-stop approval. Agree a WID.
Risks:
  Completion of the study may not be possible in Q2 for all key issues, due to RAN dependencies and meeting timings between SA2 and RAN.