## Slide 1: FS_ID_UAS_SA2 Status Report
Stefano Faccin
Qualcomm Incorporated

## Slide 2: FS_ID_UAS_SA2 Status at SA#88-e
Progress since SA#88-e:
  Minor update to architectural assumptions, several solutions merged, most solutions have detailed added to make evaluation more feasible. Five new solutions added, one being a merger of four existing ones.
  Initial set of conclusions on principles for solutions, covering KI#1 and KI#2, plus additional conclusions.
  RAN impacts and dependencies:
  One solution (#8) proposes porting to NR the LTE aerial features.
Next steps:
  Final evaluation and conclusion of what to progress towards a normative phase in Q4.
  The target completion date for the study is proposed to be moved to Dec 2020.
  Submit TR 23.754 to SA#90-e plenary for approval.
  Agree a WID.
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 50% > 70% | Jun, 20 -> Sep. 20 | SP-181114

## Slide 3: FS_ID_UAS_SA2 status after SA2#140E (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 50% > 70% | Jun, 20 -> Dec, 20 | SP-181114
General
  FS_ID_UAS_SA2 TR 23.754 v0.3.0 is available here.
  Architectural and reference architecture have been updated.
  Five new solutions added, one being the merger of four existing ones, for a total of 26 solutions.
  Several solution were merged and clarified.
Key Issue 1 (UAV identification) :
  9 solutions address KI#1.
  Initial principle conclusions were captured.
Key Issue 2 (UAV authorization by UTM)
  14 solutions address KI#2.
  Initial principle conclusions were captured.
Key Issue 3 ( UAV Controller identification and authorization/authentication):
  6 solutions address KI#3.
Key Issue 4 (UAV and UAV Controller tracking):
  8 solutions address KI#4.

## Slide 4: FS_ID_UAS_SA2 status after SA2#140E (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 50% > 70% | Jun, 20 -> Dec, 20 | SP-181114
Key Issue 5 (UAV authorization revocation and (re)authorization failures):
  9 solutions address KI#5.
Key Issue 6 (UAV Controller and UAV association):
  4 solutions address KI#6.
Key Issue 7 (User Plane Connectivity for UAVs)
  8 solutions address KI#7.

## Slide 5: FS_ID_UAS_SA2 status after SA2#139-e (2/2)
RAN impacts and dependencies:
  One solution (#8) proposes porting to NR the LTE aerial features.
Contentious Issue:
  The extent to which SA2 can influence the features of the CAA-Level UAV ID assigned and defined in the aviation space.
Focus for the Next Meeting (SA2#141-e):
  Evaluations and conclusions. New solutions have not been explicitly excluded but, with a target completion of September 2020, it is clear that new solutions would not allow for evaluation and conclusion.
Overall Plan:
  No new key issues.
  No new solutions.
  Suggest contributors to merge solutions and complete the existing ones, instead of bringing new solutions. Focus on processing solutions (mergers, adding details), evaluation, and conclusions.
Risks:
  None identified.

## Slide 6: BACKUP Previous FS_UAS_ID Status Report (S2-2002032) for information

## Slide 7: FS_ID_UAS_SA2 status after SA2#139-e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 25% > 50% | Jun, 20 -> Sep, 20 | SP-181114
General
  Total TUs requested for Study Phase in 2020 is 3. 1 TU is used and 2 TUs are remaining.
  Key Issue, architectural assumptions and requirements, and reference architecture have been agreed at 136AH and updated at 139-e.
  21 solutions, most spanning across multiple key issues, are in the TR after 139-e.
Key Issue 1 (UAV identification) :
  7 solutions address KI#1.
Key Issue 2 (UAV authorization by UTM)
  10 solutions address KI#2.
Key Issue 3 ( UAV Controller identification and authorization/authentication):
  3 solutions address KI#3.
Key Issue 4 (UAV and UAV Controller tracking):
  7 solutions address KI#4.

## Slide 8: FS_ID_UAS_SA2 status after SA2#139-e (2/2)
Key Issue 5 (UAV authorization revocation and (re)authorization failures):
  7 solutions address KI#5.
Key Issue 6 (UAV Controller and UAV association):
  3 solutions address KI#6.
Key Issue 7 (User Plane Connectivity for UAVs)
  5 solutions address KI#7.
RAN impacts and dependencies:
  One solution (#8) proposes porting to NR the LTE aerial features.
Contentious Issue:
  The extent to which SA2 can influence the features of the CAA-Level UAV ID assigned and defined in the aviation space.
Focus for the Next Meeting (SA2#140-e):
  Evaluations and conclusions. New solutions have not been explicitly excluded but, with a target completion of September 2020, it is clear that new solutions would not allow for evaluation and conclusion.
Overall Plan:
  No new key issues. Suggest contributors to merge solutions and complete the existing ones, instead of bringing new solutions. Focus on processing solutions (mergers, adding details), evaluation, and conclusions.
Risks:
  Completion of the study may not be possible in Q3 if new solutions are brought to the August meeting.

## Slide 9: FS_ID_UAS_SA2 status after SA2#136AH (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 0% > 25% | Jun, 20 | SP-181114
General
  FS_ID_UAS_SA2 TR 23.754 v0.1.0 is available here.
  Total TUs requested for Study Phase in 2020 is 3. 1 TU is used and 2 TUs are remaining.
  Key Issue, architectural assumptions and requirements, and reference architecture have been agreed.
Key Issue 1 (UAV identification) :
  No contributions focused on this KI could be handled due to lack of time
  Next Steps: SA2#137 to handle solutions
Key Issue 2 (UAV authorization by UTM)
  No contributions focused on this KI could be handled due to lack of time
Key Issue 3 ( UAV Controller identification and authorization/authentication):
  No contributions focused on this KI could be handled due to lack of time
Key Issue 4 (UAV and UAV Controller tracking):
  One (partial) solution was added to the TR

## Slide 10: FS_ID_UAS_SA2 status after SA2#136AH (2/2)
Key Issue 5 (UAV authorization revocation and (re)authorization failures):
  No contributions focused on this KI could be handled due to lack of time
Key Issue 6 (UAV Controller and UAV association):
  No contributions focused on this KI could be handled due to lack of time
Key Issue 7 (User Plane Connectivity for UAVs)
  No contributions focused on this KI could be handled due to lack of time
RAN impacts and dependencies:
  None
Contentious Issue:
  None yet
Focus for the Next Meeting (SA2#137):
  Process new solutions
Overall Plan:
  Focus on processing solution and not adopting new key issues at next meeting, to allow May meeting to complete solutions, evaluations and conclusions.