## Slide 1: FS_5G_ProSe Status Report
Deng Qiang (CATT), Jianhua Liu (OPPO)
3GPP TSG SA WG2 Meeting #142E
Electronic meeting, Nov 16 – Nov 20 2020

## Slide 2: FS_5G_ProSe status after SA2#142e (1/4)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 85% > 90% | Dec, 20 | SP-200444
General
  FS_5G_ProSe TR 23.752 v0.7.0 is available here.
  Interim conclusions or conclusions are agreed/updated for KI#1, #3, #4, #5, #7 and #8 at SA2#142e.
Key Issue 1 (Direct Discovery):
  UP based 5G DDNMF architecture is concluded.
  This key issue is concluded.
  Next Steps: Start normative work.
Key Issue 2 (Direct Communication):
  This key issue was concluded at SA#141e and no further update.
  Next Steps: Start normative work.

## Slide 3: FS_5G_ProSe status after SA2#142e (2/4)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 85% > 90% | Dec, 20 | SP-200444
Key Issue 3 (UE-to-Network Relay):
  Interim conclusions are made for Layer-3 Relay QoS solutions and N3IWF based solution.
  The decision to support Layer 3-based UE-to-Network solution, Layer 2-based UE-to-Network solution, or both will be determined in cooperation with RAN2/SA3.
  Next Steps: Overall evaluation between Layer-2 vs. Layer-3 Relay and final conclusion.
Key Issue 4 (UE-to-UE Relay):
  Interim conclusions are made for Layer-3 and Layer-2 Relays.
  The decision to support Layer 3-based UE-to-UE solution, Layer 2-based UE-to-UE solution, or both will be determined in cooperation with RAN2/SA3.
  Next Steps: Overall evaluation between Layer-2 vs. Layer-3 Relay and final conclusion.

## Slide 4: FS_5G_ProSe status after SA2#142e (3/4)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 85% > 90% | Dec, 20 | SP-200444
Key Issue 5 (Path Selection):
  It is concluded that A path preference for ProSe Services can be provided by AF to UDR, and may be used by PCF for path selection policy generation/update, and Direct usage of NWDAF analytics and/ or QNC by PCF for path selection policy generation/update is not specified in this release.
  This key issue is concluded.
  Next Steps: Start normative work.
Key Issue 7 (Charging):
  It is concluded that the PCF is used to provision the UE on the PC5 usage reporting configuration.
  The decision to support Control Plane based UE usage reporting or User Plane based UE usage reporting will be determined in cooperation with SA5.
  Next Steps: Start normative work on concluded solution and continue aspect that has SA5 dependency.
Key Issue 8 (Service Authorization):
  Conclusion update is made.
  This key issue is concluded.
  Next Steps: Start normative work for no-relay aspects. Relay aspects to be aligned with KI#3 and #4 conclusions.

## Slide 5: FS_5G_ProSe status after SA2#141e (4/4)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 85% > 90% | Dec, 20 | SP-200444
  Other WG impacts and dependencies:
  Conclusions for KI#3 (UE-to-Network Relay) and #4 (UE-to-UE Relay) have dependencies on RAN2 and SA3. Cooperation with RAN2 and SA3 is needed.
  Conclusion for KI#7 UE usage reporting aspect has dependency on SA5. Cooperation with SA5 is needed.
Contentious Issue:
  Final conclusion on UE-to-Network Relay and UE-to-UE Relay regarding Layer-2 and/or Layer-3 Relay need to be made with cooperation with RAN2 and SA3.
Focus for the Next Meeting (SA2#143e):
  Start normative work for concluded key issues.
  Conclude the key issues that have other WGs dependencies, based on feedback from other WGs feedback.
Overall Plan:
  SA2#143e: Start normative work for concluded key issues, and finalize the evaluation and conclusion of the key issues that have other WGs dependencies .
Risks:
  Due to RAN and SA5 dependencies, KI#3 (UE-to-Network Relay) and KI#4 (UE-to-UE Relay), and KI#7 on UE usage reporting aspect are not concluded by Dec 2020.

## Slide 6: FS_5G_ProSe Status at SA#90e
Progress since SA#89-e:
  Conclusions are made/updated for KI#1 (Direct Discovery), #2 (Direct Communication), #5 (Path Selection), #7 (PC5 Charging) and #8 (Service Authorization).
  Interim conclusions are made for KI#3 (UE-to-Network Relay) and #4 (UE-to-UE Relay)
  LS out are sent to RAN WGs and SA5 to request feedback and inform SA2 progress.
RAN impacts or dependencies:
  Conclusions for KI#3 (UE-to-Network Relay) and #4 (UE-to-UE Relay) have dependencies on RAN2 and SA3. Cooperation with RAN2 and SA3 is needed.
  Conclusion for KI#7 UE usage reporting aspect has dependency on SA5. Cooperation with SA5 is needed.
Next steps:
  Start normative work for concluded key issues.
  Conclude the key issues that have other WGs dependencies, based on feedback from other WGs feedback.
  Target Completion: KI#3 and KI#4 are not conclude by Dec, 20 due to RAN2/SA3 dependency, KI#7 on UE usage reporting aspect is not concluded by Dec, 20 due to SA5 dependency.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 65% > 90% | Sep, 20 -> Dec, 20 | SP-200444

## Slide 7
Status report of previous meetings

## Slide 8: FS_5G_ProSe Status at SA#87
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 30% > 55% | Jun, 20 | SP-190443
Progress since SA#86:
  Only one SA2 WG meeting in Q1
  Total TUs requested for Study Phase in 2020 is 7. 2 TUs are used and 5 TUs are remaining.
  New solutions and solution updates are captured into TR 23.752, and for all key issues we have solutions on table.
  RAN impacts and dependencies:
  All the key issues may have RAN impact and coordination with RAN may be necessary.
Contentious Issue:
  Whether support of service continuity for UE-to-Network Relay in Release 17 needs SA#87 decision..
Next steps:
  Consolidate the solutions, make overall evaluation and conclusions for each key issue at Q2.
  For UE-to-Network Relay and UE-to-UE Relay, consolidate technical issues and conclusions on SA2 aspect, pending RAN-related issues and wait for RAN progress.

## Slide 9: FS_5G_ProSe status after SA2#136AH (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 30% > 55% | Jun, 20 | SP-190443
General
  FS_5G_ProSe TR 23.752 v0.3.0 is available here.
  Total TUs requested for Study Phase in 2020 is 7. 2 TUs are used and 5 TUs are remaining.
  New solutions and solution updates are captured into TR 23.752, and for all key issues we have solutions on table.
Key Issue 4 (UE-to-UE Relay):
  4 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#4 is 4.
  Next Steps: Consolidate the solutions and make overall evaluation and conclusions on SA2 aspect, wait for RAN NR sidelink relay SI progress.
Key Issue 5 (Path Selection):
  1 new solution was agreed for inclusion in the TR. Total number of solutions for KI#5 is 1.
  Next Steps: Resolve the ENs in this solution, discuss other solutions if available and make evaluation and conclusion.
Key Issue 7 (Charging):
  3 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#7 is 3.
  Solutions can be categorized as AMF-based and SMF-based solutions.
  Next Steps: Resolve the ENs in these solutions, discuss other solutions if available and make overall evaluation and conclusion.
Key Issue 8 (Service Authorization):
  2 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#8 is 2.
  Next Steps: Resolve the ENs in these solutions, discuss other solutions if available and make overall evaluation and conclusion.

## Slide 10: FS_5G_ProSe status after SA2#136AH (2/3)
Key Issue 1 (Direct Discovery):
  For DDNMF location, UP-based and CP-based were agreed for inclusion in the TR.
  For UE-to-Network discovery, 1 solution was agreed for inclusion in the TR.
  Total number of (related) solutions for KI#1 are 7.
  Next Steps: Consolidate the solutions and make overall evaluation and conclusions.
Key Issue 2 (Direct Communication):
  2 new solutions on ProSe QoS were agreed for inclusion in the TR.
  1 new solution on group communication was agreed for inclusion in the TR.
  Total number of (related) solutions for KI#2 is 5.
  Next Steps: Consolidate the solutions and make overall evaluation and conclusions.
Key Issue 3 (UE-to-Network Relay):
  Solutions for Layer-3 Relay (sol#6) and Layer-2 Relay (sol#7) were captured in the TR.
  Next Steps: Consolidate technical issues and conclusions on SA2 aspect, pending RAN-related issues and wait for RAN progress.

## Slide 11: FS_5G_ProSe status after SA2#136AH (3/3)
  RAN impacts and dependencies:
  All the key issues may have RAN impact and coordination with RAN may be necessary.
Contentious Issue:
  UE-to-Network Relay and UE-to-UE Relay regarding Layer-2 or Layer-3 Relay depends on RAN decision.
Focus for the Next Meeting (SA2#138):
  Consolidate the solutions, make overall evaluation and conclusions for key issues whose solutions are deemed stable at SA2#138.
  For UE-to-Network Relay and UE-to-UE Relay, consolidate technical issues and conclusions on SA2 aspect, pending RAN-related issues and wait for RAN progress.
Overall Plan:
  SA2#138 (Apr) & SA2#139 (May): Consolidate the solutions, make overall evaluation and conclusions for each key issue. Submit TR 23.752 to SA#88 plenary (June 2020) for one-stop approval. Agree a WID.

## Slide 12: FS_5G_ProSe status after SA2#139e (1/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 55% > 65% | Jun, 20 -> Sep, 20 | SP-190443
General
  FS_5G_ProSe TR 23.752 v0.4.0 is available here.
  There is only one e-meeting for Rel-17 SIDs in Q2 and all FS_5G_ProSe documents were handled at SA2#139e.
  16 new solutions and 21 solutions update agreed for inclusion in TR 23.752, there are now 38 solutions in TR 23.752 on all the 7 prioritized key issues.
  LS out was sent to SA3 to ask about security requirements on UE-to-Network Relay and UE-to-UE Relay.
Key Issue 1 (Direct Discovery):
  4 solutions updates (sol#1, #2, #3, #18) were agreed for inclusion in the TR.
  1 new solution for UE-to-Network Relay discovery and 1 new solution for UE-to-UE Relay discovery were agreed for inclusion in the TR.
  Total number of solutions for KI#1 are 9.
  Next Steps: Complete and consolidate the solutions. Start solution evaluation and (interim) conclusion(s).
Key Issue 2 (Direct Communication):
  1 new solution and 4 solutions updates (sol#4, #5, #22) were agreed for inclusion in the TR.
  Total number of solutions for KI#2 is 6.
  Next Steps: Complete and consolidate the solutions. Start solution evaluation and (interim) conclusion(s).

## Slide 13: FS_5G_ProSe status after SA2#139e (2/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 55% > 65% | Jun, 20 -> Sep, 20 | SP-190443
Key Issue 3 (UE-to-Network Relay):
  9 new solutions (addressing security, service continuity, authentication/authorization etc.) and 5 solutions updates (sol#6, #7) were agreed for inclusion in the TR.
  Total number of solutions for KI#3 are 12.
  Next Steps: Complete and consolidate the solutions and starting self-evaluation and self-conclusion(s) for L2-based Relay and L3-based Relay respectively from SA2 point of view. Communicate with RAN WGs on the TR and pend RAN/SA3-related issues, wait for RAN/SA3 progress.
Key Issue 4 (UE-to-UE Relay):
  2 new solutions and 5 solutions updates were agreed for inclusion in the TR.
  Total number of solutions for KI#4 is 6.
  Next Steps: Complete and consolidate the solutions and starting self-evaluation and self-conclusion(s) for L2-based Relay and L3-based Relay respectively from SA2 point of view. Communicate with RAN WGs on the TR and pend RAN/SA3-related issues, wait for RAN/SA3 progress.

## Slide 14: FS_5G_ProSe status after SA2#139e (3/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 55% > 65% | Jun, 20 -> Sep, 20 | SP-190443
Key Issue 5 (Path Selection):
  1 solution update (sol#12) was agreed for inclusion in the TR. Total number of solutions for KI#5 is 1.
  Next Steps: Complete and consolidate the solutions. Start solution evaluation and (interim) conclusion(s).
Key Issue 7 (Charging):
  1 new solution and 3 solutions updates (sol#13, #14, #15) were agreed for inclusion in the TR. Total number of solutions for KI#7 is 4.
  Solutions can be categorized as CP-based and UP-based solutions.
  Next Steps: Complete and consolidate the solutions. Start solution evaluation and (interim) conclusion(s).
Key Issue 8 (Service Authorization):
  2 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#8 is 4.
  Next Steps: Complete and consolidate the solutions. Start solution evaluation and (interim) conclusion(s).

## Slide 15: FS_5G_ProSe status after SA2#139e (4/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 55% > 65% | Jun, 20 -> Sep, 20 | SP-190443
  RAN impacts and dependencies:
  Solutions for KI#1, #2, #7 and #8 has minimal RAN impact.
  Solutions for KI#5 may have RAN impact and depends on the solution discussion.
  Solutions for KI#3 (UE-to-Network Relay) and #4 (UE-to-UE Relay) have dependencies on RAN and SA3. RAN/SA3 plan to start corresponding study work in August, this makes final conclusions on these two KIs in August meeting at high risk.
Contentious Issue:
  UE-to-Network Relay and UE-to-UE Relay regarding Layer-2 or Layer-3 Relay depending on RAN decision.
Focus for the Next Meeting (SA2#140e):
  No new KI, and last meeting to bring any new solutions. New solution proposals should be reasonably complete.
  For KI#1, #2, #7 and #8, complete and consolidate the solutions, and start solution evaluation and conclusion(s).
  For KI#5, complete and consolidate the solutions, make ready for evaluation and conclusion and identify RAN impact if any.
  For KI#3 and #4, complete and consolidate the solutions, and starting self-evaluation and self-conclusion(s) for L2-based Relay and L3-based Relay respectively from SA2 point of view. Communicate with RAN WGs on the TR and pend RAN/SA3-related issues, wait for RAN/SA3 progress.
  Draft LS to other WGs (e.g. RAN2/3) for feedback.

## Slide 16: FS_5G_ProSe status after SA2#139e (5/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 55% > 65% | Jun, 20 -> Sep, 20 | SP-190443
Overall Plan:
  SA2#140e (August):
    For Key Issues #1, #2, #7 and #8, complete and consolidate the solutions, and start solution evaluation and conclusion(s).
    For KI#5, complete and consolidate the solutions, make ready for evaluation and conclusion and identify RAN impact if any.
    For Key Issues #3, #4, complete and consolidate the solutions.
    Draft LS to other WGs (e.g. RAN2/3) for feedback.
  SA2#141e (October)/SA2#142e (November):
    Continue solution evaluation and conclusion for KI#1, #2, #5, #7 and #8 if not finished at SA2#140e.
    New WID proposal based on agreed conclusion(s).
    For KI#3, KI #4, self-evaluation and self-conclusion(s) for L2-based Relay and L3-based Relay respectively from SA2 point of view.
    Draft any additional LS to other WGs (e.g. RAN2/3) for feedback.

## Slide 17: FS_5G_ProSe status after SA2#140e (1/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 65% > 70% | Sep, 20 -> Dec, 20 | SP-200444
General
  FS_5G_ProSe TR 23.752 v0.5.0 is available here.
  There is only one e-meeting for Rel-17 SIDs in Q3 and all FS_5G_ProSe documents were handled at SA2#140e.
  13 new solutions added and 33 solutions update agreed for inclusion in TR 23.752, there are now 51 solutions in TR 23.752 on all the 7 prioritized key issues.
  Interim conclusions are agreed for KI#1, #2, #5 and #8 at SA2#140e.
  LS out are sent to SA3 and RAN WGs to request feedback and inform SA2 progress.
Key Issue 1 (Direct Discovery):
  1 new solution and 5 solutions updates were agreed for inclusion in the TR. Total number of solutions for KI#1 are 10.
  Interim conclusions are made on discovery model, PC5 communication channel, application layer discovery messages, ProSe code management, information elements in discovery message, etc.
  LS out is sent to RAN2 to request feedback on SA2 conclusions/assumptions.
  Next Steps: Continue solution evaluation and (interim) conclusion(s).
Key Issue 2 (Direct Communication):
  1 solution updates was agreed for inclusion in the TR. Total number of solutions for KI#2 is 6.
  Interim conclusions are made on introducing new PQI values and new data unit types.
  LS out is sent to RAN1 to confirm the support of new PQI values.
  Next Steps: Continue solution evaluation and (interim) conclusion(s).

## Slide 18: FS_5G_ProSe status after SA2#140e (2/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 65% > 70% | Sep, 20 -> Dec, 20 | SP-200444
Key Issue 3 (UE-to-Network Relay):
  9 new solutions (addressing Relay discovery, QoS, authentication/authorization, etc.) and 16 solutions updates were agreed for inclusion in the TR. Total number of solutions for KI#3 are 21.
  LS out to SA3 to request feedback on end-to-end security.
  Next Steps: Complete and consolidate the solutions, and make evaluation and interim conclusion(s) subject to RAN progress and feedback (if any).
Key Issue 4 (UE-to-UE Relay):
  2 new solutions and 3 solutions updates were agreed for inclusion in the TR. Total number of solutions for KI#4 is 8.
  Next Steps: Complete and consolidate the solutions, and make evaluation and interim conclusion(s) subject to RAN progress and feedback (if any).

## Slide 19: FS_5G_ProSe status after SA2#140e (3/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 65% > 70% | Sep, 20 -> Dec, 20 | SP-200444
Key Issue 5 (Path Selection):
  1 new solution and 3 solution update was agreed for inclusion in the TR. Total number of solutions for KI#5 is 2.
  Interim conclusions are made on Path selection policy provisioning/configuration.
  Next Steps: Continue solution evaluation and (interim) conclusion(s).
Key Issue 7 (Charging):
  No new solutions or solution update were agreed for inclusion in the TR. Total number of solutions for KI#7 is 4.
  Solutions evaluation and conclusion papers were not agreeable due to lack of common understanding on the pros and cons of the solutions, and which part falls into SA5 study.
  Next Steps: Continue solution evaluation and (interim) conclusion(s), communicate with SA5 to request feedback on the identified issues.
Key Issue 8 (Service Authorization):
  4 solutions update were agreed for inclusion in the TR. Total number of solutions for KI#8 is 4.
  Interim conclusions are made on direct discovery and direct communication policy/parameter provisioning (non-relay aspects)
  Next Steps: Continue solution evaluation and (interim) conclusion(s).

## Slide 20: FS_5G_ProSe status after SA2#140e (4/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 65% > 70% | Sep, 20 -> Dec, 20 | SP-200444
  RAN impacts and dependencies:
  Solutions for KI#1, #2, #5, #7 and #8 has minimal RAN impact.
  Solutions for KI#3 (UE-to-Network Relay) and #4 (UE-to-UE Relay) have dependencies on RAN. Cooperation with RAN SI “NR sidelink relay” is needed.
Other WGs impact and dependencies
  Solutions for KI#7 have dependencies on SA5.
  Solutions for KI#3 and #4 have dependencies on SA3.
Contentious Issue:
  UE-to-Network Relay and UE-to-UE Relay regarding Layer-2 or Layer-3 Relay depending on RAN decision.
Focus for the Next Meeting (SA2#141e):
  No new solution. Merge of existing solutions to generated new merged solution is allowed.
  For KI#1, #2, #5 and #8, continue solution evaluation and conclusion(s).
  For KI#7, converge on solution evaluation and make conclusions.
  For KI#3 and #4, complete and consolidate the solutions, and make evaluation and interim conclusion(s) subject to RAN progress and feedback (if any).
  Draft LS to other WGs (e.g. RAN2/3, SA3, SA5) for feedback.
  New WID proposal based on agreed conclusion(s) and RAN feedback.
  Discussion on how to structure the normative work, e.g. existing or new TS.

## Slide 21: FS_5G_ProSe status after SA2#140e (5/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 65% > 70% | Sep, 20 -> Dec, 20 | SP-200444
Overall Plan:
  SA2#141e (October)/SA2#142e (November):
    Continue solution evaluation and conclusion for KI#1, #2, #5, #7 and #8.
    New WID proposal based on agreed conclusion(s) and RAN feedback.
    For KI#3, KI #4, and make evaluation and interim conclusion(s) subject to RAN progress and feedback (if any).
    Draft any additional LS to other WGs (e.g. RAN2/3, SA3, SA5) for feedback.
    Discussion on how to structure the normative work, e.g. existing or new TS.

## Slide 22: FS_5G_ProSe Status at SA#89e
Progress since SA#88-e:
  13 new solutions added and 33 solutions update agreed for inclusion in TR 23.752, there are now 51 solutions in TR 23.752 on all the 7 prioritized key issues.
  Interim conclusions are made for KI#1 (Direct Discovery), #2 (Direct Communication), #5 (Path Selection) and #8 (Service Authorization).
  LS out are sent to SA3 and RAN WGs to request feedback and inform SA2 progress.
RAN impacts or dependencies:
  Solutions for KI#1, #2, #5, #7 and #8 has minimal RAN impact.
  Solutions for KI#3 (UE-to-Network Relay) and #4 (UE-to-UE Relay) have dependencies on RAN and SA3. Cooperation with RAN SI “NR sidelink relay” is needed.
  Solutions for KI#7 (PC5 charging) have dependencies on SA5.
Next steps:
  Continue solution evaluation and conclusion. Communicate with RAN WGs/SA3/SA5 to make final conclusions.
  New WID proposal based on agreed conclusion(s).
  Target Completion: KI#3 and KI#4 may not conclude by Dec, 20 due to RAN dependency.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 65% > 70% | Sep, 20 -> Dec, 20 | SP-200444

## Slide 23: FS_5G_ProSe status after SA2#141e (1/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 70% > 85% | Dec, 20 | SP-200444
General
  FS_5G_ProSe TR 23.752 v0.6.0 is available here.
  27 solutions update agreed for inclusion in TR 23.752.
  Interim conclusions or conclusions are agreed/updated for KI#1, #2, #3 and #8 at SA2#141e.
  LS out sent to RAN2 and SA3 to inform SA2 progress on UE-NW Relay and UE-UE Relay.
  LS out sent to SA5 to request feedback on PC5 charging issues.
Key Issue 1 (Direct Discovery):
  1 solution update and 3 conclusion update are agreed for inclusion in the TR.
  UP vs. CP based DDNMF solutions are further discussed and are for indicative SoH, no conclusion can be made and needs to be discussed next meeting.
  Next Steps: Continue solution evaluation and conclusion.
Key Issue 2 (Direct Communication):
  One conclusion update was agreed for inclusion in the TR.
  Next Steps: Conclusion refinement if needed.

## Slide 24: FS_5G_ProSe status after SA2#141e (2/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 70% > 85% | Dec, 20 | SP-200444
Key Issue 3 (UE-to-Network Relay):
  21 solutions updates were agreed for inclusion in the TR.
  Interim conclusions are made for both Layer-3 and Layer-2 UE-NW Relay. Final conclusions to be made with cooperation with RAN2 and SA3.
  LS out to RAN2 and SA3 to inform SA2 progress.
  Next Steps: Complete and consolidate the solutions, continue solution evaluation and (interim) conclusions.
Key Issue 4 (UE-to-UE Relay):
  3 solutions updates were agreed for inclusion in the TR.
  No conclusions are made for UE-UE Relay.
  Next Steps: Complete and consolidate the solutions, continue solution evaluation and (interim) conclusions.

## Slide 25: FS_5G_ProSe status after SA2#141e (3/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 70% > 85% | Dec, 20 | SP-200444
Key Issue 5 (Path Selection):
  1 solution update was agreed for inclusion in the TR.
  Policy update based on QNC, NWDAF, AF information are further discussed and for indicative SoH, no conclusion can be made and needs to be discussed next meeting.
  Next Steps: Continue solution evaluation and conclusions.
Key Issue 7 (Charging):
  PC5 usage information reporting configuration and PC5 usage information reporting are further discussed and for indicative SoH, way forward is agreed to ask SA5 guidance before making conclusions.
  LS out to SA5 to seek guidance on the above issues.
  Next Steps: Conclude the KI based on SA5 feedback.
Key Issue 8 (Service Authorization):
  2 solutions update and were agreed for inclusion in the TR.
  Interim conclusions are made on UE-NW Relay and UE-UE Relay, and needs to be updated based on conclusions of KI#3 and KI#4.
  Next Steps: Update the conclusions based on other KI conclusion.

## Slide 26: FS_5G_ProSe status after SA2#141e (4/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 70% > 85% | Dec, 20 | SP-200444
  Other WG impacts and dependencies:
  Conclusions for KI#3 (UE-to-Network Relay) and #4 (UE-to-UE Relay) have dependencies on RAN2 and SA3. Cooperation with RAN2 and SA3 is needed.
  Conclusion for KI#7 have dependencies on SA5. Cooperation with SA5 is needed.
Contentious Issue:
  Final conclusion on UE-to-Network Relay and UE-to-UE Relay regarding Layer-2 and/or Layer-3 Relay need to be made with cooperation with RAN2 and SA3.
Focus for the Next Meeting (SA2#142e):
  No new solution. Focus on solution evaluations/interim conclusions.
  For KI#1, make conclusion on UP vs. CP based DDNMF solutions.
  For KI#5, make conclusion on Policy update based on QNC, NWDAF, AF information.
  For KI#7, make conclusion on PC5 usage information reporting configuration and PC5 usage information reporting if get feedback from SA5.
  For KI#3 and #4, complete and consolidate the solutions, and make evaluation and interim conclusion(s) subject to RAN2 and SA3 progress and feedback (if any).
  Draft LS to other WGs (e.g. RAN2/3, SA3, SA5) for feedback.
  New WID proposal based on agreed conclusion(s) and RAN2/SA3/SA5 feedback.
  Submit TR 23.752 to SA#90e plenary for approval.

## Slide 27: FS_5G_ProSe status after SA2#141e (5/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 70% > 85% | Dec, 20 | SP-200444
Overall Plan:
  SA2#142e: Finalize the Evaluation and conclusion of the KIs.
  TR 23.752 and WID expected to be sent to SA#90E for approval.
Risks:
  Due to RAN and SA5 dependencies, completion of the study may not be possible in Q4 for all key issues.