## Slide 1: FS_5MBS Status Report
Li, Meng
Huawei

## Slide 2: FS_5MBS status after SA2#142e (1/3)
General
  TR 23.757 v1.2.0 is available.
  Evaluations and conclusions principles for KI#1, #2, #3, #4, #6, #7, and #9 are agreed.
  An LS sent to RAN2/RAN3 for the RAN dependent issues.
Key Issue 1 (MBS session management)
  Evaluation and principles for conclusion are captured.
  SMF/MB-SMF centric solutions are agreed as the baseline work.
  Whether UP-based join shall be supported or not is TBD.
  Issues recorded in clause 8.1.2.2 including roaming, DDoS treatment, ETSUN cooperation and so on are TBD.
  Next step: Start the normative work on the concluded parts, resolve the open issues without RAN dependency, and coordinate with RAN on the open issues related to the RAN.
Key Issue 2 (Levels of services)
  Evaluation and Conclusion are captured.
  Next step: Start the normative work.
Key Issue 3 (Levels of authorization)
  Evaluation and Conclusion are captured.
  Next step: Start the normative work and resolve any left open issue.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 85 % > 90% | Dec, 2020 | SP-200092

## Slide 3: FS_5MBS status after SA2#142e (2/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 85 % > 90% | Dec, 2020 | SP-200092
Key Issue 4 (QoS)
  Evaluation and conclusion for multicast and broadcast are captured.
  Only issue TBD is different understanding on the SA1 requirement on how priority upgrade for MBS Session from MCPTT AS is support.
  Next step: Start the normative work on the concluded parts and resolve the open issues.
Key Issue 6 (Local MBS)
  Evaluation and Conclusion are captured.
  Next step: Start the normative work.
Key Issue 7 (MC-UC switch)
  Evaluation and principles for conclusion are captured.
  Next step: Start the normative work on the concluded parts and coordinate with RAN on the open issues related to the RAN.
Key Issue 9 (Interworking with EPC/eMBMS for Public Safety)
  Evaluation and Conclusion are captured.
  Open issue TBD is when the UE camp at EPS network whether the unicast bearer triggered by Application Server can be associated with MBS session .
  Next step: Start the normative work and resolve any left open issue.

## Slide 4: FS_5MBS status after SA2#142e (3/3)
  RAN impacts and dependencies:
  Most of the key issues and related solutions may lead to RAN impact.
  LS sent to RAN, RAN2 and RAN3 to ask about the conclusions with RAN dependencies.
Contentious Issue:
  None identified so far.
Focus for the Next Meeting (SA2#143E):
  Finalize the conclusions for the KIs with open issues.
  Start normative work for the concluded key issues.
  Coordinate with RAN WGs to resolve the aspects with RAN dependencies.
Overall Plan:
  SA2#143e: Start normative work for concluded key issues, and finalize the evaluation and conclusion of the key issues that with open issues.
Risks:
  None.

## Slide 5: FS_5MBS Status at SA#90-e
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 85% > 92% | Sep, 20 -> Dec, 20 | SP-200092
Progress since SA#90-e:
  Conclusions are made/updated for KI#1, #2, #3, #4, #6, #7 and #9.
  KI#1 and KI#4 are concluded many parts but with non-blocking open issues to be resolved.
  KI#1 and KI#7 are concluded many parts but other parts are with RAN dependencies and need to coordinate with RAN WGs to resolve those aspects .
  LS out are sent to RAN2 and RAN3 to request feedback on clause 8 of the TR (i.e., conclusion) and questions in the LS of SA4.
  RAN impacts and dependencies:
  Most of the key issues may lead to RAN impact.
Next steps:
  Finalize the conclusions for the KIs with open issues.
  Start normative work for the concluded key issues.
  Coordinate with RAN WGs to resolve the aspects with RAN dependencies.

## Slide 6: Backup SA2#140E FS_5MBS Status Report (S2-2006060) for information

## Slide 7: FS_5MBS status after SA2#141e (1/3)
General
  TR 23.757 v1.1.0 is available.
  A consolidated architecture is agreed as the baseline architecture.
  Evaluations and conclusions principles for serveral KIs are agreed.
  Three new solutions are added, and totally 46 solutions documented in the TR.
Key Issue 1 (MBS session management)
  18 solutions available: 2 new and 9 updated during SA2 #141E.
  Initial evaluation and Several principles for conclusion are captured.
  Next step: Finalize the evaluation and conclusion of the KI.
Key Issue 7 (MC-UC switch)
  15 solutions available: 4 updated during SA2#141E.
  Initial evaluation and Several principles for conclusion are captured.
  Next step: Finalize the evaluation and conclusion of the KI.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 65 % > 85% | Dec, 2020 | SP-200092

## Slide 8: FS_5MBS status after SA2#141e (2/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 65 % > 85% | Dec, 2020 | SP-200092
Key Issue 4 (QoS)
  9 solutions available: 4 updated during SA2#141E.
  Evaluation and conclusion for multicast are captured.
  Conclusion for broadacast is expected to be completed in 142E.
  Next step: Finalize the evaluation and conclusion of the KI.
Key Issue 6 (Local MBS)
  6 solutions available: 4 updated during SA2#141E.
  Evaluation and Several principles for conclusion are captured.
  Next step: Finalize the evaluation and conclusion of the KI.
Key Issue 9 (Interworking with EPC/eMBMS for Public Safety)
  4 solutions available: 1 new and 2 udpated during SA2#141E.
  Next step: Finalize the evaluation and conclusion of the KI.
Key Issue 2 (Levels of services)
  1 solution available and updated during SA2#141E.
  Next step: Using this solution as the conclusion of the KI.
Key Issue 3 (Levels of authorization)
  Evaluation and 2 solutions updated during SA2#141E.
  Next step: Finalize the conclusion and if needed, update the evaluation.

## Slide 9: FS_5MBS status after SA2#141e (3/3)
  RAN impacts and dependencies:
  Most of the key issues and related solutions may lead to RAN impact.
  Solutions specific questions were included in the LS sent to RAN, RAN2 and RAN3.
Contentious Issue:
  None identified so far.
Focus for the Next Meeting (SA2#142E):
  Proposals for new solution will NOT be discussed (except if proposed as a Way Forward proposal to enable conclusions).
  New/updated key issue will NOT be discussed.
  Evaluate and conclude KIs.
Overall Plan:
  SA2#142e: Finalize the Evaluation and conclusion of the KIs.
  TR 23.757 and WID expected to be sent to SA#90E for approval.
Risks:
  Due to RAN dependencies, completion of the study may not be possible in Q4 for all key issue.

## Slide 10: FS_5MBS status after SA2#140e (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 50% > 65 % | Sep, 2020 -> Dec, 2020 | SP-200092
General
  TR 23.757v0.5.0 is available. The TR is sent to SA plenary for information.
  In 2020Q3 FS_5MBS was discussed in SA2#140E.
Architectural options
  Companies tried to have a consolidated architecture in SA2#140E.
  Architecture shall be determined as early as possible to not impede the progress.
  Next step: Conclude the architecture.
Key Issue 1 (MBS session management)
  16 solutions available: 14 already existing (of which 12 updated in SA2#140E) plus 2 new.
  Interim requirements for conclusions agreed.
  Next step: Evaluate and Conclude the solutions.
Key Issue 7 (MC-UC switch)
  13 solutions available: 11 already existing (of which 9 updated in SA2#140E) plus 2 new.
  Next step: Evaluate and Conclude the solutions.

## Slide 11: FS_5MBS status after SA2#140e (2/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 50% > 65 % | Sep, 2020 -> Dec, 2020 | SP-200092
Key Issue 4 (QoS)
  8 solutions available (3 new, and 1 updated).
  Next step: Evaluate and conclude the solutions.
Key Issue 6 (Local MBS)
  5 solutions available: 3 updated in SA2#140E plus 1 new.
  Next step: Evaluate and conclude the solutions.
Key Issue 9 (Interworking with EPC/eMBMS for Public Safety)
  3 solutions agreed in SA2#140E.
  Next step: Finalize descriptions of solutions and new solutions can be proposed.
Key Issue 2 (Levels of services)
  1 solution available which was introduced in SA2#136AH and updated in SA2#139E.
  Next step: Address other KIs firstly and come back after concluding those KIs.
Key Issue 3 (Levels of authorization)
  Agreed not to have a separate solutions in the TR.
  Next step: If authorization is need, address this KI in the individual solutions and conclude as part of KI#1.

## Slide 12: FS_5MBS status after SA2#140e (3/3)
  RAN impacts and dependencies:
  Most of the key issues and related solutions may lead to RAN impact.
  Solutions specific questions were included in the LS sent to RAN, RAN2 and RAN3.
Contentious Issue:
  None identified so far.
Focus for the Next Meeting (SA2#141E):
  Proposals for new solution will NOT be discussed unless they are for KI#9. New/updated key issue will NOT be discussed.
  Evaluate and conclude the architecture and KIs.
Overall Plan:
  SA2#141e: Evaluate and conclude the architecture and KIs.
  SA2#142e: Evaluate and conclude the remaining KIs.
  TR 23.757 and WID expected to be sent to SA#90E for approval.
Risks:
  Due to RAN dependencies, completion of the study may not be possible in Q4 for all key issues,

## Slide 13: FS_5MBS status at SA#87
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 15% > 35% | Jun, 20 | 830030/ SP-200xxx
Progress since SA#86:
  Only one SA2 WG meeting in Q1 (SA2#136AH)
  Total TUs requested for Study Phase in 2020 is 8, 2 TUs used in SA2#136AH and 6 TUs remaining.
  Objective B/Key Issue #5 (enTV services) and E-UTRA access removed as a result of downscoping in SA#86 and of NR_MBS WI approved in RAN#86.
  Added new Key Issue 9 (NR/5GC and E-UTRAN/EPC interworking for public safety)
  RAN impacts and dependencies:
  Most of the key issues may lead to RAN impact.
Next steps:
  Address open key issues with focus on the most important ones.
  Finalize description for already captured solutions with strong support.
  Capture new solutions with strong support.
  Select solutions for at least most important key issues.
  List identified RAN dependencies and send liaisons to relevant RAN WGs.

## Slide 14: FS_5MBS status after SA2#136AH (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 15% > 35% | Jun, 20 | 830030/ SP-200xxx
General
  TR 23.757v0.3.0 is available.
  Total TUs requested for Study Phase in 2020 is 8, 2 TUs used in SA2#136AH and 6 TUs remaining.
  Objective B/Key Issue #5 (enTV services) and E-UTRA access removed as a result of downscoping in SA#86 and of NR_MBS WI approved in RAN#86.
  Added new Key Issue 9 (NR/5GC and E-UTRAN/EPC iwk for public safety)
Architectural options
  Two architectural options captured in Annex A. Option 1 has no new network entities for transport only mode while additional CP and UP entities are needed for full service mode. Option 2 uses new, MBS specific functional components both for transport only mode and full service mode.
Key Issue 1 (MBS session management)
  Five new solutions were included in the TR.
  Next step: in SA2#138 finalize description for solutions with strong support. Proceed with solution evaluation and interim conclusion.
Key Issue 2 (Levels of services)
  One solution captured.
  Next step: in SA2#138 finalize solution description and discuss other solutions if time allows. Proceed with solution evaluation and interim conclusion.
Key Issues 7/8 (MC-UC switch/BC-UC switch)
  No solution captured.
  Next step: in SA2#138 discuss and capture solutions, evaluate and proceed with interim conclusions.
Key Issue 6 (Local MBS)
  One solution captured.
  Next step: if time allows, discuss other solutions if available, evaluate and reach interim conclusions.
Key Issues 3/4/9 (levels of authorization/QoS/IWK with EPC/eMBMS for Public Safety)
  No solution captured.
  Next step: if time allows, discuss solutions if available and time allows, evaluate and reach interim conclusion.

## Slide 15: FS_5MBS status after SA2#136AH (2/2)
  RAN impacts and dependencies:
  Most of the key issues may lead to RAN impact.
Contentious Issue:
  Selection of architectural option.
  Selection of solution(s) for MBS session establishment/management.
Focus for the Next Meeting (SA2#138):
  No new key issues.
  Prioritize solutions for Key Issue 2 (Levels of services), KI1 (MBS session management) and KI7 (MC-UC switch).
  Complete solution descriptions and list RAN impacts for which feedback is needed. Liaise RAN WGs as needed.
  Start solution evaluations and draw interim conclusions.
  If time allows, address other Key Issues and related solutions.
  Evaluate solutions and capture conclusions.
Overall Plan:
  2020Q2:
  Complete description of existing solutions and new solutions with strong support for most important KIs (KI2/1/7).
  Start solutions and architecture options evaluations and draw interim conclusions for most important KIs.
  If time allows, address solutions for other KIs.
  TR 23.757 and WID expected to be sent to SA#88 for approval.

## Slide 16: FS_5MBS status after SA2#139E (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 35% -> 50% |  | SP-200092
General
  TR 23.757v0.4.0 is available.
  In 2020Q2 FS_5MBS was only discussed in SA2#139E.
  No new key issue. 24 new solutions added, mostly vs. KI1 and KI7. Previously existing solutions updated.
  Terminology issues fixed: PTP vs. PTM and Individual vs. Shared MBS traffic delivery methods.
Architectural options
  The two architectural options captured in Annex A have been updated and are now more mature.
  Next step: Start evaluation and attempt interim conclusion.
Key Issue 1 (MBS session management)
  14 solutions available: 5 already existing (of which 4 updated in SA2#139E) plus 9 new
  Next step: Conclude descripton of solutions. Start evaluation and, if possible, capture interim conclusions.
Key Issue 7 (MC-UC switch)
  11 solutions available (all new)
  Next step: Conclude descripton of solutions. Start evaluation and, if possible, capture interim conclusions.

## Slide 17: FS_5MBS status after SA2#139E (2/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 35% -> 50% |  | SP-200092
Key Issue 4 (QoS)
  3 solutions available (all new, of which two apply also to KI1).
  Next step: Capture new solutions, if available. Finalize descriptions of solutions.
Key Issue 6 (Local MBS)
  4 solutions available: 1 already existing (and updated in SA2#139E) plus 3 new.
  Next step: Capture new solutions, if available. Finalize descriptions of solutions.
Key Issue 9 (Interworking with EPC/eMBMS for Public Safety)
  2 solutions proposed in SA2#139E but not captured to wait for KI#1/2/7 to progress.
  Next step: Capture new solutions. Finalize descriptions of solutions.
Key Issue 2 (Levels of services)
  1 solution available which was introduced in SA2#136AH and updated in SA2#139E.
  Next step: If companies still have interest, try to conclude solution description.
Key Issue 8 (BC-UC switch)
  Agreed not to address this KI in Rel-17 timeframe.
Key Issue 3 (Levels of authorization)
  No solutions submitted for this KI.
  Next step: agree not to address this in KI in Rel-17 timeframe

## Slide 18: FS_5MBS status after SA2#139E (3/3)
  RAN impacts and dependencies:
  Most of the key issues and related solutions may lead to RAN impact.
  Solutions specific questions may need to be asked to reach conclusion.
Contentious Issue:
  Evaluation and selection of architectural option.
  Evaluation and selection of solution(s) for MBS session establishment/management and UC-MC switch
Focus for the Next Meeting (SA2#140E):
  No new key issues. Last meeting for new solutions. New solutions allowed only if complete.
  Merging of solutions is encouraged.
  Prioritize solutions for KI1 (MBS session management) and KI7 (MC-UC switch)
    Complete solution descriptions and list RAN impacts for which feedback is needed.
    Start solution evaluations and draw interim conclusions wherever possible.
  Address other Key Issues and related solutions.
    If possible, evaluate solutions and capture conclusions.
  Rappoteur will collect RAN impacts. TR 23.757 for information. Specific questions for feedback may be included.
Overall Plan:
  Conclusion of all KIs (and therefore of SI) by Sep. 2020 unlikely, due to RAN dependencies.
  2020H2:
    Complete description of solutions for all open KIs.
    Complete evaluation of solutions and architecture options evaluations, including RAN feedback where needed, and complete conclusions for all open KIs.
  TR 23.757 and WID expected to be sent to SA#90E for approval.