## Slide 1: FS_eNS_Ph2 Status Report
Jinguo Zhu
ZTE

## Slide 2: FS_eNS_Ph2 status after SA2#142E (1/4)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNS_Ph2 | Study on Enhancement of Network Slicing Phase 2 | 75% -> 90% | Sep, 20 -> Dec, 20 | SP-190931
General
  FS_eNS_Ph2 is captured in TR 23.700-40 and v1.2.0 will be available here.
  4 P-CR agreed updating the solution, 9 P-CR agreed updating the evaluation and conclusion.
  Conclusion on key issue#1 and key issue #2 were agreed.
  KI#3, KI#5 and KI#7 have potential RAN dependency. KI#4 has dependency on KI#1, KI#2, KI#3 and KI#5. No agreement on the use cases for KI#6
Key Issue #1: Support of network slice related quota on the maximum number of UEs
Key Issue #2: Support of network slice related quota on the maximum number of PDU Sessions
  2 P-CRs agreed updating the evaluation. 1 P-CR agreed to capture the conclusion.
  New NF based solution agreed for KI#1 and KI#2. An LS agreed to send to SA5 to ask further coordination on this subject
  Next Steps: Next meeting(SA2#143E) will start normative work for new NF based solution
Key Issue #3: limitation of data rate per network slice in UL and DL per UE
  2 P-CR agreed for evaluation and conclusion update. RAN2 partial feedback and RAN3 feedback are received.
  One company ask for further RAN2 feedback while others don’t think so.
  Next Steps: Next meeting (SA2#143E) will focus on final evaluation

## Slide 3: FS_eNS_Ph2 status after SA2#142E (2/4)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNS_Ph2 | Study on Enhancement of Network Slicing Phase 2 | 75% ->90% | Sep, 20 -> Dec, 20 | SP-190931
Key Issue #4: Support for network slice quota event notification in a network slice
  1 P-CR agreed to update the conclusion
  This key issue has dependency on KI#1, KI#2, KI#3 and KI#5.
  Next Steps: Next meeting (SA2#143E) will focus on final conclusions.
Key Issue #5: Dynamic adjustment to meet the limitation of data rate per network slice in UL and DL.
  1 P-CR agreed to update the evaluation, no interim conclusion yet.
  This key issue may have potential dependency on KI#3 which has RAN dependency
  Next Steps: Next meeting (SA2#143E) will focus on final conclusions.
Key Issue #6: Constraints on simultaneous use of the network slice
  1 P-CR agreed updating existing solution. 1 P-CR agreed on evaluation. No interim conclusion yet.
  Some companies proposes to send LS to GSMA to ask use case of this parameter, one company objects to send the LS.
  One company believes that existing specifications already support this GST parameter and all solutions for this key issue are optimization and therefore justifications are needed.
  Next Steps: Next meeting (SA2#143E) will focus on final evaluation and conclusions.

## Slide 4: FS_eNS_Ph2 status after SA2#142E (3/4)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNS_Ph2 | Study on Enhancement of Network Slicing Phase 2 | 75% -> 90% | Sep, 20 -> Dec, 20 | SP-190931
Key Issue #7: Support of 5GC assisted cell selection to access network slice
  3 P-CRs agreed updating existing solutions.
  Regarding on homogeneous support for slice within the Registration area, RAN3 feedback and CT1 feedback are received. RAN2 feedback is expected at next meeting.
  Some companies proposed to conclude the network based solution at this meeting and then conclude the UE based solution taking into the RAN working group feedback at next meeting. One company objects to conclude any solution in this meeting
  Next Steps: Next meeting (SA2#143E) will focus on final conclusions.
Key Issue #8: Area of service: impact on PLMN selection in roaming
  Next Steps: Not pursued in this release

## Slide 5: FS_eNS_Ph2 status after SA2#142E (4/4)
  RAN impacts and dependencies:
  RAN2 further feedback on KI#3 and KI#7 are expected in order to make conclusion at next meeting
  Solutions in RAN study may cause system impact.
Other SA WGs dependencies
  SA3: None. SA5: None
Contentious Issue:
  CHF based solution and non CHF based solutions (e.g. NSSF, PCF and new NF) for key issue 1 and key issue 2 are extensively discussed in SA2. SA2 finally agreed to define new NF based solution for key issue 1 and key issue 2. An LS is sent to SA5 to ask further coordination between SA2 and SA5 on this subject
Focus for the Next Meeting (SA2#143E):
  Normative work for KI#1 and KI#2
  Final evaluation and conclusion on KI#3, KI#4, KI#5, KI#6, KI#7.
Overall Plan:
  Submit TR 23.700-40 to SA#90 plenary for approval and ask for exception
  Agree a WID based on the TR conclusions.
  SA2#143E (Mar): Final evaluation and final conclusions, normative work on KI#1 and KI#2.
  Update the WID based on further conclusion
Risks:
  Conclusions on KI#3, KI#7 and potential KI#5 are dependent on RAN WG feedback.
  Different understandings on the requirement from NEST(NG.116), for example how to count the quota for different access types and EPC interworking(KI#1, KI#2), the use cases for constraint of simultaneous usage of network slice(KI#6). This may cause impossible to agree the KI conclusion.

## Slide 6: 2.4) Rel-17 Study/Work (7/12) For SA#90E
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNS_Ph2 | Study on Enhancement of Network Slicing Phase 2 | 75% ->90% | Sep, 20 -> Dec, 20 | SP-190628
Progress since SA#89-e:
  8 KIs are in total. Total 46 solutions in TR to address various KIs.
  Evaluation and interim conclusions are agreed for each key issue
  RAN impacts and dependencies:
  Further RAN2 feedback on solution#22 for KI#3 and feedback on homogeneous support for slice within the Registration area for KI#7 are expected.
  SA2 is asked to examine the candidate solutions on RAN3 study FS_NR_Slice and provide the assessment on CN impact/System level impact, if any is foreseen .
Next steps:
  Submit TR 23.700-40 v120 to SA#90 plenary for approval and ask for exception
  Agree a WID based on the TR conclusions.
  SA2#143E (Mar): Final evaluation and final conclusions, normative work on KI#1 and KI#2.
  Update the WID based on further conclusion