## Slide 1: eNPN Status Report
Peter Hedman
Ericsson

## Slide 2: eNPN status after SA2#144E (1/3)
General
  LS reply on PWS to SA1 and SA indicating SA2 is not impacted by stage 2 work on PWS
Related to Key Issue 1 (Enhancements to Support SNPN along with credentials owned by an entity separate from the SNPN):
  4 CRs to 23.501 and 2 CRs to 23.502 agreed
  CRs postponed on “Interface between AAA-S and SNPN”
  CRs postponed on “Updating the CH lists for SNPN selection” as waiting for LS reply from CT1 and SA3
  CRs postponed on handling of SUCI/SUPI format for AUSF/UDM selection
  Next Steps: Resolve postponed topics and any remaining open issue
WI Code | Work Item Title | WP | Target Date | WID#
eNPN | Enhanced support of Non-Public Networks | 20% > 50% | June, 21 | SP-200980

## Slide 3: eNPN status after SA2#144E (2/3)
Related to Key Issue 2 (NPN support for Video, Imaging and Audio for Professional Applications (VIAPA))
  1 CR agreed to 23.501 on QoS mapping
  Next Steps: Resolve any remaining open issue
Related to Key Issue 3 (Support of IMS voice and emergency services for SNPN)
  1 CR agreed to 23.501, 2 CRs agreed to 23.228 and 1 CR agreed to 23.167
  Next Steps: Resolve any remaining open issue
Related to Key Issue 4 (UE Onboarding and remote provisioning)
  6 CRs agreed to 23.501, 1 CR agreed to 23.502 and 1 CR agreed to 23.503
  1 CR postponed on handling of AUSF/UDM selection for an Onboarding UE
  TBD whether to document registration procedure as part of existing procedure or separately
  Next Steps: Resolve Editor’s notes, complete changes to e.g. 23.502 and resolve remaining open issues
WI Code | Work Item Title | WP | Target Date | WID#
eNPN | Enhanced support of Non-Public Networks | 20% > 50% | June, 21 | SP-200980

## Slide 4: eNPN status after SA2#144E (3/3)
  RAN impacts and dependencies:
  As per agreed CRs the RAN impacts are SIB related for changes related to Key issues 1, 3 and 4; new RRC indication for solutions related to Key issues 4 and additional NGAP impacts for solutions related to Key issue 4
  …
SA3 dependencies
  SA3 dependencies identified for solutions and conclusions related to key issue 1, 3 and 4.
  ...
Contentious Issue:
  KI#1: Whether AUSF or separate NF is to interact with AAA-S using non-SBI protocol
  KI#4: Selection of CP vs UP provisioning
Focus for the Next Meeting (SA2#145E):
  Progress and complete the normative work
Overall Plan:
  Complete the normative work at SA2#145e
Risks:
  Completion of the work dependent on progress in SA3 (KI#4)

## Slide 5: eNPN Status at SA#92e
Progress since SA#91-e:
  LS reply to xyz
  LS sent to xyz
  x CRs agreed to TS 23.501, x CRs agreed to TS 23.502 related to KI#y
  …
  RAN impacts and dependencies:
  RAN impacts as per agreed CRs:
    Impacts are …
Next steps:
  Maintenance, including addressing any issues and questions raised by other WGs
  …
WI Code | Work Item Title | WP | Target Date | WID#
eNPN | Enhanced support of Non-Public Networks | 20% > xx% | June, 21 | SP-200980
NOT UPDATED