## Slide 1: 5MBS Status Report
Li, Meng
Huawei

## Slide 2: 5MBS status after SA2#144e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
5MBS | Architectural enhancements for 5G multicast-broadcast services (5MBS) | 20% > 50% | June, 2021 | SP-201106
  Progress since SA#91-e:
  32 documents approved and 1 document technically endorsed.
  28 pseudo-CRs agreed to TS 23.247, 2 CRs agreed to TS 23.501, and 2 CRs agreed to TS 23.502.
  RAN impacts and dependencies:
  RAN impacts as per agreed pCRs.
Next steps:
  Resolve the open issues identified in previous meetings.
  Try to finish the normative work
  Coordinate with RAN WGs to resolve the aspects with RAN dependencies.
To be updated

## Slide 3: 5MBS status after SA2#144e (2/2)
WI Code | Work Item Title | WP | Target Date | WID#
5MBS | Architectural enhancements for 5G multicast-broadcast services (5MBS) | 20% > 50% | June, 2021 | SP-201106
General
  TS 23.247 v0.2.0 is available.
  For MBS Session join and establishment procedure, S2-2103074 is technically endorsed by SA2.
General and Architecture related
  2 pCRs are approved addressing the aspects including Architecture and Functional entities updates;
  Next step: Continue to complete the related description, add the architecture for IWK.
Principles, functionalities and concepts related
  11 pCRs are approved related to principles, functionalities and concepts.
  Next step: Continue to complete the related description, address protocol stack.
MBS session management
  14 pCRs are approved that includes Mobility, UE leave procedure, State model, Local MBS, common procedures for MBS,MBS and multicast and broadcast procedures.
  Next step: Try to complete the normative work, addressing issues for Session activation/deactivation/update
QoS and policy
  2 pCRs are approved related to QoS and Policy.
  Next step: Continue to complete the related description and update the procedures if needed.
Interworking with EPC/eMBMS for Public Safety
  Related CRs on procedures are postponed.
  Next step: Complete the principle and add the procedure.
To be updated

## Slide 4: Backup SA2#143E FS_5MBS Status Report for information

## Slide 5: 5MBS status after SA2#144e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
5MBS | Architectural enhancements for 5G multicast-broadcast services (5MBS) | 20% > 50% | June, 2021 | SP-201106
  Progress since SA#91-e:
  32 documents approved and 1 document technically endorsed.
  28 pseudo-CRs agreed to TS 23.247, 2 CRs agreed to TS 23.501, and 2 CRs agreed to TS 23.502.
  RAN impacts and dependencies:
  RAN impacts as per agreed pCRs.
Next steps:
  Resolve the open issues identified in previous meetings.
  Try to finish the normative work
  Coordinate with RAN WGs to resolve the aspects with RAN dependencies.

## Slide 6: 5MBS status after SA2#144e (2/2)
WI Code | Work Item Title | WP | Target Date | WID#
5MBS | Architectural enhancements for 5G multicast-broadcast services (5MBS) | 20% > 50% | June, 2021 | SP-201106
General
  TS 23.247 v0.2.0 is available.
  For MBS Session join and establishment procedure, S2-2103074 is technically endorsed by SA2.
General and Architecture related
  2 pCRs are approved addressing the aspects including Architecture and Functional entities updates;
  Next step: Continue to complete the related description, add the architecture for IWK.
Principles, functionalities and concepts related
  11 pCRs are approved related to principles, functionalities and concepts.
  Next step: Continue to complete the related description, address protocol stack.
MBS session management
  14 pCRs are approved that includes Mobility, UE leave procedure, State model, Local MBS, common procedures for MBS,MBS and multicast and broadcast procedures.
  Next step: Try to complete the normative work, addressing issues for Session activation/deactivation/update
QoS and policy
  2 pCRs are approved related to QoS and Policy.
  Next step: Continue to complete the related description and update the procedures if needed.
Interworking with EPC/eMBMS for Public Safety
  Related CRs on procedures are postponed.
  Next step: Complete the principle and add the procedure.