## Slide 1: SA2 work planning for Q3/Q4, 2021
Puneet Jain
SA2 Chair

## Slide 2: SA2 meetings in Q1/Q2 2021
INACTIVE
RAN1
RAN2
RAN3
RAN4
Q
U
I
E
T
P
E
R
I
O
D
WG
WG
TSG
I
N
A
C
T
I
V
E
P
E
R
I
O
D
October
December
November
January
February
March
TSG
WG
WG
TSG
WG
WG
T
S
G
#
9
1
RAN1 (4+4+5)
T
S
G
#
9
0
RAN5
RAN2/3/4
Confirmed as E-meetings by default
12-16
19-23
26-30
2-6
9-13
16-20
23-27
30-4
7-11
18-22
25-29
1-5
8-12
15-19
22-26
1-5
8-12
15-19
22-26
RAN5
RAN1
RAN2/3/4
April
June
May
29-2
5-9
12-16
19-23
26-30
3-7
10-14
17-21
24-28
31-4
7-11
14-18
5-9
T
S
G
#
9
2
RAN3/5
RAN2/4 (5+2)
RAN1 (5+2)
RAN1 (3+4)
I
N
A
C
T
I
V
E
P
E
R
I
O
D
I
N
A
C
T
I
V
E
P
E
R
I
O
D
RAN2/4 (3+4)
INACTIVE
RAN1
RAN2
RAN3
RAN4
Q
U
I
E
T
P
E
R
I
O
D
SA2 #141E
#142E
SA2 #143E
SA2 #145E
#144E
SA2 Moderated email discussion

## Slide 3: Proposed SA2 meeting plan for Q3/Q4 2021
G
O
L
D
E
N
W
E
E
K
WG
WG
TSG
July
August
Sep
TSG
WG
WG
T
S
G
#
9
3
Confirmed as E-meetings
19-23
26-30
2-6
9-13
16-20
23-27
1-3
6-10
13-17
20-24
RAN5
RAN1
RAN2/3/4
Oct
Dec
Nov
27-1
4-8
11-15
18-22
25-29
1-5
8-12
15-19
22-26
29-3
6-10
13-17
T
S
G
#
9
4
RAN 5
RAN2/3/4 (5+5)
RAN1 (5+2)
RAN1 (2+5)
SA2 #146E
(5+5)
#148E
(5)
#147E
(5)
5-9
12-16
1-2
I
N
A
C
T
I
V
E
P
E
R
I
O
D
T
H
A
N
K
S
G
I
V
I
N
G
To be Confirmed as E-meetings

## Slide 4: SA2 meetings in Q3/Q4 2021
SA2 July 2021 ad-hoc meeting [July 12 – 16, 2021] needs to be confirmed.
TSG SA will decide whether Q4 meetings will be held electronically in June 2021. SA2 Q4 meetings are planned as e-meeting. If TSG decides to schedule them as F2F then SA2 will revert to the original F2F agreed dates.
As SA2#146E will have full agenda and will span 2 weeks it is proposed to not schedule SA2 July ad-hoc.
Proposals:
  SA2 July 2021 ad-hoc meeting [July 12 – 16, 2021] is not scheduled.
  Endorse SA2#146E, SA2#147E, SA2#148E e-meeting dates as shown on slide#3.

## Slide 5: Rel-18 SID/WID Proposals
Rel-18 SID/WID proposals may be submitted to SA2#145E(May 2021) and onwards. Rel-18 SID/WID must contain the TU estimates for completing the work.
For SA2#145E(May 2021) e-meetings Rel-18 SID/WID should be submitted only for discussion/information. No Rel-18 SID/WID will be approved at SA2#145E(May 2021).
Rel-18 SID/WID may be approved in SA2#146E (Aug 2021).
Scheduling of Rel-18 SID/WID in Q4, 2021 will depend on TSG SA Approval (e.g., based on “early” prioritization discussion at TSG SA#93-e).
  SID/WID shall be TSG SA approved for scheduling in Q4.

## Slide 6: Rel-18 content decisions timeline
2021
Q1
2022
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Rel-18 “early” prioritization at SA#93-e
Rel-17 stage 3 completion at CT#95
Rel-18 Stage 1
study phase (SA1)
Rel-18 Stage 1
80% complete
Rel-18 SA2 proposals
discussed in Q2, approval in Q3
Discussion on RAN1/2/3 + ‘New’ RAN4 items
RAN Rel-18 package approval at RAN#94
Rel-18 Stage 1 100% complete
SA2 Rel-18 prioritization at SA#94
Workshop after RAN#92
Rel-18 SA2 Study Phase

## Slide 7: TEI18 Proposals
TEI18 proposals can be submitted to SA2#147E(Oct 2021) onwards. Each TEI18 proposal must contain the WID and TU estimates for completing the work.
For SA2#147E(Oct 2021) e-meetings TEI18 proposal should be submitted only for discussion/information.
TEI18 may be approved in SA2#148E (Nov 2021).
Scheduling of TEI18 will be discussed during work planning meeting in Q4 21 and/or Q1 22.
  To be discussed further

## Slide 8: SA2#146E Dates/Agenda
Preliminary Agenda (subjected to changes):
  Full agenda (4.X, 5.X, 6.X, 7.X, 8.X, 9.X)
  Any Rel-17 Exception Handling will be priority
  To be discussed further
Docs request | 10 Aug 2021 (Tuesday) | 2359 UTC
Docs submission | 10 Aug 2021 (Tuesday) | 2359 UTC
Start of e-meeting | 16 Aug 2021 (Monday), CC#1 | 0000 UTC
Deadlines#1 | Applies to AI# 4.X, 5.X, 6.X, 7.X | 
Revisions by | 18 Aug 2021 (Wednesday) | 1600 UTC
Final Comments | 19 Aug 2021 (Thursday) | 1600 UTC
Close of AI# 4.X, 5.X, 6.X, 7.X | 20 Aug 2021 (Friday), CC#2 | 1600 UTC
Upload Approved docs | 23 Aug 2021 (Monday), CC#3 | 1600 UTC
Deadlines#2 | Applies to AI# 8.X, 9.X | 
Revisions | 24 Aug 2021 (Tuesday) | 1600 UTC
Final Comments | 25 Aug 2021 (Wednesday) | 1600 UTC
 | 26 Aug 2021 (Thursday), CC4 | 
Close of e-meeting | 27 Aug 2021 (Friday), CC#5 | 1700 UTC
Upload Approved docs | 30 Aug 2021 (Monday) | 1700 UTC

## Slide 9: SA2#147E Dates/Agenda
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 8.X : Rel-17 maintenance – RAN alignment, corrections etc.
  No AI 5.X, 6.X, 7.X
  Rel-18 SID/WID scheduling (based on TSG SA approval/guidance)
  To be discussed further
Docs request | 11 Oct 2021 (Monday) | 2359 UTC
Docs submission | 11 Oct 2021 (Monday) | 2359 UTC
Start of e-meeting | 18 Oct 2021 (Monday) | 0000 UTC
Revisions | 20 Oct 2021 (Wednesday) | 1600 UTC
Final Comments | 21 Oct 2021 (Thursday) | 1600 UTC
Close of e-meeting | 22 Oct 2021 (Friday) | 1700 UTC
Upload Approved docs | 25 Oct 2021 (Monday) | 1700 UTC

## Slide 10: SA2#148E Dates/Agenda
Preliminary Agenda (subjected to changes):
  Full agenda (4.X, 5.X, 6.X, 7.X, 8.X, 9.X)
  Rel-18 SID/WID scheduling (based on TSG SA approval/guidance)
  To be discussed further
Docs request | 08 Nov 2021 (Monday) | 2359 UTC
Docs submission | 08 Nov 2021 (Monday) | 2359 UTC
Start of e-meeting | 15 Nov 2021 (Monday) | 0000 UTC
Revisions | 17 Nov 2021 (Wednesday) | 1700 UTC
Final Comments | 18 Nov 2021 (Thursday) | 1700 UTC
Close of e-meeting | 19 Nov 2021 (Friday) | 1800 UTC
Upload Approved docs | 22 Nov 2021 (Monday) | 1800 UTC

## Slide 11: Summary of Proposals for Endorsement
SA2 July 2021 ad-hoc meeting [July 12 – 16, 2021] will not be scheduled.
SA2#146E, SA2#147E, SA2#148E e-meeting dates (as shown on slide#3) are endorsed.
Rel-18 SID/WID Proposals (as shown on slide#5) are endorsed.

## Slide 12: Thank You !
Puneet Jain
Chair of 3GPP SA2
puneet.jain@intel.com
www.3gpp.org