## Slide 1: eNS_Ph2 Status Report after SA2#145E
Jinguo Zhu
ZTE

## Slide 2: eNS_Ph2 status after SA2#145e (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
eNS_Ph2 | Enhancement of Network Slicing Phase 2 | 50% -> 85% | Jun, 21 | SP-200976
General
  KI#1,KI#2,KI#3,KI#4,KI#5,KI#6 andKI#7 are progress well. 30 CRs are approved.
  Open issues remain for KI#1,2,4,5 and 7
Key Issue #1: Support of network slice related quota on the maximum number of Ues
  Focus on Access type, EPC interworking, roaming, NSACF discovery etc.
  Inter AMF mobility: revert agreement in SA2#144E
Key Issue #2: Support of network slice related quota on the maximum number of PDU Sessions
  NSAC control for number of PDU Sessions is agreed for roaming and non roaming
Key Issue #3: limitation of data rate per network slice in UL and DL per UE
  Further clarification on agreed CR

## Slide 3: eNS_Ph2 status after SA2#145e (2/3)
WI Code | Work Item Title | WP | Target Date | WID#
eNS_Ph2 | Enhancement of Network Slicing Phase 2 | 50% -> 85% | Jun, 21 | SP-200976
Key Issue #4: Support for network slice quota event notification in a network slice
  Further clarification on agreed CR.
Key Issue #5: Dynamic adjustment to meet the limitation of data rate per network slice in UL and DL.
  Further clarification on agreed CR.
  Description on NWDAF based approach
Key Issue #6: Constraints on simultaneous use of the network slice
  501 CR and 502 CR are approved.
Key Issue #7: Support of 5GC assisted cell selection to access network slice
  501 CR and 502 CR are approved
  LS to RAN2/RAN3 on the discussion of additional information provided from AMF to NG-RAN

## Slide 4: eNS_Ph2 status after SA2#145e (3/3)
  RAN impacts and dependencies:
  The completion of KI#7 depends on further RAN2 and RAN3 response on additional information provided from AMF to NG-RAN. SA2#146E is overlapping with RAN2#115E and early decisions is required during RAN2#115e.
Contentious Issue:
  - How to enable/disable the early notification control in AMF.
Focus for the Next Meeting (SA2#146e):
  Complete the open issues in exception list for eNS_Ph2(S2-2105181) per approval by SA#93E
Overall Plan:
  Achieve 100% completion after SA2 #146e.
Risk:
  None.