## Slide 1: SA WG2 Status report for MUSIM
Sašo Stojanovski
Intel

## Slide 2: FS_MUSIM and MUSIM status at SA#92e
General
  TR 23.761 v1.5.0 sent to SA#92e plenary for approval
  8 CRs on 23.401/23.501/23.502 submitted to SA#92e for approval
    Two of the CRs (S2-2105148, S2-2105149) were approved as a Working Agreement
  Exception sheet coming to SA#92e submitted for approval
RAN dependencies:
  Alignment needed with RAN2 conclusions. It is noted that SA2#146e and RAN2#115e meetings have fully overlapping dates (16-27 Aug 2021). The successful completion of MUSIM in Q3 requires early decisions during RAN2#115e meeting impacting the MUSIM work in SA2.
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 95% > 100% | Mar, 21 | SP-200297
WI Code | Work Item Title | WP | Target Date | WID#
MUSIM | System enablers for Multi-USIM devices | 20% > 90% | June, 21 | SP-210091

## Slide 3: FS_MUSIM status after SA2#145e
General
  1 pCR approved to close Editor’s notes on KI#3
  Latest TR version: TR 23.761 v1.5.0 available here
Next steps:
  Send TR 23.761 to SA#92e plenary for approval
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 98% > 100% | Mar, 21 | SP-200297

## Slide 4: MUSIM Status after SA2#145e
WI Code | Work Item Title | WP | Target Date | WID#
MUSIM | System enablers for Multi-USIM devices | 65% > 90% | June, 21 | SP-210091
Progress since SA#91E:
  Normative CRs approved for stage 2 specifications - TS 23.401/23.501/23.502
    Functional description (S2-2105148, S2-2105149) – Working Agreement
    Capability exchange (S2-2105116, S2-2105117)
    Paging Cause (S2-2105119, S2-2105120)
    Reject Paging (« Busy ») indication (S2-2105151)
    Leaving procedure for 5GS (S2-2105152)
  LS OUT to RAN2 on rejection of RAN paging (S2-2105150)
  Exception sheet agreed (S2-2105178)
RAN dependencies:
  Alignment needed with RAN2 conclusions. It is noted that SA2#146e and RAN2#115e meetings have fully overlapping dates (16-27 Aug 2021). The successful completion of MUSIM in Q3 requires early decisions during RAN2#115e meeting impacting the MUSIM work in SA2.

## Slide 5: MUSIM status after SA2#145e
  RAN and SA3 impacts and dependencies:
  Alignment needed with RAN2 conclusions.
  Check SA2 working assumptions against SA3 study conclusions.
Contentious Issue:
  There is no conclusion in TR 23.761 on how to support paging reception for 5GS and/or whether it is needed.
Focus for the Next Meeting (SA2#146E):
  Alignment with RAN2 conclusions (including paging reception for 5GS, rejection of RAN paging and coordinated leaving for 5GC/NR) to complete the items in the WI exception
  Maintenance
Overall Plan:
  Normative work expected to be completed by SA#93
Risks:
  It is noted that SA2#146e and RAN2#115e meetings have fully overlapping dates (16-27 Aug 2021). The successful completion of MUSIM in Q3 requires early decisions during RAN2#115e meeting impacting the MUSIM work in SA2.