## Slide 1: eNPN Status Report
Peter Hedman
Ericsson

## Slide 2: eNPN status after SA2#145E (1/3)
General
  No LS sent from SA2#145e
  Exception request, see S2-2105098, with items related to KI#1, KI#3 and KI#4.
    Note: CR in S2-2105213 related to KI#2, with an open issue on exposure, was agreed after SA2#145e approval of the exception request
Related to Key Issue 1 (Enhancements to Support SNPN along with credentials owned by an entity separate from the SNPN):
  9 (7 new and 2 updated) CRs to 23.501 and 3 (new) CRs to 23.502 agreed
  LS and CR postponed on “updating the Credentials Holder controlled lists for SNPN selection” (i.e. whether UPU or SoR)
  LS and CR postponed on “UE capabilities indication in UPU” (i.e. how UE capability gets known to the UDM)
  CR postponed on how to support CH selection with SUPI of IMSI type
  Next Steps: Resolve items added to exception request and maintenance for other items
WI Code | Work Item Title | WP | Target Date | WID#
eNPN | Enhanced support of Non-Public Networks | 50% > 85% | June, 21 | SP-200980

## Slide 3: eNPN status after SA2#145E (2/3)
Related to Key Issue 2 (NPN support for Video, Imaging and Audio for Professional Applications (VIAPA))
  2 new CRs and 1 updated CR to 23.501 agreed
  Open issue on how to use exposure capabilities (e.g. QoS notification, other capabilities) that might be beneficial to leverage between underlay network and overlay network
  Next Steps: Resolve item added to exception request and maintenance for other items
Related to Key Issue 3 (Support of IMS voice and emergency services for SNPN)
  1 new CR and 1 updated CR agreed to 23.501, 1 updated CR agreed to 23.228 and 1 updated CR agreed to 23.167
  Whether SNPN can support IMS services from more than one independent IMS provider without normative change is FFS
  Next Steps: Resolve item added to exception request and maintenance for other items
Related to Key Issue 4 (UE Onboarding and remote provisioning)
  4 new and 3 updated CRs agreed to 23.501, 1 new and 1 updated CR agreed to 23.502 and 1 updated CR agreed to 23.503
  Onboarding architecture dependent on SA3 feedback
  CP provisioning of credentials for NSSAA and/or secondary authentication dependent on SA3 feedback
  Open issue on how PVS addresses provided to ONN
  Open issue whether AMF re-allocation is supported and handling of AMF implementation specific timer in this case
  Details of Registration procedure to be clarified
  Next Steps: Resolve item added to exception request and maintenance for other items
WI Code | Work Item Title | WP | Target Date | WID#
eNPN | Enhanced support of Non-Public Networks | 50% > 85% | June, 21 | SP-200980

## Slide 4: eNPN status after SA2#145E (3/3)
  RAN impacts and dependencies:
  As per agreed CRs the RAN impacts are SIB related for changes related to Key issues 1, 3 and 4; new RRC indication for solutions related to Key issues 4 and potentially additional NGAP impacts for solutions related to Key issue 4
SA3 dependencies
  SA3 dependencies identified functionality related to support of Credentials Holder, support of IMS voice and emergency, and support for UE onboarding.
  SA3 feedback expected on e.g. Onboarding architrecture related to DCS and CP provisioning of credentials for NSSAA and/or secondary authentication
Contentious Issue:
  Whether to use UPU or SoR for updating CH controlled SNPN selection lists
Focus for the Next Meeting (SA2#146E):
  Complete items for exception and maintenance for anything else including changes required to support input from other WGs
Overall Plan:
  Complete the items for exception at SA2#146e and maintenance for anything else
Risks:
  Completion of the work dependent on progress in SA3 (KI#4)

## Slide 5: eNPN Status at SA#92e
Progress since SA#91-e:
  LS reply on PWS to SA1 and SA indicating SA2 is not impacted by stage 2 work on PWS
  12 CRs agreed to TS 23.501, 5 CRs agreed to TS 23.502 related to KI#1
  3 CRs agreed to TS 23.501 related to KI#2
  2 CRs agreed to TS 23.501, 2 CRs agreed to TS 23.228, 1 CR agreed to 23.167 related to KI#3
  10 CRs agreed to TS 23.501, 2 CRs agreed to TS 23.502, 1 CR agreed to 23.503 related to KI#4
  Exception request, see S2-2105098, with items related to KI#1, KI#3 and KI#4.
    Note: CR in S2-2105213 related to KI#2, with an open issue on exposure, was agreed after SA2#145e approval of the exception request
  RAN impacts and dependencies:
  RAN impacts as per agreed CRs:
    Impacts are SIB related for changes related to Key issues 1, 3 and 4; new RRC indication for solutions related to Key issues 4 and potentially additional NGAP impacts for solutions related to Key issue 4
Next steps:
  Resolve items as per requested exception (SA3 feedback expected for some items)
  Maintenance for other aspects, including addressing any issues and questions raised by other WGs
WI Code | Work Item Title | WP | Target Date | WID#
eNPN | Enhanced support of Non-Public Networks | 20% > 85% | June, 21 -> Sept, 21 | SP-200980